## Template Civil
Project | Project Name
Work Package: | Civil
Work Item: | Column: Q | Start Row: 11 | End Row: 11
Data Date: | Column: I | Start Row: 6 | End Row: 6 | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name: | Civil Top Sheet
Plan Scope | Column: Q | Start Row: 21 | End Row: 21
Actuals till date | Column: E | Start Row: 29 | End Row: 29
Plan for the Month | Column: R | Start Row: 21 | End Row: 21
Actual for the Month | Column: S | Start Row: 21 | End Row: 21
Today | Column: E | Start Row: 40 | Start Row: 40
DWG Available | Column: U | Start Row: 21 | End Row: 21
Project | Project Name
Work Package: | Structure
Work Item: | Column: Q | Start Row: 11 | End Row: 11
Data Date: | Column: I | Start Row: 6 | End Row: 6 | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name: | Structure Fab Topsheet
Plan Scope | Column: Q | Start Row: 21 | End Row: 21
Actuals till date | Column: E | Start Row: 29 | End Row: 29
Plan for the Month | Column: R | Start Row: 21 | End Row: 21
Actual for the Month | Column: S | Start Row: 21 | End Row: 21
Today | Column: E | Start Row: 40 | Start Row: 40
DWG Available | Column: U | Start Row: 21 | End Row: 21
Project | Project Name
Work Package: | Structure
Work Item: | Column: Q | Start Row: 11 | End Row: 11
Data Date: | Column: I | Start Row: 6 | End Row: 6 | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name: | Structure Erection Topsheet
Plan Scope | Column: Q | Start Row: 21 | End Row: 21
Actuals till date | Column: E | Start Row: 29 | End Row: 29
Plan for the Month | Column: R | Start Row: 21 | End Row: 21
Actual for the Month | Column: S | Start Row: 21 | End Row: 21
Today | Column: E | Start Row: 40 | Start Row: 40
DWG Available | Column: U | Start Row: 21 | End Row: 21

## Civil Top Sheet
Project : Project Name
DPR
[5 empty] | REPORT DATE | 27-09-2022 | WEATHER : | Sunny
PMC:-KPMG
Contractor :- |  |  |  |  | REPORTING DATE | 27-09-2022 | WORKING : | Full day
OVERALL PHYSICAL PROGRESS
Month | 2022-09-01 |  | Nature of Work | Civil
[10 empty] | Don’t change it |  | RCC |  |  |  |  | 2022-09-30 | 2022-09-01 | 2022-03-31
[10 empty] | Area | UOM | Scope | Plan for the month | Actual for the month | Total work done till current month | Drawings Released Till Date
[10 empty] | Yard equipments & conveyors | Cum | 5000 | 0 | 0 | 0 | 0
[10 empty] | Iron Ore & fluxes to BF-5 | Cum | 4000 | 325 | 0 | 0 | 813
[10 empty] | Coke Circuit from COB-5 to BF-5 | Cum | 4010 | 450 | 13 | 13 | 3450
[10 empty] | BF fines to existing conveyor 18J5C1 | Cum | 1250 | 0 | 0 | 0 | 0
[10 empty] | Conveyor route from JH 70 to PCI bunker | Cum | 1250 | 0 | 0 | 0 | 0
[10 empty] | Bunker Building | Cum | 1200 | 600 | 0 | 0 | 1200
[9 empty] | 842 | Sinter and pellet to BF-5 | Cum | 2000 | 0 | 0 | 0 | 540
[10 empty] | Limestone and dolomite to LCP | Cum | 2200 | 0 | 0 | 0 | 0
[10 empty] | Total |  | 20910 | 1375 | 13 | 13 | 6003
278
114
Total Quantity till date | Cum | 13 |  |  | Total Drawings Available | Cum | 6003
TODAY'S PROGRESS
Nature of Work | Civil | 2022-09-01
Area | UOM | Today's Progress | Asking Rate
Iron Ore & fluxes to BF-5 | No's | 0 | 10
Coke Circuit from COB-5 to BF-5 | No's | 0 | 15
BF fines to existing conveyor 18J5C1 | No's | 0 | 0
Conveyor route from JH 70 to PCI bunker | No's | 0 | 0
Bunker Building | No's | 0 | 19
Sinter and pellet to BF-5 | No's | 0 | 0
Limestone and dolomite to LCP | No's | 0 | 0
Today's Quantity |  | 0 | 44
REMARKS / ISSUES OF THE DAY
1)
2)
3)
4)
Rain Status:

## Structure Fab Topsheet
Project :Project Name
DPR
[5 empty] | REPORT DATE | 27-09-2022 | WEATHER : | Sunny
PMC:-KPMG
Contractor :- |  |  |  |  | REPORTING DATE | 27-09-2022 | WORKING : | Full day
OVERALL PHYSICAL PROGRESS
Month | 2022-09-01 |  | Nature of Work | Structure Fabrication
[10 empty] | Don’t change it |  | Structure Fabrication |  |  |  |  | 2022-09-30 | 2022-09-01 | 2022-03-31
[10 empty] | Area | UOM | Scope | Plan for the month | Actual for the month | Total work done till current month | Drawings Released Till Date
[10 empty] | Yard equipments & conveyors | MT | 612 | 0 | 0 | 0 | 0
[10 empty] | Iron Ore & fluxes to BF-5 | MT | 5262 | 0 | 0 | 0 | 4770
[10 empty] | Coke Circuit from COB-5 to BF-5 | MT | 4650 | 402 | 5 | 115.689 | 3400
[10 empty] | BF fines to existing conveyor 18J5C1 | MT | 1400 | 0 | 0 | 0 | 0
[10 empty] | Conveyor route from JH 70 to PCI bunker | MT | 1082 | 0 | 0 | 0 | 0
[10 empty] | Bunker Building | MT | 1216 | 0 | 0 | 0 | 1216
[9 empty] | 842 | Sinter and pellet to BF-5 | MT | 4000 | 0 | 0 | 0 | 800
[10 empty] | Limestone and dolomite to LCP | MT | 2200 | 0 | 0 | 0 | 0
[10 empty] | Total |  | 20422 | 402 | 5 | 115.689 | 10186
278
114
Total Quantity till date | MT | 115.689 |  |  | Total Drawings Available | MT | 10186
TODAY'S PROGRESS
Nature of Work | Structure Fabrication | 2022-09-01
Area | UOM | Today's Progress | Asking Rate
Iron Ore & fluxes to BF-5 | No's | 0 | 0
Coke Circuit from COB-5 to BF-5 | No's | 0 | 13
BF fines to existing conveyor 18J5C1 | No's | 0 | 0
Conveyor route from JH 70 to PCI bunker | No's | 0 | 0
Bunker Building | No's | 0 | 0
Sinter and pellet to BF-5 | No's | 0 | 0
Limestone and dolomite to LCP | No's | 0 | 0
Today's Quantity |  | 0 | 13
REMARKS / ISSUES OF THE DAY
1)
2)
3)
4)
Rain Status:

## Structure Erection Topsheet
Project : Project Name
DPR
[5 empty] | REPORT DATE | 27-09-2022 | WEATHER : | Sunny
PMC:-KPMG
Contractor :- |  |  |  |  | REPORTING DATE | 27-09-2022 | WORKING : | Full day
OVERALL PHYSICAL PROGRESS
Month | 2022-09-01 |  | Nature of Work | Structure Erection
[10 empty] | Don’t change it |  | Structure Erection |  |  |  |  | 2022-09-30 | 2022-09-01 | 2022-03-31
[10 empty] | Area | UOM | Scope | Plan for the month | Actual for the month | Total work done till current month | Drawings Released Till Date
[10 empty] | Yard equipments & conveyors | MT | 612 | 0 | 0 | 0 | 0
[10 empty] | Iron Ore & fluxes to BF-5 | MT | 5262 | 0 | 0 | 0 | 4770
[10 empty] | Coke Circuit from COB-5 to BF-5 | MT | 4650 | 100 | 0 | 0 | 3400
[10 empty] | BF fines to existing conveyor 18J5C1 | MT | 1400 | 0 | 0 | 0 | 0
[10 empty] | Conveyor route from JH 70 to PCI bunker | MT | 1082 | 0 | 0 | 0 | 0
[10 empty] | Bunker Building | MT | 1216 | 0 | 0 | 0 | 1216
[9 empty] | 842 | Sinter and pellet to BF-5 | MT | 4000 | 0 | 0 | 0 | 800
[10 empty] | Limestone and dolomite to LCP | MT | 2200 | 0 | 0 | 0 | 0
[10 empty] | Total |  | 20422 | 100 | 0 | 0 | 10186
278
114
Total Quantity till date | MT | 0 |  |  | Total Drawings Available | MT | 10186
TODAY'S PROGRESS
Nature of Work | Structure Erection | 2022-09-01
Area | UOM | Today's Progress | Asking Rate
Iron Ore & fluxes to BF-5 | No's | 0 | 0
Coke Circuit from COB-5 to BF-5 | No's | 0 | 3
BF fines to existing conveyor 18J5C1 | No's | 0 | 0
Conveyor route from JH 70 to PCI bunker | No's | 0 | 0
Bunker Building | No's | 0 | 0
Sinter and pellet to BF-5 | No's | 0 | 0
Limestone and dolomite to LCP | No's | 0 | 0
Today's Quantity |  | 0 | 3
REMARKS / ISSUES OF THE DAY
1)
2)
3)
4)
Rain Status:

## Backup Data
Master Data
Sr No | Date | Area | Nature of Work | UOM | Quantity | Remarks
1 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
2 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
3 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
4 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
5 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
6 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
7 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
8 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
9 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
10 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
11 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
12 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
13 | 2022-05-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
14 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
15 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
16 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
17 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
18 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
19 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
20 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
21 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
22 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
23 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
24 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
25 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
26 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
27 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
28 | 2022-05-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
29 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
30 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
31 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
32 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
33 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
34 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
35 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
36 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
37 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
38 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
39 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
40 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
41 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
42 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
43 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
44 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
45 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
46 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
47 | 2022-05-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
48 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
49 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
50 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
51 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
52 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
53 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
54 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
55 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
56 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
57 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
58 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
59 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
60 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
61 | 2022-05-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
62 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
63 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
64 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
65 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
66 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
67 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
68 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
69 | 2022-05-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
70 | 2022-05-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
71 | 2022-05-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
72 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
73 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
74 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
75 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
76 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
77 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
78 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
79 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
80 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
81 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
82 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
83 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
84 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
85 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
86 | 2022-05-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
87 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
88 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
89 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
90 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
91 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
92 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
93 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
94 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
95 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
96 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
97 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
98 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
99 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
100 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
101 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
102 | 2022-05-20 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
1 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
2 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
3 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
4 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
5 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
6 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
7 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
8 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
9 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
10 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
11 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
12 | 2022-05-21 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
13 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
14 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
15 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
16 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
17 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
18 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
19 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
20 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
21 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
22 | 2022-05-23 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
23 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
24 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
25 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
26 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
27 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
28 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
29 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
30 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
31 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
32 | 2022-05-24 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
33 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
34 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
35 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
36 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
37 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
38 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
39 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
40 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
41 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
42 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
43 | 2022-05-25 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
44 | 2022-05-26 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
45 | 2022-05-26 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
46 | 2022-05-27 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
47 | 2022-05-27 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
48 | 2022-05-27 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
49 | 2022-05-27 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
50 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
51 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
52 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
53 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
54 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
55 | 2022-05-28 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
56 | 2022-05-30 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
57 | 2022-05-30 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
58 | 2022-05-30 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
59 | 2022-05-30 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
60 | 2022-05-30 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
61 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
62 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
63 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
64 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
65 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
66 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
67 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
68 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
69 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
70 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
71 | 2022-06-01 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
72 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
73 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
74 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
75 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
76 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
77 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
78 | 2022-06-02 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
79 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
80 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
81 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
82 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
83 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
84 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
85 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
86 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
87 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
88 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
89 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
90 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
91 | 2022-06-03 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
92 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
93 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
94 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
95 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
96 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
97 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
98 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
99 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
100 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
101 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
102 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
103 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
104 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
105 | 2022-06-04 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
106 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
107 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
108 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
109 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
110 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
111 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
112 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
113 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
114 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
115 | 2022-06-06 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
116 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
117 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
118 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
119 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
120 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
121 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
122 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
123 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
124 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
125 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
126 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
127 | 2022-06-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
128 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
129 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
130 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
131 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
132 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
133 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
134 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
135 | 2022-06-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
136 | 2022-06-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
137 | 2022-06-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
138 | 2022-06-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
139 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
140 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
141 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
142 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
143 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
144 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
145 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
146 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
147 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
148 | 2022-06-11 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
149 | 2022-06-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
150 | 2022-06-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
151 | 2022-06-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
152 | 2022-06-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
153 | 2022-06-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
154 | 2022-06-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
155 | 2022-06-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
156 | 2022-06-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
157 | 2022-06-15 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
158 | 2022-06-15 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
159 | 2022-06-15 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
160 | 2022-06-15 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
161 | 2022-06-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
162 | 2022-06-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
163 | 2022-06-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
164 | 2022-06-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
165 | 2022-06-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
166 | 2022-06-17 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
167 | 2022-07-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
168 | 2022-07-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
169 | 2022-07-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
170 | 2022-07-16 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
171 | 2022-07-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
172 | 2022-07-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
173 | 2022-07-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
174 | 2022-07-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
175 | 2022-07-18 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
176 | 2022-07-19 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
177 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
178 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
179 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
180 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
181 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
182 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
183 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
184 | 2022-07-25 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
185 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
186 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
187 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
188 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
189 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
190 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
191 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
192 | 2022-07-26 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
193 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
194 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
195 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
196 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
197 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
198 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
199 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
200 | 2022-07-27 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
201 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
202 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
203 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
204 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
205 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
206 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
207 | 2022-07-28 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
208 | 2022-07-28 | Coke Circuit from COB-5 to BF-5 | Structure Fabrication | MT | 57
209 | 2022-08-02 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
210 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
211 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
212 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
213 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
214 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
215 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
216 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
217 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
218 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
219 | 2022-08-03 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
220 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
221 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
222 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
223 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
224 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
225 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
226 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
227 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
228 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
229 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
230 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
231 | 2022-08-04 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
232 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
233 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
234 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
235 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
236 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
237 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
238 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
239 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
240 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
241 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
242 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
243 | 2022-08-05 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
244 | 2022-08-06 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
245 | 2022-08-06 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
246 | 2022-08-06 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
247 | 2022-08-06 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
248 | 2022-08-20 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
249 | 2022-08-20 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
250 | 2022-08-20 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
251 | 2022-08-20 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
252 | 2022-08-20 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
253 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
254 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
255 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
256 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
257 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
258 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
259 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
260 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
261 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
262 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
263 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
264 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
265 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
266 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
267 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
268 | 2022-08-22 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
269 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
270 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
271 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
272 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
273 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
274 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
275 | 2022-08-23 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
276 | 2022-08-24 | Coke Circuit from COB-5 to BF-5 | Structure Fabrication | MT | 53.689
277 | 2022-08-24 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
278 | 2022-08-24 | Iron Ore & fluxes to BF-5 | Pilling | No's | 1
279 | 2022-09-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
280 | 2022-09-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
281 | 2022-09-07 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
282 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
283 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
284 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
285 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
286 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
287 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
288 | 2022-09-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
289 | 2022-09-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
290 | 2022-09-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
291 | 2022-09-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
292 | 2022-09-09 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
293 | 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
294 | 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
295 | 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
296 | 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
297 | 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
298 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
299 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
300 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
301 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
302 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
303 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 1
304 | 2022-09-12 | Coke Circuit from COB-5 to BF-5 | Civil | Cum | 6.5
305 | 2022-09-08 | Coke Circuit from COB-5 to BF-5 | PCC | Cum | 17
306 | 2022-09-13 | Coke Circuit from COB-5 to BF-5 | Civil | Cum | 6.5
307 | 2022-09-13 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 4
308 | 2022-09-14 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 9
309 | 2022-09-15 | Coke Circuit from COB-5 to BF-5 | Pilling | No's | 6
| 2022-09-10 | Coke Circuit from COB-5 to BF-5 | Structure Fabrication | MT | 5

## Drawing Status
Area | Nature of Work | UOM | Drawing Quantity | Scope |  | Pipe Laying
Yard equipments & conveyors | Pilling | No's | 0
Yard equipments & conveyors | Civil | Cum | 0 | 5000
Yard equipments & conveyors | Structure Fabrication | MT | 0 | 612
Yard equipments & conveyors | Structure Erection | MT | 0 | 612
Yard equipments & conveyors | Mechanical | MT | 1200 | 1200
Yard equipments & conveyors | Electrical | MT
Iron Ore & fluxes to BF-5 | Pilling | No's | 100 | 350
Iron Ore & fluxes to BF-5 | Civil | Cum | 813 | 4000
Iron Ore & fluxes to BF-5 | Structure Fabrication | MT | 4770 | 5262
Iron Ore & fluxes to BF-5 | Structure Erection | MT | 4770 | 5262
Iron Ore & fluxes to BF-5 | Mechanical | MT | 1180 | 1180
Iron Ore & fluxes to BF-5 | Electrical | MT
Coke Circuit from COB-5 to BF-5 | Pilling | No's | 392 | 392
Coke Circuit from COB-5 to BF-5 | Civil | Cum | 3450 | 4010
Coke Circuit from COB-5 to BF-5 | Structure Fabrication | MT | 3400 | 4650
Coke Circuit from COB-5 to BF-5 | Structure Erection | MT | 3400 | 4650
Coke Circuit from COB-5 to BF-5 | Mechanical | MT | 950 | 950
Coke Circuit from COB-5 to BF-5 | Electrical | MT
BF fines to existing conveyor 18J5C1 | Pilling | No's | 0 | 108
BF fines to existing conveyor 18J5C1 | Civil | Cum | 0 | 1250
BF fines to existing conveyor 18J5C1 | Structure Fabrication | MT | 0 | 1400
BF fines to existing conveyor 18J5C1 | Structure Erection | MT | 0 | 1400
BF fines to existing conveyor 18J5C1 | Mechanical | MT | 400 | 400
BF fines to existing conveyor 18J5C1 | Electrical | MT
Conveyor route from JH 70 to PCI bunker | Pilling | No's
Conveyor route from JH 70 to PCI bunker | Civil | Cum | 0 | 1250
Conveyor route from JH 70 to PCI bunker | Structure Fabrication | MT | 0 | 1082
Conveyor route from JH 70 to PCI bunker | Structure Erection | MT | 0 | 1082
Conveyor route from JH 70 to PCI bunker | Mechanical | MT | 260 | 260
Conveyor route from JH 70 to PCI bunker | Electrical | MT
Bunker Building | Pilling | No's
Bunker Building | Civil | Cum | 1200 | 1200
Bunker Building | Structure Fabrication | MT | 1216 | 1216
Bunker Building | Structure Erection | MT | 1216 | 1216
Bunker Building | Mechanical | MT | 106.25 | 106.25
Bunker Building | Electrical | MT
Sinter and pellet to BF-5 | Pilling | No's
Sinter and pellet to BF-5 | Civil | Cum | 540 | 2000
Sinter and pellet to BF-5 | Structure Fabrication | MT | 800 | 4000
Sinter and pellet to BF-5 | Structure Erection | MT | 800 | 4000
Sinter and pellet to BF-5 | Mechanical | MT | 850 | 1000
Sinter and pellet to BF-5 | Electrical | MT
Limestone and dolomite to LCP | Pilling | No's
Limestone and dolomite to LCP | Civil | Cum | 0 | 2200
Limestone and dolomite to LCP | Structure Fabrication | MT | 0 | 2200
Limestone and dolomite to LCP | Structure Erection | MT | 0 | 2200
Limestone and dolomite to LCP | Mechanical | MT | 160 | 320
Limestone and dolomite to LCP | Electrical | MT | 0 | 800
612
5262
4650
1400
1082
1216
4000
2200

## Pile Tracker
Sr No | Location | Area | Pile ID | Date of Casting | Dia of Pile (m) | Depth from EGL (m) | Concrete Depth (m) | Reinforcement (m) | Tentative Concrete Quantity (cum) | Month
1 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 13 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
2 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 1 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
3 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 19 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
4 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 17 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
5 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 15 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
6 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 8 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
7 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 6 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
8 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 2 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
9 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 12 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
10 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 10 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
11 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 20 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
12 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 14 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
13 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 4 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
14 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 3 | 2022-05-23 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
15 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 31 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
16 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 32 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
17 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 16 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
18 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 11 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
19 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 9 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
20 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 36 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
21 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 33 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
22 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 34 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
23 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 22 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
24 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 21 | 2022-05-24 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
25 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 30 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
26 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 7 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
27 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 5 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
28 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 27 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
29 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 18 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
30 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 28 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
31 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 26 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
32 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 29 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
33 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 24 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
34 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 23 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
35 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 35 | 2022-05-25 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
36 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 86 | 2022-05-26 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
37 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 25 | 2022-05-26 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
38 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 89 | 2022-05-27 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
39 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 87 | 2022-05-27 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
40 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 85 | 2022-05-27 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
41 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 88 | 2022-05-27 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
42 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 92 | 2022-05-28 | 0.6 | 15 | 14.025 | 0.50053 | 0.29123 | May
43 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 91 | 2022-05-28 | 0.6 | 15 | 14.025 | 0.50053 | 0.29123 | May
44 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 90 | 2022-05-28 | 0.6 | 15 | 14.025 | 0.50053 | 0.29123 | May
45 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 29 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
46 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 31 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
47 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 32 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
48 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 128 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
49 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 131 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
50 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 125 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
51 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 126 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
52 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 129 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
53 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 94 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
54 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 93 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
55 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 102 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
56 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 113 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
57 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 114 | 2022-05-12 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
58 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 103 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
59 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 116 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
60 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 105 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
61 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 106 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
62 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 115 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
63 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 123 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
64 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 124 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
65 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 130 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
66 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 127 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
67 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 132 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
68 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 30 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
69 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 26 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
70 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 21 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
71 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 13 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
72 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 14 | 2022-05-13 | 0.6 | 16 | 14.025 | 0.53581 | 0.29123 | May
73 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 10 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
74 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 9 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
75 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 22 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
76 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 25 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
77 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 18 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
78 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 17 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
79 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 119 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
80 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 107 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
81 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 108 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
82 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 121 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
83 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 120 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
84 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 117 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
85 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 122 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
86 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 95 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
87 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 96 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
88 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 89 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
89 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 91 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
90 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 90 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
91 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 92 | 2022-05-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
92 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 86 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
93 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 85 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
94 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 88 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
95 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 87 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
96 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 118 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
97 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 110 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
98 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 98 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
99 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 109 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
100 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 100 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
101 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 112 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
102 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 111 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
103 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 15 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
104 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 12 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
105 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 11 | 2022-05-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
106 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 20 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
107 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 19 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
108 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 24 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
109 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 23 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
110 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 16 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
111 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 81 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
112 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 97 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
113 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 99 | 2022-05-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
114 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 28 | 2022-05-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
115 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 27 | 2022-05-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
116 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 155 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
117 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 154 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
118 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 136 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
119 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 133 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
120 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 152 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
121 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 162 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
122 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 160 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
123 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 137 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
124 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 134 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
125 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 135 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
126 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 82 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
127 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 84 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
128 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 104 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
129 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 101 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
130 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 83 | 2022-05-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
131 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 168 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
132 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 156 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
133 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 161 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
134 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 150 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
135 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 149 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
136 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 148 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
137 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 147 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
138 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 159 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
139 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 163 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
140 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 165 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
141 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 141 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
142 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 142 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
143 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 139 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
144 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 140 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
145 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 157 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
146 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 138 | 2022-05-20 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
147 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 33 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
148 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 34 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
149 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 36 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
150 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 35 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
151 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 151 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
152 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 164 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
153 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 153 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
154 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 166 | 2022-05-21 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
155 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 77 | 2022-05-28 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
156 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 74 | 2022-05-28 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
157 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 73 | 2022-05-28 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
158 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 66 | 2022-05-30 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
159 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 65 | 2022-05-30 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
160 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 70 | 2022-05-30 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
161 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 69 | 2022-05-30 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
162 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 78 | 2022-05-30 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | May
163 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 11 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
164 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 12 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
165 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 7 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
166 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 1 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
167 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 2 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
168 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 6 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
169 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 44 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
170 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 45 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
171 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 8 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
172 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 53 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
173 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 54 | 2022-06-01 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
174 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 33 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
175 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 34 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
176 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 52 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
177 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 39 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
178 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 38 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
179 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 26 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
180 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 4 | 2022-06-02 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
181 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 46 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
182 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 47 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
183 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 48 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
184 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 20 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
185 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 18 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
186 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 19 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
187 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 27 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
188 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 28 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
189 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 29 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
190 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 43 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
191 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 36 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
192 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 17 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
193 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 16 | 2022-06-03 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
194 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 55 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
195 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 13 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
196 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 42 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
197 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 41 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
198 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 30 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
199 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 31 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
200 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 49 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
201 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 50 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
202 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 9 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
203 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 10 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
204 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 40 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
205 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 14 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
206 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 21 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
207 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 22 | 2022-06-04 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
208 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 56 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
209 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 51 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
210 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 23 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
211 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 32 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
212 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 3 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
213 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 5 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
214 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 24 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
215 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 35 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
216 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 37 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
217 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 15 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
218 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 25 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
219 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 46 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
220 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 53 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
221 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 47 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
222 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 48 | 2022-06-06 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
223 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 49 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
224 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 42 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
225 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 55 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
226 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 56 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
227 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 41 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
228 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 51 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
229 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 54 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
230 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 38 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
231 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 45 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
232 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 43 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
233 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 44 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
234 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 37 | 2022-06-09 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
235 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 39 | 2022-06-09 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
236 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 40 | 2022-06-10 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
237 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 50 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
238 | Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 52 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
239 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 80 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
240 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 79 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
241 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 76 | 2022-06-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
242 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 75 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
243 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 72 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
244 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 71 | 2022-06-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
245 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 45 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
246 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 46 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
247 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 48 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
248 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 47 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
249 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 56 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
250 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 54 | 2022-06-11 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
251 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 64 | 2022-06-13 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
252 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 62 | 2022-06-13 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
253 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 55 | 2022-06-13 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
254 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 53 | 2022-06-13 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
255 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 58 | 2022-06-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
256 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 60 | 2022-06-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
257 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 63 | 2022-06-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
258 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 61 | 2022-06-14 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
259 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 143 | 2022-06-15 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
260 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 144 | 2022-06-15 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
261 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 145 | 2022-06-15 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
262 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 146 | 2022-06-15 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
263 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 68 | 2022-06-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
264 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 67 | 2022-06-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
265 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 51 | 2022-06-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
266 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 49 | 2022-06-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
267 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 57 | 2022-06-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
268 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 59 | 2022-06-17 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | June
269 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 41 | 2022-07-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
270 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 42 | 2022-07-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
271 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 43 | 2022-07-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
272 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 44 | 2022-07-16 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
273 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 50 | 2022-07-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
274 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 52 | 2022-07-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
275 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 40 | 2022-07-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
276 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 39 | 2022-07-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
277 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 38 | 2022-07-18 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
278 | Conveyor Gallery 18J45C1, C2 | Coke Circuit from COB-5 to BF-5 | 37 | 2022-07-19 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | July
279 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 98 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
280 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 97 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
281 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 96 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
282 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 94 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
283 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 91 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
284 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 89 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
285 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 87 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
286 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 93 | 2022-07-25 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
287 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 86 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
288 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 85 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
289 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 53 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
290 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 54 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
291 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 65 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
292 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 66 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
293 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 67 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
294 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 68 | 2022-07-26 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
295 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 60 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
296 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 57 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
297 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 56 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
298 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 55 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
299 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 78 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
300 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 80 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
301 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 82 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
302 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 84 | 2022-07-27 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
303 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 77 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
304 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 79 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
305 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 83 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
306 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 88 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
307 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 90 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
308 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 95 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
309 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 72 | 2022-07-28 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
310 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 92 | 2022-08-02 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
311 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 81 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
312 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 33 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
313 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 34 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
314 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 35 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
315 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 36 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
316 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 74 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
317 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 75 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
318 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 76 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
319 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 1 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
320 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 17 | 2022-08-03 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
321 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 18 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
322 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 2 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
323 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 42 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
324 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 43 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
325 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 45 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
326 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 46 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
327 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 15 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
328 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 23 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
329 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 16 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
330 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 3 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
331 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 19 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
332 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 69 | 2022-08-04 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | July
333 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 73 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
334 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 7 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
335 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 8 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
336 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 21 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
337 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 44 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
338 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 24 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
339 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 22 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
340 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 10 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
341 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 6 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
342 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 9 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
343 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 31 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
344 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 29 | 2022-08-05 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
345 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 20 | 2022-08-06 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
346 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 48 | 2022-08-06 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
347 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 37 | 2022-08-06 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
348 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 47 | 2022-08-06 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
349 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 26 | 2022-08-20 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
350 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 30 | 2022-08-20 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
350 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 32 | 2022-08-20 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
351 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 11 | 2022-08-20 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
352 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 13 | 2022-08-20 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
353 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 28 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
354 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 38 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
355 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 40 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
356 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 12 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
357 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 14 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
358 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 56 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
359 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 54 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
360 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 53 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
361 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 64 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
362 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 63 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
363 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 62 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
364 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 61 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
365 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 41 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
366 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 25 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
367 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 27 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
368 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 71 | 2022-08-22 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
369 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 4 | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
370 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 70 | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
371 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 55 | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
372 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 57' | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
373 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 58 | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
374 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 59 | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
375 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 60' | 2022-08-23 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
376 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 5 | 2022-08-24 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
377 | Junction House-18JH47 | Iron Ore & fluxes to BF-5 | 39 | 2022-08-24 | 0.6 | 14 | 13.025 | 0.50053 | 0.29123 | August
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 57 | 2022-09-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 58 | 2022-09-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 62 | 2022-09-07 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 61 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 66 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 60 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 68 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 67 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 64 | 2022-09-08 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 59 | 2022-09-09 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 63 | 2022-09-09 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Conveyor Gallery 18J46C1,C2 | Coke Circuit from COB-5 to BF-5 | 65 | 2022-09-09 | 0.6 | 15 | 13.025 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 3 | 2022-09-09 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 4 | 2022-09-09 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 6 | 2022-09-10 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 8 | 2022-09-10 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 7 | 2022-09-10 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 15 | 2022-09-10 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 16 | 2022-09-10 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 19 | 2022-09-12 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 20 | 2022-09-12 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 2 | 2022-09-12 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 17 | 2022-09-12 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 18 | 2022-09-12 | 0.6 | 15 | 14.165 | 0.50053 | 0.29123 | September
| Junction House-18JH46 | Coke Circuit from COB-5 to BF-5 | 51 | 2022-09-12 | 0.6 | 15 | 13.665 | 0.50053 | 0.29123 | September

## Concrete Tracker
Sr No | Location | Area | Date of Casting | Tentative Concrete Quantity (cum) | Month
1 | Junction House-18JH45 | Coke Circuit from COB-5 to BF-5 | 2022-09-13 | 6.5 | May
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377

## Sheet2
Pilling
Civil | Cum | Yard equipments & conveyors
Structure Fabrication | MT | Iron Ore & fluxes to BF-5 | Pilling | No's
Structure Erection | No's | Coke Circuit from COB-5 to BF-5 | Civil | Cum
Mechanical |  | BF fines to existing conveyor 18J5C1 | PCC | Cum
Electrical |  | Conveyor route from JH 70 to PCI bunker | Structure Fabrication | MT
|  | Bunker Building | Structure Erection | MT
|  | Sinter and pellet to BF-5 | Mechanical | MT
|  | Limestone and dolomite to LCP | Electrical | %
|  |  | Excavation | Cum
2022-03-01 |  | Sunny
2022-04-01 |  | Rainy
2022-05-01 |  | Cloudy
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01

## Plan for a month
Sr No. | Months | Nature of Work | Area | Quantity | Drawings Actual | From central plaza to HSM3 Gas Mixing Station | BF5 Gas Holder
1 | 2022-03-01 | Civil | Yard equipments & conveyors | 0
2 | 2022-04-01 | Civil | Yard equipments & conveyors | 0
3 | 2022-05-01 | Civil | Yard equipments & conveyors | 0
4 | 2022-06-01 | Civil | Yard equipments & conveyors | 0
5 | 2022-07-01 | Civil | Yard equipments & conveyors | 0
6 | 2022-08-01 | Civil | Yard equipments & conveyors
7 | 2022-09-01 | Civil | Yard equipments & conveyors
8 | 2022-10-01 | Civil | Yard equipments & conveyors
9 | 2022-11-01 | Civil | Yard equipments & conveyors
10 | 2022-12-01 | Civil | Yard equipments & conveyors
11 | 2023-01-01 | Civil | Yard equipments & conveyors
12 | 2023-02-01 | Civil | Yard equipments & conveyors
13 | 2023-03-01 | Civil | Yard equipments & conveyors
14 | 2023-04-01 | Civil | Yard equipments & conveyors
15 | 2023-05-01 | Civil | Yard equipments & conveyors
16 | 2023-06-01 | Civil | Yard equipments & conveyors
17 | 2023-07-01 | Civil | Yard equipments & conveyors
18 | 2023-08-01 | Civil | Yard equipments & conveyors
19 | 2023-09-01 | Civil | Yard equipments & conveyors
20 | 2023-10-01 | Civil | Yard equipments & conveyors
21 | 2023-11-01 | Civil | Yard equipments & conveyors
22 | 2023-12-01 | Civil | Yard equipments & conveyors
23 | 2024-01-01 | Civil | Yard equipments & conveyors
24 | 2022-03-01 | Civil | Iron Ore & fluxes to BF-5 | 0
25 | 2022-04-01 | Civil | Iron Ore & fluxes to BF-5 | 0
26 | 2022-05-01 | Civil | Iron Ore & fluxes to BF-5 | 0
27 | 2022-06-01 | Civil | Iron Ore & fluxes to BF-5 | 0
28 | 2022-07-01 | Civil | Iron Ore & fluxes to BF-5 | 0
29 | 2022-08-01 | Civil | Iron Ore & fluxes to BF-5 | 325
30 | 2022-09-01 | Civil | Iron Ore & fluxes to BF-5 | 325
31 | 2022-10-01 | Civil | Iron Ore & fluxes to BF-5
32 | 2022-11-01 | Civil | Iron Ore & fluxes to BF-5
33 | 2022-12-01 | Civil | Iron Ore & fluxes to BF-5
34 | 2023-01-01 | Civil | Iron Ore & fluxes to BF-5
35 | 2023-02-01 | Civil | Iron Ore & fluxes to BF-5
36 | 2023-03-01 | Civil | Iron Ore & fluxes to BF-5
37 | 2023-04-01 | Civil | Iron Ore & fluxes to BF-5
38 | 2023-05-01 | Civil | Iron Ore & fluxes to BF-5
39 | 2023-06-01 | Civil | Iron Ore & fluxes to BF-5
40 | 2023-07-01 | Civil | Iron Ore & fluxes to BF-5
41 | 2023-08-01 | Civil | Iron Ore & fluxes to BF-5
42 | 2023-09-01 | Civil | Iron Ore & fluxes to BF-5
43 | 2023-10-01 | Civil | Iron Ore & fluxes to BF-5
44 | 2023-11-01 | Civil | Iron Ore & fluxes to BF-5
45 | 2023-12-01 | Civil | Iron Ore & fluxes to BF-5
46 | 2024-01-01 | Civil | Iron Ore & fluxes to BF-5
47 | 2022-03-01 | Civil | Coke Circuit from COB-5 to BF-5 | 0
48 | 2022-04-01 | Civil | Coke Circuit from COB-5 to BF-5 | 0
49 | 2022-05-01 | Civil | Coke Circuit from COB-5 to BF-5 | 0
50 | 2022-06-01 | Civil | Coke Circuit from COB-5 to BF-5 | 0
51 | 2022-07-01 | Civil | Coke Circuit from COB-5 to BF-5 | 0
52 | 2022-08-01 | Civil | Coke Circuit from COB-5 to BF-5 | 450
53 | 2022-09-01 | Civil | Coke Circuit from COB-5 to BF-5 | 450
54 | 2022-10-01 | Civil | Coke Circuit from COB-5 to BF-5
55 | 2022-11-01 | Civil | Coke Circuit from COB-5 to BF-5
56 | 2022-12-01 | Civil | Coke Circuit from COB-5 to BF-5
57 | 2023-01-01 | Civil | Coke Circuit from COB-5 to BF-5
58 | 2023-02-01 | Civil | Coke Circuit from COB-5 to BF-5
59 | 2023-03-01 | Civil | Coke Circuit from COB-5 to BF-5
60 | 2023-04-01 | Civil | Coke Circuit from COB-5 to BF-5
61 | 2023-05-01 | Civil | Coke Circuit from COB-5 to BF-5
62 | 2023-06-01 | Civil | Coke Circuit from COB-5 to BF-5
63 | 2023-07-01 | Civil | Coke Circuit from COB-5 to BF-5
64 | 2023-08-01 | Civil | Coke Circuit from COB-5 to BF-5
65 | 2023-09-01 | Civil | Coke Circuit from COB-5 to BF-5
66 | 2023-10-01 | Civil | Coke Circuit from COB-5 to BF-5
67 | 2023-11-01 | Civil | Coke Circuit from COB-5 to BF-5
68 | 2023-12-01 | Civil | Coke Circuit from COB-5 to BF-5
69 | 2024-01-01 | Civil | Coke Circuit from COB-5 to BF-5
70 | 2022-03-01 | Civil | BF fines to existing conveyor 18J5C1 | 0
71 | 2022-04-01 | Civil | BF fines to existing conveyor 18J5C1 | 0
72 | 2022-05-01 | Civil | BF fines to existing conveyor 18J5C1 | 0
73 | 2022-06-01 | Civil | BF fines to existing conveyor 18J5C1 | 0
74 | 2022-07-01 | Civil | BF fines to existing conveyor 18J5C1 | 0
75 | 2022-08-01 | Civil | BF fines to existing conveyor 18J5C1
76 | 2022-09-01 | Civil | BF fines to existing conveyor 18J5C1
77 | 2022-10-01 | Civil | BF fines to existing conveyor 18J5C1
78 | 2022-11-01 | Civil | BF fines to existing conveyor 18J5C1
79 | 2022-12-01 | Civil | BF fines to existing conveyor 18J5C1
80 | 2023-01-01 | Civil | BF fines to existing conveyor 18J5C1
81 | 2023-02-01 | Civil | BF fines to existing conveyor 18J5C1
82 | 2023-03-01 | Civil | BF fines to existing conveyor 18J5C1
83 | 2023-04-01 | Civil | BF fines to existing conveyor 18J5C1
84 | 2023-05-01 | Civil | BF fines to existing conveyor 18J5C1
85 | 2023-06-01 | Civil | BF fines to existing conveyor 18J5C1
86 | 2023-07-01 | Civil | BF fines to existing conveyor 18J5C1
87 | 2023-08-01 | Civil | BF fines to existing conveyor 18J5C1
88 | 2023-09-01 | Civil | BF fines to existing conveyor 18J5C1
89 | 2023-10-01 | Civil | BF fines to existing conveyor 18J5C1
90 | 2023-11-01 | Civil | BF fines to existing conveyor 18J5C1
91 | 2023-12-01 | Civil | BF fines to existing conveyor 18J5C1
92 | 2024-01-01 | Civil | BF fines to existing conveyor 18J5C1
93 | 2022-03-01 | Civil | Conveyor route from JH 70 to PCI bunker | 0
94 | 2022-04-01 | Civil | Conveyor route from JH 70 to PCI bunker | 0
95 | 2022-05-01 | Civil | Conveyor route from JH 70 to PCI bunker | 0
96 | 2022-06-01 | Civil | Conveyor route from JH 70 to PCI bunker | 0
97 | 2022-07-01 | Civil | Conveyor route from JH 70 to PCI bunker | 0
98 | 2022-08-01 | Civil | Conveyor route from JH 70 to PCI bunker
99 | 2022-09-01 | Civil | Conveyor route from JH 70 to PCI bunker
100 | 2022-10-01 | Civil | Conveyor route from JH 70 to PCI bunker
101 | 2022-11-01 | Civil | Conveyor route from JH 70 to PCI bunker
102 | 2022-12-01 | Civil | Conveyor route from JH 70 to PCI bunker
103 | 2023-01-01 | Civil | Conveyor route from JH 70 to PCI bunker
104 | 2023-02-01 | Civil | Conveyor route from JH 70 to PCI bunker
105 | 2023-03-01 | Civil | Conveyor route from JH 70 to PCI bunker
106 | 2023-04-01 | Civil | Conveyor route from JH 70 to PCI bunker
107 | 2023-05-01 | Civil | Conveyor route from JH 70 to PCI bunker
108 | 2023-06-01 | Civil | Conveyor route from JH 70 to PCI bunker
109 | 2023-07-01 | Civil | Conveyor route from JH 70 to PCI bunker
110 | 2023-08-01 | Civil | Conveyor route from JH 70 to PCI bunker
111 | 2023-09-01 | Civil | Conveyor route from JH 70 to PCI bunker
112 | 2023-10-01 | Civil | Conveyor route from JH 70 to PCI bunker
113 | 2023-11-01 | Civil | Conveyor route from JH 70 to PCI bunker
114 | 2023-12-01 | Civil | Conveyor route from JH 70 to PCI bunker
115 | 2024-01-01 | Civil | Conveyor route from JH 70 to PCI bunker
116 | 2022-03-01 | Civil | Bunker Building | 0
117 | 2022-04-01 | Civil | Bunker Building | 0
118 | 2022-05-01 | Civil | Bunker Building | 0
119 | 2022-06-01 | Civil | Bunker Building | 0
120 | 2022-07-01 | Civil | Bunker Building | 0
121 | 2022-08-01 | Civil | Bunker Building | 600
122 | 2022-09-01 | Civil | Bunker Building | 600
123 | 2022-10-01 | Civil | Bunker Building
124 | 2022-11-01 | Civil | Bunker Building
125 | 2022-12-01 | Civil | Bunker Building
126 | 2023-01-01 | Civil | Bunker Building
127 | 2023-02-01 | Civil | Bunker Building
128 | 2023-03-01 | Civil | Bunker Building
129 | 2023-04-01 | Civil | Bunker Building
130 | 2023-05-01 | Civil | Bunker Building
131 | 2023-06-01 | Civil | Bunker Building
132 | 2023-07-01 | Civil | Bunker Building
133 | 2023-08-01 | Civil | Bunker Building
134 | 2023-09-01 | Civil | Bunker Building
135 | 2023-10-01 | Civil | Bunker Building
136 | 2023-11-01 | Civil | Bunker Building
137 | 2023-12-01 | Civil | Bunker Building
138 | 2024-01-01 | Civil | Bunker Building
139 | 2022-03-01 | Civil | Sinter and pellet to BF-5 | 0
140 | 2022-04-01 | Civil | Sinter and pellet to BF-5 | 0
141 | 2022-05-01 | Civil | Sinter and pellet to BF-5 | 0
142 | 2022-06-01 | Civil | Sinter and pellet to BF-5 | 0
143 | 2022-07-01 | Civil | Sinter and pellet to BF-5 | 0
144 | 2022-08-01 | Civil | Sinter and pellet to BF-5
145 | 2022-09-01 | Civil | Sinter and pellet to BF-5
146 | 2022-10-01 | Civil | Sinter and pellet to BF-5
147 | 2022-11-01 | Civil | Sinter and pellet to BF-5
148 | 2022-12-01 | Civil | Sinter and pellet to BF-5
149 | 2023-01-01 | Civil | Sinter and pellet to BF-5
150 | 2023-02-01 | Civil | Sinter and pellet to BF-5
151 | 2023-03-01 | Civil | Sinter and pellet to BF-5
152 | 2023-04-01 | Civil | Sinter and pellet to BF-5
153 | 2023-05-01 | Civil | Sinter and pellet to BF-5
154 | 2023-06-01 | Civil | Sinter and pellet to BF-5
155 | 2023-07-01 | Civil | Sinter and pellet to BF-5
156 | 2023-08-01 | Civil | Sinter and pellet to BF-5
157 | 2023-09-01 | Civil | Sinter and pellet to BF-5
158 | 2023-10-01 | Civil | Sinter and pellet to BF-5
159 | 2023-11-01 | Civil | Sinter and pellet to BF-5
160 | 2023-12-01 | Civil | Sinter and pellet to BF-5
161 | 2024-01-01 | Civil | Sinter and pellet to BF-5
162 | 2022-03-01 | Civil | Limestone and dolomite to LCP | 0
163 | 2022-04-01 | Civil | Limestone and dolomite to LCP | 0
164 | 2022-05-01 | Civil | Limestone and dolomite to LCP | 0
165 | 2022-06-01 | Civil | Limestone and dolomite to LCP | 0
166 | 2022-07-01 | Civil | Limestone and dolomite to LCP | 0
167 | 2022-08-01 | Civil | Limestone and dolomite to LCP
168 | 2022-09-01 | Civil | Limestone and dolomite to LCP
169 | 2022-10-01 | Civil | Limestone and dolomite to LCP
170 | 2022-11-01 | Civil | Limestone and dolomite to LCP
171 | 2022-12-01 | Civil | Limestone and dolomite to LCP
172 | 2023-01-01 | Civil | Limestone and dolomite to LCP
173 | 2023-02-01 | Civil | Limestone and dolomite to LCP
174 | 2023-03-01 | Civil | Limestone and dolomite to LCP
175 | 2023-04-01 | Civil | Limestone and dolomite to LCP
176 | 2023-05-01 | Civil | Limestone and dolomite to LCP
177 | 2023-06-01 | Civil | Limestone and dolomite to LCP
178 | 2023-07-01 | Civil | Limestone and dolomite to LCP
179 | 2023-08-01 | Civil | Limestone and dolomite to LCP
180 | 2023-09-01 | Civil | Limestone and dolomite to LCP
181 | 2023-10-01 | Civil | Limestone and dolomite to LCP
182 | 2023-11-01 | Civil | Limestone and dolomite to LCP
183 | 2023-12-01 | Civil | Limestone and dolomite to LCP
184 | 2024-01-01 | Civil | Limestone and dolomite to LCP
185 | 2022-03-01 | Structure Fabrication | Yard equipments & conveyors | 0
186 | 2022-04-01 | Structure Fabrication | Yard equipments & conveyors | 0
187 | 2022-05-01 | Structure Fabrication | Yard equipments & conveyors | 0
188 | 2022-06-01 | Structure Fabrication | Yard equipments & conveyors | 0
189 | 2022-07-01 | Structure Fabrication | Yard equipments & conveyors | 0
190 | 2022-08-01 | Structure Fabrication | Yard equipments & conveyors
191 | 2022-09-01 | Structure Fabrication | Yard equipments & conveyors
192 | 2022-10-01 | Structure Fabrication | Yard equipments & conveyors
193 | 2022-11-01 | Structure Fabrication | Yard equipments & conveyors
194 | 2022-12-01 | Structure Fabrication | Yard equipments & conveyors
195 | 2023-01-01 | Structure Fabrication | Yard equipments & conveyors
196 | 2023-02-01 | Structure Fabrication | Yard equipments & conveyors
197 | 2023-03-01 | Structure Fabrication | Yard equipments & conveyors
198 | 2023-04-01 | Structure Fabrication | Yard equipments & conveyors
199 | 2023-05-01 | Structure Fabrication | Yard equipments & conveyors
200 | 2023-06-01 | Structure Fabrication | Yard equipments & conveyors
201 | 2023-07-01 | Structure Fabrication | Yard equipments & conveyors
202 | 2023-08-01 | Structure Fabrication | Yard equipments & conveyors
203 | 2023-09-01 | Structure Fabrication | Yard equipments & conveyors
204 | 2023-10-01 | Structure Fabrication | Yard equipments & conveyors
205 | 2023-11-01 | Structure Fabrication | Yard equipments & conveyors
206 | 2023-12-01 | Structure Fabrication | Yard equipments & conveyors
207 | 2024-01-01 | Structure Fabrication | Yard equipments & conveyors
208 | 2022-03-01 | Structure Fabrication | Iron Ore & fluxes to BF-5 | 0
209 | 2022-04-01 | Structure Fabrication | Iron Ore & fluxes to BF-5 | 0
210 | 2022-05-01 | Structure Fabrication | Iron Ore & fluxes to BF-5 | 0
211 | 2022-06-01 | Structure Fabrication | Iron Ore & fluxes to BF-5 | 0
212 | 2022-07-01 | Structure Fabrication | Iron Ore & fluxes to BF-5 | 0
213 | 2022-08-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
214 | 2022-09-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
215 | 2022-10-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
216 | 2022-11-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
217 | 2022-12-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
218 | 2023-01-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
219 | 2023-02-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
220 | 2023-03-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
221 | 2023-04-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
222 | 2023-05-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
223 | 2023-06-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
224 | 2023-07-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
225 | 2023-08-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
226 | 2023-09-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
227 | 2023-10-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
228 | 2023-11-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
229 | 2023-12-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
230 | 2024-01-01 | Structure Fabrication | Iron Ore & fluxes to BF-5
231 | 2022-03-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 0
232 | 2022-04-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 0
233 | 2022-05-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 0
234 | 2022-06-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 0
235 | 2022-07-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 0
236 | 2022-08-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 205
237 | 2022-09-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5 | 402
238 | 2022-10-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
239 | 2022-11-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
240 | 2022-12-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
241 | 2023-01-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
242 | 2023-02-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
243 | 2023-03-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
244 | 2023-04-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
245 | 2023-05-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
246 | 2023-06-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
247 | 2023-07-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
248 | 2023-08-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
249 | 2023-09-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
250 | 2023-10-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
251 | 2023-11-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
252 | 2023-12-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
253 | 2024-01-01 | Structure Fabrication | Coke Circuit from COB-5 to BF-5
254 | 2022-03-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1 | 0
255 | 2022-04-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1 | 0
256 | 2022-05-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1 | 0
257 | 2022-06-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1 | 0
258 | 2022-07-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1 | 0
259 | 2022-08-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
260 | 2022-09-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
261 | 2022-10-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
262 | 2022-11-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
263 | 2022-12-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
264 | 2023-01-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
265 | 2023-02-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
266 | 2023-03-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
267 | 2023-04-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
268 | 2023-05-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
269 | 2023-06-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
270 | 2023-07-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
271 | 2023-08-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
272 | 2023-09-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
273 | 2023-10-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
274 | 2023-11-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
275 | 2023-12-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
276 | 2024-01-01 | Structure Fabrication | BF fines to existing conveyor 18J5C1
277 | 2022-03-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker | 0
278 | 2022-04-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker | 0
279 | 2022-05-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker | 0
280 | 2022-06-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker | 0
281 | 2022-07-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker | 0
282 | 2022-08-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
283 | 2022-09-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
284 | 2022-10-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
285 | 2022-11-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
286 | 2022-12-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
287 | 2023-01-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
288 | 2023-02-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
289 | 2023-03-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
290 | 2023-04-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
291 | 2023-05-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
292 | 2023-06-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
293 | 2023-07-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
294 | 2023-08-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
295 | 2023-09-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
296 | 2023-10-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
297 | 2023-11-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
298 | 2023-12-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
299 | 2024-01-01 | Structure Fabrication | Conveyor route from JH 70 to PCI bunker
300 | 2022-03-01 | Structure Fabrication | Bunker Building | 0
301 | 2022-04-01 | Structure Fabrication | Bunker Building | 0
302 | 2022-05-01 | Structure Fabrication | Bunker Building | 0
303 | 2022-06-01 | Structure Fabrication | Bunker Building | 0
304 | 2022-07-01 | Structure Fabrication | Bunker Building | 0
305 | 2022-08-01 | Structure Fabrication | Bunker Building
306 | 2022-09-01 | Structure Fabrication | Bunker Building
307 | 2022-10-01 | Structure Fabrication | Bunker Building
308 | 2022-11-01 | Structure Fabrication | Bunker Building
309 | 2022-12-01 | Structure Fabrication | Bunker Building
310 | 2023-01-01 | Structure Fabrication | Bunker Building
311 | 2023-02-01 | Structure Fabrication | Bunker Building
312 | 2023-03-01 | Structure Fabrication | Bunker Building
313 | 2023-04-01 | Structure Fabrication | Bunker Building
314 | 2023-05-01 | Structure Fabrication | Bunker Building
315 | 2023-06-01 | Structure Fabrication | Bunker Building
316 | 2023-07-01 | Structure Fabrication | Bunker Building
317 | 2023-08-01 | Structure Fabrication | Bunker Building
318 | 2023-09-01 | Structure Fabrication | Bunker Building
319 | 2023-10-01 | Structure Fabrication | Bunker Building
320 | 2023-11-01 | Structure Fabrication | Bunker Building
321 | 2023-12-01 | Structure Fabrication | Bunker Building
322 | 2024-01-01 | Structure Fabrication | Bunker Building
323 | 2022-03-01 | Structure Fabrication | Sinter and pellet to BF-5 | 0
324 | 2022-04-01 | Structure Fabrication | Sinter and pellet to BF-5 | 0
325 | 2022-05-01 | Structure Fabrication | Sinter and pellet to BF-5 | 0
326 | 2022-06-01 | Structure Fabrication | Sinter and pellet to BF-5 | 0
327 | 2022-07-01 | Structure Fabrication | Sinter and pellet to BF-5 | 0
328 | 2022-08-01 | Structure Fabrication | Sinter and pellet to BF-5
329 | 2022-09-01 | Structure Fabrication | Sinter and pellet to BF-5
330 | 2022-10-01 | Structure Fabrication | Sinter and pellet to BF-5
331 | 2022-11-01 | Structure Fabrication | Sinter and pellet to BF-5
332 | 2022-12-01 | Structure Fabrication | Sinter and pellet to BF-5
333 | 2023-01-01 | Structure Fabrication | Sinter and pellet to BF-5
334 | 2023-02-01 | Structure Fabrication | Sinter and pellet to BF-5
335 | 2023-03-01 | Structure Fabrication | Sinter and pellet to BF-5
336 | 2023-04-01 | Structure Fabrication | Sinter and pellet to BF-5
337 | 2023-05-01 | Structure Fabrication | Sinter and pellet to BF-5
338 | 2023-06-01 | Structure Fabrication | Sinter and pellet to BF-5
339 | 2023-07-01 | Structure Fabrication | Sinter and pellet to BF-5
340 | 2023-08-01 | Structure Fabrication | Sinter and pellet to BF-5
341 | 2023-09-01 | Structure Fabrication | Sinter and pellet to BF-5
342 | 2023-10-01 | Structure Fabrication | Sinter and pellet to BF-5
343 | 2023-11-01 | Structure Fabrication | Sinter and pellet to BF-5
344 | 2023-12-01 | Structure Fabrication | Sinter and pellet to BF-5
345 | 2024-01-01 | Structure Fabrication | Sinter and pellet to BF-5
346 | 2022-03-01 | Structure Fabrication | Limestone and dolomite to LCP | 0
347 | 2022-04-01 | Structure Fabrication | Limestone and dolomite to LCP | 0
348 | 2022-05-01 | Structure Fabrication | Limestone and dolomite to LCP | 0
349 | 2022-06-01 | Structure Fabrication | Limestone and dolomite to LCP | 0
350 | 2022-07-01 | Structure Fabrication | Limestone and dolomite to LCP | 0
351 | 2022-08-01 | Structure Fabrication | Limestone and dolomite to LCP
352 | 2022-09-01 | Structure Fabrication | Limestone and dolomite to LCP
353 | 2022-10-01 | Structure Fabrication | Limestone and dolomite to LCP
354 | 2022-11-01 | Structure Fabrication | Limestone and dolomite to LCP
355 | 2022-12-01 | Structure Fabrication | Limestone and dolomite to LCP
356 | 2023-01-01 | Structure Fabrication | Limestone and dolomite to LCP
357 | 2023-02-01 | Structure Fabrication | Limestone and dolomite to LCP
358 | 2023-03-01 | Structure Fabrication | Limestone and dolomite to LCP
359 | 2023-04-01 | Structure Fabrication | Limestone and dolomite to LCP
360 | 2023-05-01 | Structure Fabrication | Limestone and dolomite to LCP
361 | 2023-06-01 | Structure Fabrication | Limestone and dolomite to LCP
362 | 2023-07-01 | Structure Fabrication | Limestone and dolomite to LCP
363 | 2023-08-01 | Structure Fabrication | Limestone and dolomite to LCP
364 | 2023-09-01 | Structure Fabrication | Limestone and dolomite to LCP
365 | 2023-10-01 | Structure Fabrication | Limestone and dolomite to LCP
366 | 2023-11-01 | Structure Fabrication | Limestone and dolomite to LCP
367 | 2023-12-01 | Structure Fabrication | Limestone and dolomite to LCP
368 | 2024-01-01 | Structure Fabrication | Limestone and dolomite to LCP
369 | 2022-03-01 | Structure Erection | Yard equipments & conveyors | 0
370 | 2022-04-01 | Structure Erection | Yard equipments & conveyors | 0
371 | 2022-05-01 | Structure Erection | Yard equipments & conveyors | 0
372 | 2022-06-01 | Structure Erection | Yard equipments & conveyors | 0
373 | 2022-07-01 | Structure Erection | Yard equipments & conveyors | 0
374 | 2022-08-01 | Structure Erection | Yard equipments & conveyors
375 | 2022-09-01 | Structure Erection | Yard equipments & conveyors
376 | 2022-10-01 | Structure Erection | Yard equipments & conveyors
377 | 2022-11-01 | Structure Erection | Yard equipments & conveyors
378 | 2022-12-01 | Structure Erection | Yard equipments & conveyors
379 | 2023-01-01 | Structure Erection | Yard equipments & conveyors
380 | 2023-02-01 | Structure Erection | Yard equipments & conveyors
381 | 2023-03-01 | Structure Erection | Yard equipments & conveyors
382 | 2023-04-01 | Structure Erection | Yard equipments & conveyors
383 | 2023-05-01 | Structure Erection | Yard equipments & conveyors
384 | 2023-06-01 | Structure Erection | Yard equipments & conveyors
385 | 2023-07-01 | Structure Erection | Yard equipments & conveyors
386 | 2023-08-01 | Structure Erection | Yard equipments & conveyors
387 | 2023-09-01 | Structure Erection | Yard equipments & conveyors
388 | 2023-10-01 | Structure Erection | Yard equipments & conveyors
389 | 2023-11-01 | Structure Erection | Yard equipments & conveyors
390 | 2023-12-01 | Structure Erection | Yard equipments & conveyors
391 | 2024-01-01 | Structure Erection | Yard equipments & conveyors
392 | 2022-03-01 | Structure Erection | Iron Ore & fluxes to BF-5 | 0
393 | 2022-04-01 | Structure Erection | Iron Ore & fluxes to BF-5 | 0
394 | 2022-05-01 | Structure Erection | Iron Ore & fluxes to BF-5 | 0
395 | 2022-06-01 | Structure Erection | Iron Ore & fluxes to BF-5 | 0
396 | 2022-07-01 | Structure Erection | Iron Ore & fluxes to BF-5 | 0
397 | 2022-08-01 | Structure Erection | Iron Ore & fluxes to BF-5
398 | 2022-09-01 | Structure Erection | Iron Ore & fluxes to BF-5
399 | 2022-10-01 | Structure Erection | Iron Ore & fluxes to BF-5
400 | 2022-11-01 | Structure Erection | Iron Ore & fluxes to BF-5
401 | 2022-12-01 | Structure Erection | Iron Ore & fluxes to BF-5
402 | 2023-01-01 | Structure Erection | Iron Ore & fluxes to BF-5
403 | 2023-02-01 | Structure Erection | Iron Ore & fluxes to BF-5
404 | 2023-03-01 | Structure Erection | Iron Ore & fluxes to BF-5
405 | 2023-04-01 | Structure Erection | Iron Ore & fluxes to BF-5
406 | 2023-05-01 | Structure Erection | Iron Ore & fluxes to BF-5
407 | 2023-06-01 | Structure Erection | Iron Ore & fluxes to BF-5
408 | 2023-07-01 | Structure Erection | Iron Ore & fluxes to BF-5
409 | 2023-08-01 | Structure Erection | Iron Ore & fluxes to BF-5
410 | 2023-09-01 | Structure Erection | Iron Ore & fluxes to BF-5
411 | 2023-10-01 | Structure Erection | Iron Ore & fluxes to BF-5
412 | 2023-11-01 | Structure Erection | Iron Ore & fluxes to BF-5
413 | 2023-12-01 | Structure Erection | Iron Ore & fluxes to BF-5
414 | 2024-01-01 | Structure Erection | Iron Ore & fluxes to BF-5
415 | 2022-03-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 0
416 | 2022-04-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 0
417 | 2022-05-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 0
418 | 2022-06-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 0
419 | 2022-07-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 0
420 | 2022-08-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
421 | 2022-09-01 | Structure Erection | Coke Circuit from COB-5 to BF-5 | 100
422 | 2022-10-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
423 | 2022-11-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
424 | 2022-12-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
425 | 2023-01-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
426 | 2023-02-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
427 | 2023-03-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
428 | 2023-04-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
429 | 2023-05-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
430 | 2023-06-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
431 | 2023-07-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
432 | 2023-08-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
433 | 2023-09-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
434 | 2023-10-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
435 | 2023-11-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
436 | 2023-12-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
437 | 2024-01-01 | Structure Erection | Coke Circuit from COB-5 to BF-5
438 | 2022-03-01 | Structure Erection | BF fines to existing conveyor 18J5C1 | 0
439 | 2022-04-01 | Structure Erection | BF fines to existing conveyor 18J5C1 | 0
440 | 2022-05-01 | Structure Erection | BF fines to existing conveyor 18J5C1 | 0
441 | 2022-06-01 | Structure Erection | BF fines to existing conveyor 18J5C1 | 0
442 | 2022-07-01 | Structure Erection | BF fines to existing conveyor 18J5C1 | 0
443 | 2022-08-01 | Structure Erection | BF fines to existing conveyor 18J5C1
444 | 2022-09-01 | Structure Erection | BF fines to existing conveyor 18J5C1
445 | 2022-10-01 | Structure Erection | BF fines to existing conveyor 18J5C1
446 | 2022-11-01 | Structure Erection | BF fines to existing conveyor 18J5C1
447 | 2022-12-01 | Structure Erection | BF fines to existing conveyor 18J5C1
448 | 2023-01-01 | Structure Erection | BF fines to existing conveyor 18J5C1
449 | 2023-02-01 | Structure Erection | BF fines to existing conveyor 18J5C1
450 | 2023-03-01 | Structure Erection | BF fines to existing conveyor 18J5C1
451 | 2023-04-01 | Structure Erection | BF fines to existing conveyor 18J5C1
452 | 2023-05-01 | Structure Erection | BF fines to existing conveyor 18J5C1
453 | 2023-06-01 | Structure Erection | BF fines to existing conveyor 18J5C1
454 | 2023-07-01 | Structure Erection | BF fines to existing conveyor 18J5C1
455 | 2023-08-01 | Structure Erection | BF fines to existing conveyor 18J5C1
456 | 2023-09-01 | Structure Erection | BF fines to existing conveyor 18J5C1
457 | 2023-10-01 | Structure Erection | BF fines to existing conveyor 18J5C1
458 | 2023-11-01 | Structure Erection | BF fines to existing conveyor 18J5C1
459 | 2023-12-01 | Structure Erection | BF fines to existing conveyor 18J5C1
460 | 2024-01-01 | Structure Erection | BF fines to existing conveyor 18J5C1
461 | 2022-03-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker | 0
462 | 2022-04-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker | 0
463 | 2022-05-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker | 0
464 | 2022-06-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker | 0
465 | 2022-07-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker | 0
466 | 2022-08-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
467 | 2022-09-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
468 | 2022-10-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
469 | 2022-11-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
470 | 2022-12-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
471 | 2023-01-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
472 | 2023-02-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
473 | 2023-03-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
474 | 2023-04-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
475 | 2023-05-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
476 | 2023-06-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
477 | 2023-07-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
478 | 2023-08-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
479 | 2023-09-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
480 | 2023-10-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
481 | 2023-11-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
482 | 2023-12-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
483 | 2024-01-01 | Structure Erection | Conveyor route from JH 70 to PCI bunker
484 | 2022-03-01 | Structure Erection | Bunker Building | 0
485 | 2022-04-01 | Structure Erection | Bunker Building | 0
486 | 2022-05-01 | Structure Erection | Bunker Building | 0
487 | 2022-06-01 | Structure Erection | Bunker Building | 0
488 | 2022-07-01 | Structure Erection | Bunker Building | 0
489 | 2022-08-01 | Structure Erection | Bunker Building
490 | 2022-09-01 | Structure Erection | Bunker Building
491 | 2022-10-01 | Structure Erection | Bunker Building
492 | 2022-11-01 | Structure Erection | Bunker Building
493 | 2022-12-01 | Structure Erection | Bunker Building
494 | 2023-01-01 | Structure Erection | Bunker Building
495 | 2023-02-01 | Structure Erection | Bunker Building
496 | 2023-03-01 | Structure Erection | Bunker Building
497 | 2023-04-01 | Structure Erection | Bunker Building
498 | 2023-05-01 | Structure Erection | Bunker Building
499 | 2023-06-01 | Structure Erection | Bunker Building
500 | 2023-07-01 | Structure Erection | Bunker Building
501 | 2023-08-01 | Structure Erection | Bunker Building
502 | 2023-09-01 | Structure Erection | Bunker Building
503 | 2023-10-01 | Structure Erection | Bunker Building
504 | 2023-11-01 | Structure Erection | Bunker Building
505 | 2023-12-01 | Structure Erection | Bunker Building
506 | 2024-01-01 | Structure Erection | Bunker Building
507 | 2022-03-01 | Structure Erection | Sinter and pellet to BF-5 | 0
508 | 2022-04-01 | Structure Erection | Sinter and pellet to BF-5 | 0
509 | 2022-05-01 | Structure Erection | Sinter and pellet to BF-5 | 0
510 | 2022-06-01 | Structure Erection | Sinter and pellet to BF-5 | 0
511 | 2022-07-01 | Structure Erection | Sinter and pellet to BF-5 | 0
512 | 2022-08-01 | Structure Erection | Sinter and pellet to BF-5
513 | 2022-09-01 | Structure Erection | Sinter and pellet to BF-5
514 | 2022-10-01 | Structure Erection | Sinter and pellet to BF-5
515 | 2022-11-01 | Structure Erection | Sinter and pellet to BF-5
516 | 2022-12-01 | Structure Erection | Sinter and pellet to BF-5
517 | 2023-01-01 | Structure Erection | Sinter and pellet to BF-5
518 | 2023-02-01 | Structure Erection | Sinter and pellet to BF-5
519 | 2023-03-01 | Structure Erection | Sinter and pellet to BF-5
520 | 2023-04-01 | Structure Erection | Sinter and pellet to BF-5
521 | 2023-05-01 | Structure Erection | Sinter and pellet to BF-5
522 | 2023-06-01 | Structure Erection | Sinter and pellet to BF-5
523 | 2023-07-01 | Structure Erection | Sinter and pellet to BF-5
524 | 2023-08-01 | Structure Erection | Sinter and pellet to BF-5
525 | 2023-09-01 | Structure Erection | Sinter and pellet to BF-5
526 | 2023-10-01 | Structure Erection | Sinter and pellet to BF-5
527 | 2023-11-01 | Structure Erection | Sinter and pellet to BF-5
528 | 2023-12-01 | Structure Erection | Sinter and pellet to BF-5
529 | 2024-01-01 | Structure Erection | Sinter and pellet to BF-5
530 | 2022-03-01 | Structure Erection | Limestone and dolomite to LCP | 0
531 | 2022-04-01 | Structure Erection | Limestone and dolomite to LCP | 0
532 | 2022-05-01 | Structure Erection | Limestone and dolomite to LCP | 0
533 | 2022-06-01 | Structure Erection | Limestone and dolomite to LCP | 0
534 | 2022-07-01 | Structure Erection | Limestone and dolomite to LCP | 0
535 | 2022-08-01 | Structure Erection | Limestone and dolomite to LCP
536 | 2022-09-01 | Structure Erection | Limestone and dolomite to LCP
537 | 2022-10-01 | Structure Erection | Limestone and dolomite to LCP
538 | 2022-11-01 | Structure Erection | Limestone and dolomite to LCP
539 | 2022-12-01 | Structure Erection | Limestone and dolomite to LCP
540 | 2023-01-01 | Structure Erection | Limestone and dolomite to LCP
541 | 2023-02-01 | Structure Erection | Limestone and dolomite to LCP
542 | 2023-03-01 | Structure Erection | Limestone and dolomite to LCP
543 | 2023-04-01 | Structure Erection | Limestone and dolomite to LCP
544 | 2023-05-01 | Structure Erection | Limestone and dolomite to LCP
545 | 2023-06-01 | Structure Erection | Limestone and dolomite to LCP
546 | 2023-07-01 | Structure Erection | Limestone and dolomite to LCP
547 | 2023-08-01 | Structure Erection | Limestone and dolomite to LCP
548 | 2023-09-01 | Structure Erection | Limestone and dolomite to LCP
549 | 2023-10-01 | Structure Erection | Limestone and dolomite to LCP
550 | 2023-11-01 | Structure Erection | Limestone and dolomite to LCP
551 | 2023-12-01 | Structure Erection | Limestone and dolomite to LCP
552 | 2024-01-01 | Structure Erection | Limestone and dolomite to LCP
553 | 2022-03-01 | Mechanical | Yard equipments & conveyors | 0
554 | 2022-04-01 | Mechanical | Yard equipments & conveyors | 0
555 | 2022-05-01 | Mechanical | Yard equipments & conveyors | 0
556 | 2022-06-01 | Mechanical | Yard equipments & conveyors | 0
557 | 2022-07-01 | Mechanical | Yard equipments & conveyors | 0
558 | 2022-08-01 | Mechanical | Yard equipments & conveyors
559 | 2022-09-01 | Mechanical | Yard equipments & conveyors
560 | 2022-10-01 | Mechanical | Yard equipments & conveyors
561 | 2022-11-01 | Mechanical | Yard equipments & conveyors
562 | 2022-12-01 | Mechanical | Yard equipments & conveyors
563 | 2023-01-01 | Mechanical | Yard equipments & conveyors
564 | 2023-02-01 | Mechanical | Yard equipments & conveyors
565 | 2023-03-01 | Mechanical | Yard equipments & conveyors
566 | 2023-04-01 | Mechanical | Yard equipments & conveyors
567 | 2023-05-01 | Mechanical | Yard equipments & conveyors
568 | 2023-06-01 | Mechanical | Yard equipments & conveyors
569 | 2023-07-01 | Mechanical | Yard equipments & conveyors
570 | 2023-08-01 | Mechanical | Yard equipments & conveyors
571 | 2023-09-01 | Mechanical | Yard equipments & conveyors
572 | 2023-10-01 | Mechanical | Yard equipments & conveyors
573 | 2023-11-01 | Mechanical | Yard equipments & conveyors
574 | 2023-12-01 | Mechanical | Yard equipments & conveyors
575 | 2024-01-01 | Mechanical | Yard equipments & conveyors
576 | 2022-03-01 | Mechanical | Iron Ore & fluxes to BF-5 | 0
577 | 2022-04-01 | Mechanical | Iron Ore & fluxes to BF-5 | 0
578 | 2022-05-01 | Mechanical | Iron Ore & fluxes to BF-5 | 0
579 | 2022-06-01 | Mechanical | Iron Ore & fluxes to BF-5 | 0
580 | 2022-07-01 | Mechanical | Iron Ore & fluxes to BF-5 | 0
581 | 2022-08-01 | Mechanical | Iron Ore & fluxes to BF-5
582 | 2022-09-01 | Mechanical | Iron Ore & fluxes to BF-5
583 | 2022-10-01 | Mechanical | Iron Ore & fluxes to BF-5
584 | 2022-11-01 | Mechanical | Iron Ore & fluxes to BF-5
585 | 2022-12-01 | Mechanical | Iron Ore & fluxes to BF-5
586 | 2023-01-01 | Mechanical | Iron Ore & fluxes to BF-5
587 | 2023-02-01 | Mechanical | Iron Ore & fluxes to BF-5
588 | 2023-03-01 | Mechanical | Iron Ore & fluxes to BF-5
589 | 2023-04-01 | Mechanical | Iron Ore & fluxes to BF-5
590 | 2023-05-01 | Mechanical | Iron Ore & fluxes to BF-5
591 | 2023-06-01 | Mechanical | Iron Ore & fluxes to BF-5
592 | 2023-07-01 | Mechanical | Iron Ore & fluxes to BF-5
593 | 2023-08-01 | Mechanical | Iron Ore & fluxes to BF-5
594 | 2023-09-01 | Mechanical | Iron Ore & fluxes to BF-5
595 | 2023-10-01 | Mechanical | Iron Ore & fluxes to BF-5
596 | 2023-11-01 | Mechanical | Iron Ore & fluxes to BF-5
597 | 2023-12-01 | Mechanical | Iron Ore & fluxes to BF-5
598 | 2024-01-01 | Mechanical | Iron Ore & fluxes to BF-5
599 | 2022-03-01 | Mechanical | Coke Circuit from COB-5 to BF-5 | 0
600 | 2022-04-01 | Mechanical | Coke Circuit from COB-5 to BF-5 | 0
601 | 2022-05-01 | Mechanical | Coke Circuit from COB-5 to BF-5 | 0
602 | 2022-06-01 | Mechanical | Coke Circuit from COB-5 to BF-5 | 0
603 | 2022-07-01 | Mechanical | Coke Circuit from COB-5 to BF-5 | 0
604 | 2022-08-01 | Mechanical | Coke Circuit from COB-5 to BF-5
605 | 2022-09-01 | Mechanical | Coke Circuit from COB-5 to BF-5
606 | 2022-10-01 | Mechanical | Coke Circuit from COB-5 to BF-5
607 | 2022-11-01 | Mechanical | Coke Circuit from COB-5 to BF-5
608 | 2022-12-01 | Mechanical | Coke Circuit from COB-5 to BF-5
609 | 2023-01-01 | Mechanical | Coke Circuit from COB-5 to BF-5
610 | 2023-02-01 | Mechanical | Coke Circuit from COB-5 to BF-5
611 | 2023-03-01 | Mechanical | Coke Circuit from COB-5 to BF-5
612 | 2023-04-01 | Mechanical | Coke Circuit from COB-5 to BF-5
613 | 2023-05-01 | Mechanical | Coke Circuit from COB-5 to BF-5
614 | 2023-06-01 | Mechanical | Coke Circuit from COB-5 to BF-5
615 | 2023-07-01 | Mechanical | Coke Circuit from COB-5 to BF-5
616 | 2023-08-01 | Mechanical | Coke Circuit from COB-5 to BF-5
617 | 2023-09-01 | Mechanical | Coke Circuit from COB-5 to BF-5
618 | 2023-10-01 | Mechanical | Coke Circuit from COB-5 to BF-5
619 | 2023-11-01 | Mechanical | Coke Circuit from COB-5 to BF-5
620 | 2023-12-01 | Mechanical | Coke Circuit from COB-5 to BF-5
621 | 2024-01-01 | Mechanical | Coke Circuit from COB-5 to BF-5
622 | 2022-03-01 | Mechanical | BF fines to existing conveyor 18J5C1 | 0
623 | 2022-04-01 | Mechanical | BF fines to existing conveyor 18J5C1 | 0
624 | 2022-05-01 | Mechanical | BF fines to existing conveyor 18J5C1 | 0
625 | 2022-06-01 | Mechanical | BF fines to existing conveyor 18J5C1 | 0
626 | 2022-07-01 | Mechanical | BF fines to existing conveyor 18J5C1 | 0
627 | 2022-08-01 | Mechanical | BF fines to existing conveyor 18J5C1
628 | 2022-09-01 | Mechanical | BF fines to existing conveyor 18J5C1
629 | 2022-10-01 | Mechanical | BF fines to existing conveyor 18J5C1
630 | 2022-11-01 | Mechanical | BF fines to existing conveyor 18J5C1
631 | 2022-12-01 | Mechanical | BF fines to existing conveyor 18J5C1
632 | 2023-01-01 | Mechanical | BF fines to existing conveyor 18J5C1
633 | 2023-02-01 | Mechanical | BF fines to existing conveyor 18J5C1
634 | 2023-03-01 | Mechanical | BF fines to existing conveyor 18J5C1
635 | 2023-04-01 | Mechanical | BF fines to existing conveyor 18J5C1
636 | 2023-05-01 | Mechanical | BF fines to existing conveyor 18J5C1
637 | 2023-06-01 | Mechanical | BF fines to existing conveyor 18J5C1
638 | 2023-07-01 | Mechanical | BF fines to existing conveyor 18J5C1
639 | 2023-08-01 | Mechanical | BF fines to existing conveyor 18J5C1
640 | 2023-09-01 | Mechanical | BF fines to existing conveyor 18J5C1
641 | 2023-10-01 | Mechanical | BF fines to existing conveyor 18J5C1
642 | 2023-11-01 | Mechanical | BF fines to existing conveyor 18J5C1
643 | 2023-12-01 | Mechanical | BF fines to existing conveyor 18J5C1
644 | 2024-01-01 | Mechanical | BF fines to existing conveyor 18J5C1
645 | 2022-03-01 | Mechanical | Conveyor route from JH 70 to PCI bunker | 0
646 | 2022-04-01 | Mechanical | Conveyor route from JH 70 to PCI bunker | 0
647 | 2022-05-01 | Mechanical | Conveyor route from JH 70 to PCI bunker | 0
648 | 2022-06-01 | Mechanical | Conveyor route from JH 70 to PCI bunker | 0
649 | 2022-07-01 | Mechanical | Conveyor route from JH 70 to PCI bunker | 0
650 | 2022-08-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
651 | 2022-09-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
652 | 2022-10-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
653 | 2022-11-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
654 | 2022-12-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
655 | 2023-01-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
656 | 2023-02-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
657 | 2023-03-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
658 | 2023-04-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
659 | 2023-05-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
660 | 2023-06-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
661 | 2023-07-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
662 | 2023-08-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
663 | 2023-09-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
664 | 2023-10-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
665 | 2023-11-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
666 | 2023-12-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
667 | 2024-01-01 | Mechanical | Conveyor route from JH 70 to PCI bunker
668 | 2022-03-01 | Mechanical | Bunker Building | 0
669 | 2022-04-01 | Mechanical | Bunker Building | 0
670 | 2022-05-01 | Mechanical | Bunker Building | 0
671 | 2022-06-01 | Mechanical | Bunker Building | 0
672 | 2022-07-01 | Mechanical | Bunker Building | 0
673 | 2022-08-01 | Mechanical | Bunker Building
674 | 2022-09-01 | Mechanical | Bunker Building
675 | 2022-10-01 | Mechanical | Bunker Building
676 | 2022-11-01 | Mechanical | Bunker Building
677 | 2022-12-01 | Mechanical | Bunker Building
678 | 2023-01-01 | Mechanical | Bunker Building
679 | 2023-02-01 | Mechanical | Bunker Building
680 | 2023-03-01 | Mechanical | Bunker Building
681 | 2023-04-01 | Mechanical | Bunker Building
682 | 2023-05-01 | Mechanical | Bunker Building
683 | 2023-06-01 | Mechanical | Bunker Building
684 | 2023-07-01 | Mechanical | Bunker Building
685 | 2023-08-01 | Mechanical | Bunker Building
686 | 2023-09-01 | Mechanical | Bunker Building
687 | 2023-10-01 | Mechanical | Bunker Building
688 | 2023-11-01 | Mechanical | Bunker Building
689 | 2023-12-01 | Mechanical | Bunker Building
690 | 2024-01-01 | Mechanical | Bunker Building
691 | 2022-03-01 | Mechanical | Sinter and pellet to BF-5 | 0
692 | 2022-04-01 | Mechanical | Sinter and pellet to BF-5 | 0
693 | 2022-05-01 | Mechanical | Sinter and pellet to BF-5 | 0
694 | 2022-06-01 | Mechanical | Sinter and pellet to BF-5 | 0
695 | 2022-07-01 | Mechanical | Sinter and pellet to BF-5 | 0
696 | 2022-08-01 | Mechanical | Sinter and pellet to BF-5
697 | 2022-09-01 | Mechanical | Sinter and pellet to BF-5
698 | 2022-10-01 | Mechanical | Sinter and pellet to BF-5
699 | 2022-11-01 | Mechanical | Sinter and pellet to BF-5
700 | 2022-12-01 | Mechanical | Sinter and pellet to BF-5
701 | 2023-01-01 | Mechanical | Sinter and pellet to BF-5
702 | 2023-02-01 | Mechanical | Sinter and pellet to BF-5
703 | 2023-03-01 | Mechanical | Sinter and pellet to BF-5
704 | 2023-04-01 | Mechanical | Sinter and pellet to BF-5
705 | 2023-05-01 | Mechanical | Sinter and pellet to BF-5
706 | 2023-06-01 | Mechanical | Sinter and pellet to BF-5
707 | 2023-07-01 | Mechanical | Sinter and pellet to BF-5
708 | 2023-08-01 | Mechanical | Sinter and pellet to BF-5
709 | 2023-09-01 | Mechanical | Sinter and pellet to BF-5
710 | 2023-10-01 | Mechanical | Sinter and pellet to BF-5
711 | 2023-11-01 | Mechanical | Sinter and pellet to BF-5
712 | 2023-12-01 | Mechanical | Sinter and pellet to BF-5
713 | 2024-01-01 | Mechanical | Sinter and pellet to BF-5
714 | 2022-03-01 | Mechanical | Limestone and dolomite to LCP | 0
715 | 2022-04-01 | Mechanical | Limestone and dolomite to LCP | 0
716 | 2022-05-01 | Mechanical | Limestone and dolomite to LCP | 0
717 | 2022-06-01 | Mechanical | Limestone and dolomite to LCP | 0
718 | 2022-07-01 | Mechanical | Limestone and dolomite to LCP | 0
719 | 2022-08-01 | Mechanical | Limestone and dolomite to LCP
720 | 2022-09-01 | Mechanical | Limestone and dolomite to LCP
721 | 2022-10-01 | Mechanical | Limestone and dolomite to LCP
722 | 2022-11-01 | Mechanical | Limestone and dolomite to LCP
723 | 2022-12-01 | Mechanical | Limestone and dolomite to LCP
724 | 2023-01-01 | Mechanical | Limestone and dolomite to LCP
725 | 2023-02-01 | Mechanical | Limestone and dolomite to LCP
726 | 2023-03-01 | Mechanical | Limestone and dolomite to LCP
727 | 2023-04-01 | Mechanical | Limestone and dolomite to LCP
728 | 2023-05-01 | Mechanical | Limestone and dolomite to LCP
729 | 2023-06-01 | Mechanical | Limestone and dolomite to LCP
730 | 2023-07-01 | Mechanical | Limestone and dolomite to LCP
731 | 2023-08-01 | Mechanical | Limestone and dolomite to LCP
732 | 2023-09-01 | Mechanical | Limestone and dolomite to LCP
733 | 2023-10-01 | Mechanical | Limestone and dolomite to LCP
734 | 2023-11-01 | Mechanical | Limestone and dolomite to LCP
735 | 2023-12-01 | Mechanical | Limestone and dolomite to LCP
736 | 2024-01-01 | Mechanical | Limestone and dolomite to LCP
737 | 2022-03-01 | Electrical | Yard equipments & conveyors | 0
738 | 2022-04-01 | Electrical | Yard equipments & conveyors | 0
739 | 2022-05-01 | Electrical | Yard equipments & conveyors | 0
740 | 2022-06-01 | Electrical | Yard equipments & conveyors | 0
741 | 2022-07-01 | Electrical | Yard equipments & conveyors | 0
742 | 2022-08-01 | Electrical | Yard equipments & conveyors
743 | 2022-09-01 | Electrical | Yard equipments & conveyors
744 | 2022-10-01 | Electrical | Yard equipments & conveyors
745 | 2022-11-01 | Electrical | Yard equipments & conveyors
746 | 2022-12-01 | Electrical | Yard equipments & conveyors
747 | 2023-01-01 | Electrical | Yard equipments & conveyors
748 | 2023-02-01 | Electrical | Yard equipments & conveyors
749 | 2023-03-01 | Electrical | Yard equipments & conveyors
750 | 2023-04-01 | Electrical | Yard equipments & conveyors
751 | 2023-05-01 | Electrical | Yard equipments & conveyors
752 | 2023-06-01 | Electrical | Yard equipments & conveyors
753 | 2023-07-01 | Electrical | Yard equipments & conveyors
754 | 2023-08-01 | Electrical | Yard equipments & conveyors
755 | 2023-09-01 | Electrical | Yard equipments & conveyors
756 | 2023-10-01 | Electrical | Yard equipments & conveyors
757 | 2023-11-01 | Electrical | Yard equipments & conveyors
758 | 2023-12-01 | Electrical | Yard equipments & conveyors
759 | 2024-01-01 | Electrical | Yard equipments & conveyors
760 | 2022-03-01 | Electrical | Iron Ore & fluxes to BF-5 | 0
761 | 2022-04-01 | Electrical | Iron Ore & fluxes to BF-5 | 0
762 | 2022-05-01 | Electrical | Iron Ore & fluxes to BF-5 | 0
763 | 2022-06-01 | Electrical | Iron Ore & fluxes to BF-5 | 0
764 | 2022-07-01 | Electrical | Iron Ore & fluxes to BF-5 | 0
765 | 2022-08-01 | Electrical | Iron Ore & fluxes to BF-5
766 | 2022-09-01 | Electrical | Iron Ore & fluxes to BF-5
767 | 2022-10-01 | Electrical | Iron Ore & fluxes to BF-5
768 | 2022-11-01 | Electrical | Iron Ore & fluxes to BF-5
769 | 2022-12-01 | Electrical | Iron Ore & fluxes to BF-5
770 | 2023-01-01 | Electrical | Iron Ore & fluxes to BF-5
771 | 2023-02-01 | Electrical | Iron Ore & fluxes to BF-5
772 | 2023-03-01 | Electrical | Iron Ore & fluxes to BF-5
773 | 2023-04-01 | Electrical | Iron Ore & fluxes to BF-5
774 | 2023-05-01 | Electrical | Iron Ore & fluxes to BF-5
775 | 2023-06-01 | Electrical | Iron Ore & fluxes to BF-5
776 | 2023-07-01 | Electrical | Iron Ore & fluxes to BF-5
777 | 2023-08-01 | Electrical | Iron Ore & fluxes to BF-5
778 | 2023-09-01 | Electrical | Iron Ore & fluxes to BF-5
779 | 2023-10-01 | Electrical | Iron Ore & fluxes to BF-5
780 | 2023-11-01 | Electrical | Iron Ore & fluxes to BF-5
781 | 2023-12-01 | Electrical | Iron Ore & fluxes to BF-5
782 | 2024-01-01 | Electrical | Iron Ore & fluxes to BF-5
783 | 2022-03-01 | Electrical | Coke Circuit from COB-5 to BF-5 | 0
784 | 2022-04-01 | Electrical | Coke Circuit from COB-5 to BF-5 | 0
785 | 2022-05-01 | Electrical | Coke Circuit from COB-5 to BF-5 | 0
786 | 2022-06-01 | Electrical | Coke Circuit from COB-5 to BF-5 | 0
787 | 2022-07-01 | Electrical | Coke Circuit from COB-5 to BF-5 | 0
788 | 2022-08-01 | Electrical | Coke Circuit from COB-5 to BF-5
789 | 2022-09-01 | Electrical | Coke Circuit from COB-5 to BF-5
790 | 2022-10-01 | Electrical | Coke Circuit from COB-5 to BF-5
791 | 2022-11-01 | Electrical | Coke Circuit from COB-5 to BF-5
792 | 2022-12-01 | Electrical | Coke Circuit from COB-5 to BF-5
793 | 2023-01-01 | Electrical | Coke Circuit from COB-5 to BF-5
794 | 2023-02-01 | Electrical | Coke Circuit from COB-5 to BF-5
795 | 2023-03-01 | Electrical | Coke Circuit from COB-5 to BF-5
796 | 2023-04-01 | Electrical | Coke Circuit from COB-5 to BF-5
797 | 2023-05-01 | Electrical | Coke Circuit from COB-5 to BF-5
798 | 2023-06-01 | Electrical | Coke Circuit from COB-5 to BF-5
799 | 2023-07-01 | Electrical | Coke Circuit from COB-5 to BF-5
800 | 2023-08-01 | Electrical | Coke Circuit from COB-5 to BF-5
801 | 2023-09-01 | Electrical | Coke Circuit from COB-5 to BF-5
802 | 2023-10-01 | Electrical | Coke Circuit from COB-5 to BF-5
803 | 2023-11-01 | Electrical | Coke Circuit from COB-5 to BF-5
804 | 2023-12-01 | Electrical | Coke Circuit from COB-5 to BF-5
805 | 2024-01-01 | Electrical | Coke Circuit from COB-5 to BF-5
806 | 2022-03-01 | Electrical | BF fines to existing conveyor 18J5C1 | 0
807 | 2022-04-01 | Electrical | BF fines to existing conveyor 18J5C1 | 0
808 | 2022-05-01 | Electrical | BF fines to existing conveyor 18J5C1 | 0
809 | 2022-06-01 | Electrical | BF fines to existing conveyor 18J5C1 | 0
810 | 2022-07-01 | Electrical | BF fines to existing conveyor 18J5C1 | 0
811 | 2022-08-01 | Electrical | BF fines to existing conveyor 18J5C1
812 | 2022-09-01 | Electrical | BF fines to existing conveyor 18J5C1
813 | 2022-10-01 | Electrical | BF fines to existing conveyor 18J5C1
814 | 2022-11-01 | Electrical | BF fines to existing conveyor 18J5C1
815 | 2022-12-01 | Electrical | BF fines to existing conveyor 18J5C1
816 | 2023-01-01 | Electrical | BF fines to existing conveyor 18J5C1
817 | 2023-02-01 | Electrical | BF fines to existing conveyor 18J5C1
818 | 2023-03-01 | Electrical | BF fines to existing conveyor 18J5C1
819 | 2023-04-01 | Electrical | BF fines to existing conveyor 18J5C1
820 | 2023-05-01 | Electrical | BF fines to existing conveyor 18J5C1
821 | 2023-06-01 | Electrical | BF fines to existing conveyor 18J5C1
822 | 2023-07-01 | Electrical | BF fines to existing conveyor 18J5C1
823 | 2023-08-01 | Electrical | BF fines to existing conveyor 18J5C1
824 | 2023-09-01 | Electrical | BF fines to existing conveyor 18J5C1
825 | 2023-10-01 | Electrical | BF fines to existing conveyor 18J5C1
826 | 2023-11-01 | Electrical | BF fines to existing conveyor 18J5C1
827 | 2023-12-01 | Electrical | BF fines to existing conveyor 18J5C1
828 | 2024-01-01 | Electrical | BF fines to existing conveyor 18J5C1
829 | 2022-03-01 | Electrical | Conveyor route from JH 70 to PCI bunker | 0
830 | 2022-04-01 | Electrical | Conveyor route from JH 70 to PCI bunker | 0
831 | 2022-05-01 | Electrical | Conveyor route from JH 70 to PCI bunker | 0
832 | 2022-06-01 | Electrical | Conveyor route from JH 70 to PCI bunker | 0
833 | 2022-07-01 | Electrical | Conveyor route from JH 70 to PCI bunker | 0
834 | 2022-08-01 | Electrical | Conveyor route from JH 70 to PCI bunker
835 | 2022-09-01 | Electrical | Conveyor route from JH 70 to PCI bunker
836 | 2022-10-01 | Electrical | Conveyor route from JH 70 to PCI bunker
837 | 2022-11-01 | Electrical | Conveyor route from JH 70 to PCI bunker
838 | 2022-12-01 | Electrical | Conveyor route from JH 70 to PCI bunker
839 | 2023-01-01 | Electrical | Conveyor route from JH 70 to PCI bunker
840 | 2023-02-01 | Electrical | Conveyor route from JH 70 to PCI bunker
841 | 2023-03-01 | Electrical | Conveyor route from JH 70 to PCI bunker
842 | 2023-04-01 | Electrical | Conveyor route from JH 70 to PCI bunker
843 | 2023-05-01 | Electrical | Conveyor route from JH 70 to PCI bunker
844 | 2023-06-01 | Electrical | Conveyor route from JH 70 to PCI bunker
845 | 2023-07-01 | Electrical | Conveyor route from JH 70 to PCI bunker
846 | 2023-08-01 | Electrical | Conveyor route from JH 70 to PCI bunker
847 | 2023-09-01 | Electrical | Conveyor route from JH 70 to PCI bunker
848 | 2023-10-01 | Electrical | Conveyor route from JH 70 to PCI bunker
849 | 2023-11-01 | Electrical | Conveyor route from JH 70 to PCI bunker
850 | 2023-12-01 | Electrical | Conveyor route from JH 70 to PCI bunker
851 | 2024-01-01 | Electrical | Conveyor route from JH 70 to PCI bunker
852 | 2022-03-01 | Electrical | Bunker Building | 0
853 | 2022-04-01 | Electrical | Bunker Building | 0
854 | 2022-05-01 | Electrical | Bunker Building | 0
855 | 2022-06-01 | Electrical | Bunker Building | 0
856 | 2022-07-01 | Electrical | Bunker Building | 0
857 | 2022-08-01 | Electrical | Bunker Building
858 | 2022-09-01 | Electrical | Bunker Building
859 | 2022-10-01 | Electrical | Bunker Building
860 | 2022-11-01 | Electrical | Bunker Building
861 | 2022-12-01 | Electrical | Bunker Building
862 | 2023-01-01 | Electrical | Bunker Building
863 | 2023-02-01 | Electrical | Bunker Building
864 | 2023-03-01 | Electrical | Bunker Building
865 | 2023-04-01 | Electrical | Bunker Building
866 | 2023-05-01 | Electrical | Bunker Building
867 | 2023-06-01 | Electrical | Bunker Building
868 | 2023-07-01 | Electrical | Bunker Building
869 | 2023-08-01 | Electrical | Bunker Building
870 | 2023-09-01 | Electrical | Bunker Building
871 | 2023-10-01 | Electrical | Bunker Building
872 | 2023-11-01 | Electrical | Bunker Building
873 | 2023-12-01 | Electrical | Bunker Building
874 | 2024-01-01 | Electrical | Bunker Building
875 | 2022-03-01 | Electrical | Sinter and pellet to BF-5 | 0
876 | 2022-04-01 | Electrical | Sinter and pellet to BF-5 | 0
877 | 2022-05-01 | Electrical | Sinter and pellet to BF-5 | 0
878 | 2022-06-01 | Electrical | Sinter and pellet to BF-5 | 0
879 | 2022-07-01 | Electrical | Sinter and pellet to BF-5 | 0
880 | 2022-08-01 | Electrical | Sinter and pellet to BF-5
881 | 2022-09-01 | Electrical | Sinter and pellet to BF-5
882 | 2022-10-01 | Electrical | Sinter and pellet to BF-5
883 | 2022-11-01 | Electrical | Sinter and pellet to BF-5
884 | 2022-12-01 | Electrical | Sinter and pellet to BF-5
885 | 2023-01-01 | Electrical | Sinter and pellet to BF-5
886 | 2023-02-01 | Electrical | Sinter and pellet to BF-5
887 | 2023-03-01 | Electrical | Sinter and pellet to BF-5
888 | 2023-04-01 | Electrical | Sinter and pellet to BF-5
889 | 2023-05-01 | Electrical | Sinter and pellet to BF-5
890 | 2023-06-01 | Electrical | Sinter and pellet to BF-5
891 | 2023-07-01 | Electrical | Sinter and pellet to BF-5
892 | 2023-08-01 | Electrical | Sinter and pellet to BF-5
893 | 2023-09-01 | Electrical | Sinter and pellet to BF-5
894 | 2023-10-01 | Electrical | Sinter and pellet to BF-5
895 | 2023-11-01 | Electrical | Sinter and pellet to BF-5
896 | 2023-12-01 | Electrical | Sinter and pellet to BF-5
897 | 2024-01-01 | Electrical | Sinter and pellet to BF-5
898 | 2022-03-01 | Electrical | Limestone and dolomite to LCP | 0
899 | 2022-04-01 | Electrical | Limestone and dolomite to LCP | 0
900 | 2022-05-01 | Electrical | Limestone and dolomite to LCP | 0
901 | 2022-06-01 | Electrical | Limestone and dolomite to LCP | 0
902 | 2022-07-01 | Electrical | Limestone and dolomite to LCP | 0
903 | 2022-08-01 | Electrical | Limestone and dolomite to LCP
904 | 2022-09-01 | Electrical | Limestone and dolomite to LCP
905 | 2022-10-01 | Electrical | Limestone and dolomite to LCP
906 | 2022-11-01 | Electrical | Limestone and dolomite to LCP
907 | 2022-12-01 | Electrical | Limestone and dolomite to LCP
908 | 2023-01-01 | Electrical | Limestone and dolomite to LCP
909 | 2023-02-01 | Electrical | Limestone and dolomite to LCP
910 | 2023-03-01 | Electrical | Limestone and dolomite to LCP
911 | 2023-04-01 | Electrical | Limestone and dolomite to LCP
912 | 2023-05-01 | Electrical | Limestone and dolomite to LCP
913 | 2023-06-01 | Electrical | Limestone and dolomite to LCP
914 | 2023-07-01 | Electrical | Limestone and dolomite to LCP
915 | 2023-08-01 | Electrical | Limestone and dolomite to LCP
916 | 2023-09-01 | Electrical | Limestone and dolomite to LCP
917 | 2023-10-01 | Electrical | Limestone and dolomite to LCP
918 | 2023-11-01 | Electrical | Limestone and dolomite to LCP
919 | 2023-12-01 | Electrical | Limestone and dolomite to LCP
920 | 2024-01-01 | Electrical | Limestone and dolomite to LCP
921 | 2022-03-01 | Pilling | Yard equipments & conveyors
922 | 2022-04-01 | Pilling | Yard equipments & conveyors
923 | 2022-05-01 | Pilling | Yard equipments & conveyors
924 | 2022-06-01 | Pilling | Yard equipments & conveyors
925 | 2022-07-01 | Pilling | Yard equipments & conveyors
926 | 2022-08-01 | Pilling | Yard equipments & conveyors
927 | 2022-09-01 | Pilling | Yard equipments & conveyors
928 | 2022-10-01 | Pilling | Yard equipments & conveyors
929 | 2022-11-01 | Pilling | Yard equipments & conveyors
930 | 2022-12-01 | Pilling | Yard equipments & conveyors
931 | 2023-01-01 | Pilling | Yard equipments & conveyors
932 | 2023-02-01 | Pilling | Yard equipments & conveyors
933 | 2023-03-01 | Pilling | Yard equipments & conveyors
934 | 2023-04-01 | Pilling | Yard equipments & conveyors
935 | 2023-05-01 | Pilling | Yard equipments & conveyors
936 | 2023-06-01 | Pilling | Yard equipments & conveyors
937 | 2023-07-01 | Pilling | Yard equipments & conveyors
938 | 2023-08-01 | Pilling | Yard equipments & conveyors
939 | 2023-09-01 | Pilling | Yard equipments & conveyors
940 | 2023-10-01 | Pilling | Yard equipments & conveyors
941 | 2023-11-01 | Pilling | Yard equipments & conveyors
942 | 2023-12-01 | Pilling | Yard equipments & conveyors
943 | 2024-01-01 | Pilling | Yard equipments & conveyors
944 | 2022-03-01 | Pilling | Iron Ore & fluxes to BF-5
945 | 2022-04-01 | Pilling | Iron Ore & fluxes to BF-5
946 | 2022-05-01 | Pilling | Iron Ore & fluxes to BF-5
947 | 2022-06-01 | Pilling | Iron Ore & fluxes to BF-5
948 | 2022-07-01 | Pilling | Iron Ore & fluxes to BF-5
949 | 2022-08-01 | Pilling | Iron Ore & fluxes to BF-5 | 183
950 | 2022-09-01 | Pilling | Iron Ore & fluxes to BF-5
951 | 2022-10-01 | Pilling | Iron Ore & fluxes to BF-5
952 | 2022-11-01 | Pilling | Iron Ore & fluxes to BF-5
953 | 2022-12-01 | Pilling | Iron Ore & fluxes to BF-5
954 | 2023-01-01 | Pilling | Iron Ore & fluxes to BF-5
955 | 2023-02-01 | Pilling | Iron Ore & fluxes to BF-5
956 | 2023-03-01 | Pilling | Iron Ore & fluxes to BF-5
957 | 2023-04-01 | Pilling | Iron Ore & fluxes to BF-5
958 | 2023-05-01 | Pilling | Iron Ore & fluxes to BF-5
959 | 2023-06-01 | Pilling | Iron Ore & fluxes to BF-5
960 | 2023-07-01 | Pilling | Iron Ore & fluxes to BF-5
961 | 2023-08-01 | Pilling | Iron Ore & fluxes to BF-5
962 | 2023-09-01 | Pilling | Iron Ore & fluxes to BF-5
963 | 2023-10-01 | Pilling | Iron Ore & fluxes to BF-5
964 | 2023-11-01 | Pilling | Iron Ore & fluxes to BF-5
965 | 2023-12-01 | Pilling | Iron Ore & fluxes to BF-5
966 | 2024-01-01 | Pilling | Iron Ore & fluxes to BF-5
967 | 2022-03-01 | Pilling | Coke Circuit from COB-5 to BF-5
968 | 2022-04-01 | Pilling | Coke Circuit from COB-5 to BF-5
969 | 2022-05-01 | Pilling | Coke Circuit from COB-5 to BF-5
970 | 2022-06-01 | Pilling | Coke Circuit from COB-5 to BF-5
971 | 2022-07-01 | Pilling | Coke Circuit from COB-5 to BF-5
972 | 2022-08-01 | Pilling | Coke Circuit from COB-5 to BF-5
973 | 2022-09-01 | Pilling | Coke Circuit from COB-5 to BF-5 | 114
974 | 2022-10-01 | Pilling | Coke Circuit from COB-5 to BF-5
975 | 2022-11-01 | Pilling | Coke Circuit from COB-5 to BF-5
976 | 2022-12-01 | Pilling | Coke Circuit from COB-5 to BF-5
977 | 2023-01-01 | Pilling | Coke Circuit from COB-5 to BF-5
978 | 2023-02-01 | Pilling | Coke Circuit from COB-5 to BF-5
979 | 2023-03-01 | Pilling | Coke Circuit from COB-5 to BF-5
980 | 2023-04-01 | Pilling | Coke Circuit from COB-5 to BF-5
981 | 2023-05-01 | Pilling | Coke Circuit from COB-5 to BF-5
982 | 2023-06-01 | Pilling | Coke Circuit from COB-5 to BF-5
983 | 2023-07-01 | Pilling | Coke Circuit from COB-5 to BF-5
984 | 2023-08-01 | Pilling | Coke Circuit from COB-5 to BF-5
985 | 2023-09-01 | Pilling | Coke Circuit from COB-5 to BF-5
986 | 2023-10-01 | Pilling | Coke Circuit from COB-5 to BF-5
987 | 2023-11-01 | Pilling | Coke Circuit from COB-5 to BF-5
988 | 2023-12-01 | Pilling | Coke Circuit from COB-5 to BF-5
989 | 2024-01-01 | Pilling | Coke Circuit from COB-5 to BF-5
990 | 2022-03-01 | Pilling | BF fines to existing conveyor 18J5C1
991 | 2022-04-01 | Pilling | BF fines to existing conveyor 18J5C1
992 | 2022-05-01 | Pilling | BF fines to existing conveyor 18J5C1
993 | 2022-06-01 | Pilling | BF fines to existing conveyor 18J5C1
994 | 2022-07-01 | Pilling | BF fines to existing conveyor 18J5C1
995 | 2022-08-01 | Pilling | BF fines to existing conveyor 18J5C1
996 | 2022-09-01 | Pilling | BF fines to existing conveyor 18J5C1
997 | 2022-10-01 | Pilling | BF fines to existing conveyor 18J5C1
998 | 2022-11-01 | Pilling | BF fines to existing conveyor 18J5C1
999 | 2022-12-01 | Pilling | BF fines to existing conveyor 18J5C1
1000 | 2023-01-01 | Pilling | BF fines to existing conveyor 18J5C1
1001 | 2023-02-01 | Pilling | BF fines to existing conveyor 18J5C1
1002 | 2023-03-01 | Pilling | BF fines to existing conveyor 18J5C1
1003 | 2023-04-01 | Pilling | BF fines to existing conveyor 18J5C1
1004 | 2023-05-01 | Pilling | BF fines to existing conveyor 18J5C1
1005 | 2023-06-01 | Pilling | BF fines to existing conveyor 18J5C1
1006 | 2023-07-01 | Pilling | BF fines to existing conveyor 18J5C1
1007 | 2023-08-01 | Pilling | BF fines to existing conveyor 18J5C1
1008 | 2023-09-01 | Pilling | BF fines to existing conveyor 18J5C1
1009 | 2023-10-01 | Pilling | BF fines to existing conveyor 18J5C1
1010 | 2023-11-01 | Pilling | BF fines to existing conveyor 18J5C1
1011 | 2023-12-01 | Pilling | BF fines to existing conveyor 18J5C1
1012 | 2024-01-01 | Pilling | BF fines to existing conveyor 18J5C1
1013 | 2022-03-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1014 | 2022-04-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1015 | 2022-05-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1016 | 2022-06-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1017 | 2022-07-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1018 | 2022-08-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1019 | 2022-09-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1020 | 2022-10-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1021 | 2022-11-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1022 | 2022-12-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1023 | 2023-01-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1024 | 2023-02-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1025 | 2023-03-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1026 | 2023-04-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1027 | 2023-05-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1028 | 2023-06-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1029 | 2023-07-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1030 | 2023-08-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1031 | 2023-09-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1032 | 2023-10-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1033 | 2023-11-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1034 | 2023-12-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1035 | 2024-01-01 | Pilling | Conveyor route from JH 70 to PCI bunker
1036 | 2022-03-01 | Pilling | Bunker Building
1037 | 2022-04-01 | Pilling | Bunker Building
1038 | 2022-05-01 | Pilling | Bunker Building
1039 | 2022-06-01 | Pilling | Bunker Building
1040 | 2022-07-01 | Pilling | Bunker Building
1041 | 2022-08-01 | Pilling | Bunker Building
1042 | 2022-09-01 | Pilling | Bunker Building
1043 | 2022-10-01 | Pilling | Bunker Building
1044 | 2022-11-01 | Pilling | Bunker Building
1045 | 2022-12-01 | Pilling | Bunker Building
1046 | 2023-01-01 | Pilling | Bunker Building
1047 | 2023-02-01 | Pilling | Bunker Building
1048 | 2023-03-01 | Pilling | Bunker Building
1049 | 2023-04-01 | Pilling | Bunker Building
1050 | 2023-05-01 | Pilling | Bunker Building
1051 | 2023-06-01 | Pilling | Bunker Building
1052 | 2023-07-01 | Pilling | Bunker Building
1053 | 2023-08-01 | Pilling | Bunker Building
1054 | 2023-09-01 | Pilling | Bunker Building
1055 | 2023-10-01 | Pilling | Bunker Building
1056 | 2023-11-01 | Pilling | Bunker Building
1057 | 2023-12-01 | Pilling | Bunker Building
1058 | 2024-01-01 | Pilling | Bunker Building
1059 | 2022-03-01 | Pilling | Sinter and pellet to BF-5
1060 | 2022-04-01 | Pilling | Sinter and pellet to BF-5
1061 | 2022-05-01 | Pilling | Sinter and pellet to BF-5
1062 | 2022-06-01 | Pilling | Sinter and pellet to BF-5
1063 | 2022-07-01 | Pilling | Sinter and pellet to BF-5
1064 | 2022-08-01 | Pilling | Sinter and pellet to BF-5
1065 | 2022-09-01 | Pilling | Sinter and pellet to BF-5
1066 | 2022-10-01 | Pilling | Sinter and pellet to BF-5
1067 | 2022-11-01 | Pilling | Sinter and pellet to BF-5
1068 | 2022-12-01 | Pilling | Sinter and pellet to BF-5
1069 | 2023-01-01 | Pilling | Sinter and pellet to BF-5
1070 | 2023-02-01 | Pilling | Sinter and pellet to BF-5
1071 | 2023-03-01 | Pilling | Sinter and pellet to BF-5
1072 | 2023-04-01 | Pilling | Sinter and pellet to BF-5
1073 | 2023-05-01 | Pilling | Sinter and pellet to BF-5
1074 | 2023-06-01 | Pilling | Sinter and pellet to BF-5
1075 | 2023-07-01 | Pilling | Sinter and pellet to BF-5
1076 | 2023-08-01 | Pilling | Sinter and pellet to BF-5
1077 | 2023-09-01 | Pilling | Sinter and pellet to BF-5
1078 | 2023-10-01 | Pilling | Sinter and pellet to BF-5
1079 | 2023-11-01 | Pilling | Sinter and pellet to BF-5
1080 | 2023-12-01 | Pilling | Sinter and pellet to BF-5
1081 | 2024-01-01 | Pilling | Sinter and pellet to BF-5
1082 | 2022-03-01 | Pilling | Limestone and dolomite to LCP
1083 | 2022-04-01 | Pilling | Limestone and dolomite to LCP
1084 | 2022-05-01 | Pilling | Limestone and dolomite to LCP
1085 | 2022-06-01 | Pilling | Limestone and dolomite to LCP
1086 | 2022-07-01 | Pilling | Limestone and dolomite to LCP
1087 | 2022-08-01 | Pilling | Limestone and dolomite to LCP
1088 | 2022-09-01 | Pilling | Limestone and dolomite to LCP
1089 | 2022-10-01 | Pilling | Limestone and dolomite to LCP
1090 | 2022-11-01 | Pilling | Limestone and dolomite to LCP
1091 | 2022-12-01 | Pilling | Limestone and dolomite to LCP
1092 | 2023-01-01 | Pilling | Limestone and dolomite to LCP
1093 | 2023-02-01 | Pilling | Limestone and dolomite to LCP
1094 | 2023-03-01 | Pilling | Limestone and dolomite to LCP
1095 | 2023-04-01 | Pilling | Limestone and dolomite to LCP
1096 | 2023-05-01 | Pilling | Limestone and dolomite to LCP
1097 | 2023-06-01 | Pilling | Limestone and dolomite to LCP
1098 | 2023-07-01 | Pilling | Limestone and dolomite to LCP
1099 | 2023-08-01 | Pilling | Limestone and dolomite to LCP
1100 | 2023-09-01 | Pilling | Limestone and dolomite to LCP
1101 | 2023-10-01 | Pilling | Limestone and dolomite to LCP
1102 | 2023-11-01 | Pilling | Limestone and dolomite to LCP
1103 | 2023-12-01 | Pilling | Limestone and dolomite to LCP
1104 | 2024-01-01 | Pilling | Limestone and dolomite to LCP

## Drawing Report.
Sr No | Area | Drawing Number | Description | Type of Drawing | Start Date | Received Date | Revised Date | UOM | Quantity
1 | Coke Circuit from COB-5 to BF-5 | 6701 | Conveyor Gallery 18J44C1C2 | Civil |  | 2022-05-10 |  | Cum | 615
2 | Coke Circuit from COB-5 to BF-5 | 6728 | Conv. Gallery 18J43C1C2 – Layout Plan of Foundation (TR-1 to TR-7) | Civil |  | 2022-03-02 | 2022-08-20 | Cum | 160
3 | Coke Circuit from COB-5 to BF-5 | 6729 | Conv. Gallery 18J43C1C2 – Sand Pit drawing | Civil |  | 2022-03-14 |  | Cum | 8
4 | Coke Circuit from COB-5 to BF-5 | 6731 | Conveyor Gallery 18J46C1C2 | Civil |  | 2022-04-02 | 2022-05-04 | Cum | 203
5 | Coke Circuit from COB-5 to BF-5 | 7151 | Junction House 18JH44 | Civil |  | 2022-07-06 |  | Cum | 315
6 | Coke Circuit from COB-5 to BF-5 | 6737 | Junction House 18JH44 | Civil |  | 2022-04-02 |  | Cum | 120 | 225
7 | Coke Circuit from COB-5 to BF-5 | 6734 | Conveyor Gallery 18J45C1C2 | Pile |  | 2022-03-09 | 2022-03-14 | No's | 166
8 | Iron Ore & fluxes to BF-5 | 6730 | Conveyor Gallery 18J46C1C2 | Pile |  | 2022-03-10 | 2022-05-04 | No's | 92
9 | Coke Circuit from COB-5 to BF-5 | 7150 | Junction House 18J46 | Pile |  | 2022-06-17 |  | No's | 84
10 | Iron Ore & fluxes to BF-5 | 6765 | Junction House 18J47 | Pile |  | 2022-07-15 |  | No's | 98
11 | Coke Circuit from COB-5 to BF-5 | 6736 | Junction House 18JH44 | Pile |  | 2022-03-14 | 2022-04-02 | No's | 52
12 | Coke Circuit from COB-5 to BF-5 |  | Conveyor Gallery 18J45C1C2 | Structure |  | 2022-01-15 |  | MT | 851.85
13 | Iron Ore & fluxes to BF-5 | 11231to 11247 | Conveyor Gallery 18J46C3C4C5 | Structure |  | 2022-07-21 |  | MT | 1734
14 | Coke Circuit from COB-5 to BF-5 | 1121 to 11226 | Conveyor Gallery 18J43C1C2 | Structure |  | 2022-02-01 |  | MT | 267
15 | Coke Circuit from COB-5 to BF-5 | 12402 to 12403 | Conveyor Gallery 18J44C1C2 | Structure |  | 2022-01-25 |  | MT | 103.518 |  | 3114
16 | Coke Circuit from COB-5 to BF-5 | 12402 to 12403 | Conveyor Gallery 18J44C1C2 | Structure |  | 2022-02-19 |  | MT | 78.624
17 | Coke Circuit from COB-5 to BF-5 | 12408 | Conveyor Gallery 18J44C1C2 | Structure |  | 2022-03-10 |  | MT | 446.752
18 | Coke Circuit from COB-5 to BF-5 | 12408 to 12410 | Conveyor Gallery 18J44C1C2 | Structure |  | 2022-03-06 |  | MT | 113.806
19 | Coke Circuit from COB-5 to BF-5 | 11207 to 11216 | Conveyor Gallery 18J46C1C2 | Structure |  | 2022-01-15 | 2022-03-11 | MT | 1106
20 | Coke Circuit from COB-5 to BF-5 | 12252 to 12257 | Junction House 18J44 | Structure |  | 2022-03-30 |  | MT | 19.554
21 | Coke Circuit from COB-5 to BF-5 | 12258 to 12263 | Junction House 18J44 | Structure |  | 2022-04-13 |  | MT | 154.946
22 | Coke Circuit from COB-5 to BF-5 | 12256 to 11259 | Junction House 18J45 | Structure |  | 2022-04-29 |  | MT | 133
23 | Coke Circuit from COB-5 to BF-5 | 11251 to 11254 | Junction House 18JH43 | Structure |  | 2022-03-11 |  | MT | 125.3
24 | Iron Ore & fluxes to BF-5 | 11261 to 11267 | Junction House 18J46 | Structure |  | 2022-07-18 |  | MT | 595.5
25 | Iron Ore & fluxes to BF-5 | 2622 to 2626 | Junction House 18J63 | Structure |  | 2022-07-27 |  | MT | 110.52
| Bunker Building |  | PCI Bunker Building | Structure |  | 2022-06-15 |  | MT | 1216
| Sinter and pellet to BF-5 |  | Sinter and pellet to BF-5 | Structure |  | 2021-11-15 |  | MT | 800 | 600
| Iron Ore & fluxes to BF-5 |  | Junction House 18JH47 | Structure |  | 2022-08-13 |  | MT | 674.3
| Iron Ore & fluxes to BF-5 |  | Junction House 18JH68 | Structure |  | 2022-08-19 |  | MT | 116
| Iron Ore & fluxes to BF-5 |  | Junction House 18JH68 | Civil |  | 2022-09-03 |  | Cum | 175 |  | 5616
| Iron Ore & fluxes to BF-5 |  | Conveyor Gallery 18J64C1 | Civil |  | 2022-09-03 | 2022-09-08 | Cum | 48
| Iron Ore & fluxes to BF-5 |  | Junction House 18JH63 | Civil |  | 2022-09-03 |  | Cum | 118
| Iron Ore & fluxes to BF-5 |  | Junction House 18JH64 | Civil |  | 2022-09-03 |  | Cum | 85
| Iron Ore & fluxes to BF-5 |  | Conveyor Gallery 18J64C1 | Structure |  | 2022-09-02 |  | MT | 49
| Iron Ore & fluxes to BF-5 | 6772 | Junction House 18JH65 | Civil |  | 2022-09-15 |  | Cum | 217
| Iron Ore & fluxes to BF-5 | 15821 to 15826 | Junction House 18JH69 | Structure |  | 2022-09-13 |  | MT | 169
| Iron Ore & fluxes to BF-5 | 11284 to 11300 | Conveyor Gallery 18J67C1C2 | Structure |  | 2022-09-15 |  | MT | 1322
| Iron Ore & fluxes to BF-5 | 6773 | Junction House 18JH66 | Civil |  | 2022-09-12 |  | Cum | 170