## Sheet1 (hidden)
JSW VML BLAST FURNACE
DAILY PROGRESS REPORT
D.O.P | 03.07.2021
SL.NO | ACTIVITY DESCRIPTION | UNIT | EST.TOTAL SCOPE | ACTUAL SCOPE | DRAWINGS RECEIPT | CUM.COMPLETED JUNE'21 | JULY ' 21 |  |  |  | CUMM. ACHIEVED | CUMM. BALANCE | % OF CUMM. ACHIEVED | Remarks
[7 empty] | MONTH PLAN | MONTH ACHIEVED | DAY PLAN | DAY ACHIEVED
1 | CIVIL
i | PILING | NOS | 6500 | 6514 | 4339 | 2012 | 1000 | 99 | 61 | 41 | 2111 | 4389 | 32.4769
ii | PILE CHIPPING | NOS | 6500 | 6514 | 4339 | 746 |  | 59 | 38 | 36 | 850 | 5650 | 13.0769
iii | RCC | CUM | 105000 |  | 22865 | 0 | 750 | 0 | 0 | 24.1935 | 0 | 105000 | 0
2 | STRUCUTRAL |  | 51634
i | BUILDING STR FABRICATON | MT | 33585 |  | 1043 | 0 | 150 | 0 | 4.8387 | 0 | 0 | 33585 | 0 | Request to Plan Fabrication of 750 MT instead of 150 MT in Building Structures dtd 02.07.2021
ii | BUILDING STR ERECTION | MT | 33585 |  | 1043 | 0 | 0 | 0 | 0 | 0 | 0 | 33585 | 0
iii | TECH STR FABRICATON | MT | 18049 |  | 1400.32 | 0 | 192 | 0 | 6.1935 | 0 | 0 | 18049 | 0 | Furnace Shell rolling started
iv | TECH STR ERECTION | MT | 18049 |  | 1400.32 | 0 | 0 | 0 | 0 | 0 | 0 | 18049 | 0
3 | EQUIPMENT RECEIPT | MT | 17955 |  | 2897 | 0 | 0 | 0 | 0 | 0 | 0 | 17955 | 0
4 | EQUIPMENT ERECTION | MT | 17955 |  | 2897 | 0 | 0 | 0 | 0 | 0 | 0 | 17955 | 0
5 | REFRACTORY ERECTION | MT | 34290 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34290 | 0
6 | PIPING | INCH-MTR | 469800 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 469800 | 0
7 | CABLE TRAY | KM | 29.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 29.5 | 0
8 | CABLES | KM | 1255 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1255 | 0
9 | PANELS | NOS | 1275 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0
10 | TRANSFORMERS | NOS | 33 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0

## Mapping
Project | Blast Furnace
Work Package: | Civil
Work Item: | Piling |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 5 | End Row: 5
Actual Scope | Column: L | Start Row: 5 | End Row: 5
Plan for the Month | Column: H | Start Row: 5 | End Row: 5
Actual for the Month | Column: I | Start Row: 5 | End Row: 5
Today | Column: J | Start Row: 5 | End Row: 5
DWG Available | Column: F | Start Row: 5 | End Row: 5
Project | Project Name
Work Package: | Civil
Work Item: | RCC |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 6 | End Row: 6
Actual Scope | Column: L | Start Row: 6 | End Row: 6
Plan for the Month | Column: H | Start Row: 6 | End Row: 6
Actual for the Month | Column: I | Start Row: 6 | End Row: 6
Today | Column: J | Start Row: 6 | End Row: 6
DWG Available | Column: F | Start Row: 6 | End Row: 6
Work Item: | Structural fabrication |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 13 | End Row: 13
Actual Scope | Column: L | Start Row: 13 | End Row: 13
Plan for the Month | Column: H | Start Row: 13 | End Row: 13
Actual for the Month | Column: I | Start Row: 13 | End Row: 13
Today | Column: J | Start Row: 13 | End Row: 13
DWG Available | Column: F | Start Row: 13 | End Row: 13
Work Item: | Structural erection |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 14 | End Row: 14
Actual Scope | Column: L | Start Row: 14 | End Row: 14
Plan for the Month | Column: H | Start Row: 14 | End Row: 14
Actual for the Month | Column: I | Start Row: 14 | End Row: 14
Today | Column: J | Start Row: 14 | End Row: 14
DWG Available | Column: F | Start Row: 14 | End Row: 14
Work Item: | Equipment supply |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 35 | End Row: 35
Actual Scope | Column: L | Start Row: 35 | End Row: 35
Plan for the Month | Column: H | Start Row: 35 | End Row: 35
Actual for the Month | Column: I | Start Row: 35 | End Row: 35
Today | Column: J | Start Row: 35 | End Row: 35
DWG Available | Column: F | Start Row: 35 | End Row: 35
Work Item: | Equipment erection |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 36 | End Row: 36
Actual Scope | Column: L | Start Row: 36 | End Row: 36
Plan for the Month | Column: H | Start Row: 36 | End Row: 36
Actual for the Month | Column: I | Start Row: 36 | End Row: 36
Today | Column: J | Start Row: 36 | End Row: 36
DWG Available | Column: F | Start Row: 36 | End Row: 36
Work Item: | Piping erection |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 40 | End Row: 40
Actual Scope | Column: L | Start Row: 40 | End Row: 40
Plan for the Month | Column: H | Start Row: 40 | End Row: 40
Actual for the Month | Column: I | Start Row: 40 | End Row: 40
Today | Column: J | Start Row: 40 | End Row: 40
DWG Available | Column: F | Start Row: 40 | End Row: 40
Work Item: | Cable tray erection |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 47 | End Row: 47
Actual Scope | Column: L | Start Row: 47 | End Row: 47
Plan for the Month | Column: H | Start Row: 47 | End Row: 47
Actual for the Month | Column: I | Start Row: 47 | End Row: 47
Today | Column: J | Start Row: 47 | End Row: 47
DWG Available | Column: F | Start Row: 47 | End Row: 47
Work Item: | Cable laying |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 49 | End Row: 49
Actual Scope | Column: L | Start Row: 49 | End Row: 49
Plan for the Month | Column: H | Start Row: 49 | End Row: 49
Actual for the Month | Column: I | Start Row: 49 | End Row: 49
Today | Column: J | Start Row: 49 | End Row: 49
DWG Available | Column: F | Start Row: 49 | End Row: 49
Work Item: | Panel installation |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 51 | End Row: 51
Actual Scope | Column: L | Start Row: 51 | End Row: 51
Plan for the Month | Column: H | Start Row: 51 | End Row: 51
Actual for the Month | Column: I | Start Row: 51 | End Row: 51
Today | Column: J | Start Row: 51 | End Row: 51
DWG Available | Column: F | Start Row: 51 | End Row: 51
Work Item: | Transformer installation |  |  |  | Fixed Value | <value = Work Item Eg. 'PCC'. 'RCC'>
Data Date | Column: C | Start Row: 1 | End Row: 1 |  | Accepted Formats: | "dd-MM-yyyy", "dd.MM.yyyy", "dd/MM/yyyy", "dd-MMM-yy", "=today()", "Progress Date: dd-mm-yyyy"
Sheet Name | Overall Progress |  |  | DPR
Plan Scope | Column: E | Start Row: 53 | End Row: 53
Actual Scope | Column: L | Start Row: 53 | End Row: 53
Plan for the Month | Column: H | Start Row: 53 | End Row: 53
Actual for the Month | Column: I | Start Row: 53 | End Row: 53
Today | Column: J | Start Row: 53 | End Row: 53
DWG Available | Column: F | Start Row: 53 | End Row: 53

## Overall Progress
D.O.P |  | 2022-09-27 | Project Name - DAILY PROGRESS REPORT
SL.NO | Agency | ACTIVITY DESCRIPTION | UNIT | TOTAL SCOPE | DRAWINGS RECEIPT | CUM.COMPLETED AUG'22 | SEP' 22 |  |  |  | CUMM. ACHIEVED | CUMM. BALANCE | % OF CUMM. ACHIEVED | Remarks
[7 empty] | MONTH PLAN | MONTH ACHIEVED | DAY ACHIEVED | % ACHIEVED
1 |  | CIVIL
i | Vendor | PILING | NOS | 8678 | 8554 | 8255 | 100 | 35 | 0 | 35% | 8290 | 388 | 95.5289
| Vendor One | RCC +PCC | CUM | 113991 | 94945 | 66741.5 | 4742 | 1918.4 | 130 | 40.46% | 68443.5 | 37082.5 | 60.0429
i |  | RCC | CUM | 95526 | 86480 | 61002.5 | 3630 | 1614 | 90 | 44.46% | 62616.5 | 32909.5 | 65.5492
ii |  | PCC | CUM | 10000 |  | 5739 | 182 | 88 | 0 | 48.35% | 5827 | 4173 | 58.27
iii | Vendor 2 | RCC | CUM | 5590 | 5690 | 86 | 555 | 88 | 20 | 15.86% | 174 | 5416 | 3.1127
|  | PCC | CUM | 100 |  | 2 | 45 | 22 | 22 | 48.89% | 24 | 76 | 24
iv | vendor 3 | RCC | CUM | 1875 | 1875 | 54 | 130 | 8.4 | 0 | 6.462% | 62.4 | 1812.6 | 3.328
v | vendor 45 | RCC | CUM | 900 | 900 | 67 | 200 | 98 | 20 | 49% | 165
2 | vendor 45 | STRUCUTRAL FABRICATION |  | 66112.839 | 56245.719 | 28445.188 | 3602 | 1519.88 | 105 | 42.2% | 29965.068 | 35197.771 | 45.3241
| vendor 23 | STRUCUTRAL ERECTION |  | 68612.839 | 56245.719 | 15125.97 | 2629.67 | 893.64 | 61.71 | 33.98% | 16019.61 | 50443.229 | 23.3478
i | vendor 47 | BUILDING STR FAB | MT | 31531.451 | 29639.951 | 12776.87 | 2316 | 1050.63 | 0 | 45.36% | 13827.5 | 17703.951 | 1600
ii |  | TECH STR FAB | MT | 20123.21 | 17247.59 | 10408.01 | 326 | 144.5 | 65 | 44.33% | 10552.51 | 9570.7 | 52.4395
iii |  | BUILDING STR EREC | MT | 31531.451 | 29639.951 | 5535.6 | 1319 | 426.6 | 26 | 32.34% | 5962.2 | 25569.251 | 18.9087
iv |  | TECH STR EREC | MT | 20123.21 | 17247.59 | 7118.3 | 674 | 127 | 0 | 18.84% | 7245.3 | 12877.91 | 36.0047
i | vendor 48 | BUILDING STR FAB | MT | 4290 | 3122 | 2548.788 | 0 | 89 | 0 | #DIV/0! | 2637.788 | 1652.212 | 61.4869
ii |  | TECH STR FAB | MT | 1000 | 811 | 339 | 260 | 28 | 10 | 10.77% | 367 | 633 | 36.7
iii |  | BUILDING STR EREC | MT | 4290 | 3122 | 882 | 86.67 | 57 | 5 | 65.77% | 939 | 3351 | 21.8881
iv |  | TECH STR EREC | MT | 1000 | 811 | 0 | 0 | 0 | 0 | 0% | 0 | 1000 | 0
i | vendor 5 | BUILDING STR FAB | MT | 6745.26 | 4752.26 | 2256.52 | 650 | 172.75 | 0 | 26.58% | 2429.27 | 4315.99 | 36.0145
iii |  | BUILDING STR EREC | MT | 6745.26 | 4752.26 | 1590.07 | 550 | 283.04 | 30.71 | 51.46% | 1873.11 | 4872.15 | 27.7693
ii | vendor 6 | TECH STR FAB | MT | 800 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 800 | 0
iv |  | TECH STR EREC | MT | 800 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 800 | 0
i | vendor 20 | BUILDING STR FAB | MT | 200 | 200 | 0 | 0 | 0 | 0 | 0% | 0 | 200 | 0
ii |  | TECH STR FAB | MT | 472.918 | 472.918 | 116 | 50 | 35 | 30 | 70% | 151 | 321.918 | 31.9294
iii |  | BUILDING STR EREC | MT | 1500 | 200 | 0 | 0 | 0 | 0 | 0% | 0 | 1500 | 0
iv |  | TECH STR EREC | MT | 472.918 | 472.918 | 0 | 0 | 0 | 0 | 0% | 0 | 472.918 | 0
i | vendor 21 | BUILDING STR FAB | MT | 300 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 300 | 0
ii |  | TECH STR FAB | MT | 650 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 650 | 0
iii |  | BUILDING STR EREC | MT | 1500 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1500 | 0
iv |  | TECH STR EREC | MT | 650 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 650 | 0
3 |  | EQUIPMENT RECEIPT | MT | 17402.5 | 13595.64 | 2983.355 | 2363.09 | 1548.505 | 0 | 65.53% | 4531.86 | 12870.64 | 26.0414
4 |  | EQUIPMENT ERECTION | MT | 17402.5 | 13595.64 | 169 | 316.5 | 210.1 | 0 | 66.38% | 379.1 | 17023.4 | 2.1784
|  | REFRACTORY RECEIPT | MT | 32714 | 28214 | 6500 | 2000 | 1500 | 500 | 75% | 8000 | 24714 | 24.4544
5 |  | REFRACTORY ERECTION | MT | 32714 | 28214 | 130 | 0 | 0 | 0 | 0% | 130 | 32584 | 0.39738
|  | PIPING RECEIPT | INCH-MTR | 527185 | 345695 | 286471 | 18000 | 15000 | 0 | 0% | 301471 | 225714 | 57.185
6 |  | PIPING ERECTION | INCH-MTR | 527185 | 345695 | 19937 | 17556 | 7782.2 | 571 | 44.33% | 27719.2 | 499465.8 | 5.258
| vendor 34 | WTP & Utilities, SGP & PCI | INCH-MTR | 227000 | 160600 | 5912 | 7556 | 62.2 | 11 | 0.8232% | 5974.2 | 221025.8 | 2.6318
| vendor 35 | HYD | INCH-MTR | 27465 | 24095 | 0 | 0 | 0 | 0 | 0% | 0 | 27465 | 0
| vendor 36 | Outside Furnace WTP | INCH-MTR | 206000 | 140000 | 14025 | 10000 | 7720 | 560 | 77.2% | 21745 | 184255 | 10.5558
| vendor 37 | Outside Furnace utilities | INCH-MTR | 55000 | 10000 | 0 | 0 | 0 | 0 | 0% | 0 | 55000 | 0
| vendor 38 | Blower & TRT | INCH-MTR | 11600 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 11600 | 0
|  | CABLE TRAY RECEIPT | KM | 120 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 120 | 0
7 |  | CABLE TRAY ERECTION | KM | 120 | NA | 0 | 0.8 | 0.36 | 0 | 0% | 0.36 | 119.64 | 0.3
|  | CABLES RECEIPT | KM | 1800 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 1800 | 0
8 |  | CABLES ERECTION | KM | 1800 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 1800 | 0
|  | PANELS RECEIPT | NOS | 1275 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 1275 | 0
9 |  | PANELS ERECTION | NOS | 1275 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 1275 | 0
|  | TRANSFORMERS RECEIPT | NOS | 33 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 33 | 0
10 |  | TRANSFORMERS ERECTION | NOS | 33 | NA | 0 | 0 | 0 | 0 | 0% | 0 | 33 | 0 |  | 242
Man Power
[6 empty] | At Erection Site in nos | At Fab Site in nos
[5 empty] | vendor 1 | 1223 | 1202
[5 empty] | vendor 2 | 56 | 0
[5 empty] | vendor 3 | 30 | 98
[5 empty] | vendor 4 | 0 | 12
[5 empty] | vendor 5 | 82 | 0
[5 empty] | vendor 6 | 30 | 0
[5 empty] | vendor 7 | 19 | 0
[5 empty] | Total | 1440 | 1312
218
|  | Civil Drawings Yet to receive from MECON | Dates committed |  | Major Structural Drawings yet to Receive
| Piling | Stock House DDS | 31.07.2022 |  | 1. Stock House Conveyors and Junction Houses |  |  |  | SFC01 BOQ Recived
|  | Balance IPPL | 15.07.2022 | Not started | 2. IPPL Structrures & Ducting
|  | Stock House Conveyors & Junction Houses | 15.07.2022 | Startted 19072022 | 3. PCI & CPP Incoming conveyor
| RCC | Stock House DDS | 31.07.2022 |  | 4. Weigh Hopper, discharge equipment support structures
|  | Balance IPPL | 15.08.2022
|  | Stock House Conveyors & Junction Houses | 20.07.2022
ETP (Thickner)
|  | TRT inlet and outlet google valves | 30.07.2022

## Sheet6 (hidden)
|  |  |  | Plan | Achieved | Variance | Plan | Plan
Piling | Nos | 8500 | 8040 | 200 | 155 | 45 | 100 | 100 | 7548 | 88.8 | 952
Civil | CuM | 105000 | 76110 | 1553 | 1429 | 124 | 1011 | 1839 | 45955 | 43.7667 | 59045
Structural Fab | MT | 69092 | 47487 | 1064 | 876 | 188 | 781 | 661 | 13746 | 19.8952 | 55346
L&T Scope | MT | 49986 | 40407 | 633 | 601 | 32 | 554 | 924 | 14804 | 29.6163 | 35182
DS Engg Scope | MT | 5240 | 3168 | 203 | 202 | 1 | 113 | 138 | 1985 | 37.8817 | 3255
JSSL Scope | MT | 9566 | 3767 | 228 | 73 | 155 | 114 | 113 | 72 | 0.75267 | 9494
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300
Structural Erec | MT | 69092 | 47487 | 456 | 296 | 160 | 413 | 874 | 6344 | 9.182 | 62748
L&T Scope | MT | 49986 | 40407 | 381 | 278 | 103 | 276 | 651 | 7632 | 15.2683 | 42354
DS Engg Scope | MT | 5240 | 3168 | 0 | 0 | 0 | 100 | 185 | 0 | 0 | 5240
JSSL Scope | MT | 9566 | 3767 | 75 | 18 | 57 | 37 | 38 | 18 | 0.18817 | 9548
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300

## Sheet4 (hidden)
Area | Scope | Drg Receipt | Balance | %
Piling (Nos) | 6500 | 6482 | 18 | 99.7231
RCC (CuM) | 105000 | 48209 | 56791 | 45.9133
Structural (MT) | 61780 | 21581 | 40199 | 34.932
Equipment (MT) | 17955 | 3151 | 14804 | 17.5494
Piping (Inch-mtr) | 469800 | 16000 | 453800 | 3.4057
Refractory (MT) | 34290 | 3470 | 30820 | 10.1196
Area | Scope | Progress | Balance | %
Piling (Nos) | 6500 | 5889 | 611 | 90.6
RCC (CuM) | 105000 | 29149 | 75851 | 27.761
Structural Fab(MT) | 61780 | 7790 | 53990 | 12.6093
Structural Erec(MT) | 61780 | 1487 | 60293 | 2.4069
Equipment (MT) | 17955 | 0 | 17955 | 0
Piping (Inch-mtr) | 469800 | 5000 | 464800 | 1.0643
Refractory (MT) | 34290 | 0 | 34290 | 0

## April Plan'22 (hidden)
PLAN FOR THE MONTH Apr' 2022
Civil
1 | Piling | 400Nos
Sl.No | Area | RCC Qty in CuM
1 | SGP Cooling Tower (East & West) | 60
2 | ECR-1 | 80
3 | ECR-2,4 , 5 & 6 | 200
4 | PCI Building including Mill Foundation | 12
5 | Slag Granulation Plant INBA (East & West ) Dewatering Area | 75
6 | Torpedo Laddle Repair Shop | 150
7 | Recirculation Pump House incl. soft water tank | 350
8 | TRT including foundation | 50
9 | Stove Housing | 125
10 | Main Charging Conveyor | 20
11 | Fines Building | 154
12 | Dry Slag Pit (East & West) | 1064
13 | Cast House Ramp | 70
14 | INBA East Dewatering Tank area fdn. For conveyor structure | 180
15 | WHRS - Ducting outside stove building ( Waste Gas Heat Recovery System) | 250
16 | Blower House (Turbo blower main raft) | 1040
17 | GCP & TB Pump House & TBS ECR Electrical Sub-Station | 70
18 | Interplant Pipeline from GCP to TRT | 80
| Total | 4030
Fabrication & Erection Plan for Mar'22
Building Structure
Sl.No | Area | Fabrication Qty in MT | Erection Qty in MT
1 | Furnace Tower | 505 | 231
2 | Stock House | 24 | 467
4 | CPP | 292.55 | 0
5 | Outsourced str supply | 200 | 0
Total (A) |  | 1021.55 | 698
Technological Structure
Sl.No | Area | Fabrication Qty in MT | Erection Qty in MT
1 | BF Shell | 0 | 154.7
2 | Stove Shell | 200 | 184
3 | Stock House Tech Structure | 175 | 586
4 | Axial Cyclone & GCP | 25 | 10
5 | CPP | 107.45 | 0
Total (B) |  | 507.45 | 934.7
Grand Total (A+B) |  | 1529 | 1632.7

## Civil Day Wise Progress
PILING PROGRESS IN Nos | [9 empty] | 0 | 2022-09-22
SI. No. | Area | Name Of Structure | Scope in Nos | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug-22 | Cumm As on Sep' 22 | Balance qty | % of Execution |  | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | BF Proper | Blast furnace proper (incl 9 test piles) | 707 | 707 | 0 | 707 | 707 | 0 | 100 |  | 100 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Elevator | 20 | 20 | 0 | 20 | 20 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | South Side Stair Case | 4 | 4 | 0 | 0 | 6 | -2 | 150 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 3; 2022-09-13: 0; 2022-09-14: 3; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 6
2 | Cast House | Cast house | 1122 | 1122 | 0 | 1122 | 1122 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Ramp east side | 56 | 56 | 0 | 56 | 56 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Ramp west side | 56 | 56 | 0 | 56 | 56 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | ECR 01 Ramp | 60 | 60 | 0 | 60 | 60 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
3 | Dedusting System | Cast House dedusting duct support | 24 | 24 | 0 | 18 | 19 | 5 | 79.1667 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 1; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 1
|  | Cast House dedusting E&W | 164 | 164 | 0 | 160 | 161 | 3 | 98.1707 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 1; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 1
|  | CH DDS Stack ID Fan & Duct support (E&W) | 80 | 80 | 0 | 77 | 82 | -2 | 102.5 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 4; 2022-09-11: 0; 2022-09-12: 1; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 5
|  | Stock House bag filter house 1 | 64 | 64 | 0 | 42 | 64 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 6; 2022-09-03: 6; 2022-09-04: 0; 2022-09-05: 2; 2022-09-06: 4; 2022-09-07: 4; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 22
|  | Stock House bag filter house 2 | 11 | 11 | 0 | 0 | 0 | 11 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SH DDS 1 & 2 ID Fan & Chimney | 25 | 0 | 25 | 0 | 0 | 25 |  |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 5; 2022-09-15: 3; 2022-09-16: 1; 2022-09-17: 0; 2022-09-18: 0
4 | Slag Pit | East side dry slag pit | 144 | 144 | 0 | 144 | 144 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | West side dry slag pit | 144 | 144 | 0 | 144 | 144 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
5 | Stoves | Stove Proper | 366 | 366 | 0 | 366 | 366 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Waste Gas Chimney | 61 | 61 | 0 | 61 | 61 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Stove Housing | 300 | 300 | 0 | 300 | 300 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | WHRS | 385 | 385 | 0 | 385 | 385 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CA Fan | 16 | 16 | 0 | 16 | 16 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
6 | GCP | Cyclone, | 42 | 42 | 0 | 42 | 42 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Scrubber, Demister | 65 | 65 | 0 | 65 | 65 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Goggle Valve Platform | 29 | 29 | 0 | 29 | 29 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
7 | SGP | SGP inba (e) Condensation tower | 35 | 35 | 0 | 35 | 35 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SGP cooling tower INBA (e) | 110 | 110 | 0 | 110 | 110 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SGP inba (W) Condensation tower | 35 | 35 | 0 | 35 | 35 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SGP cooling tower inba (w) | 110 | 110 | 0 | 110 | 110 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
8 | CPP | CPP Building | 295 | 295 | 0 | 295 | 295 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP Mill Foundation | 40 | 40 | 0 | 40 | 40 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - CA fan & HGG | 16 | 16 | 0 | 16 | 16 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - Booster Station | 8 | 8 | 0 | 8 | 8 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - Nitorgen Vessels | 25 | 25 | 0 | 25 | 25 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - Nitrogen Tank | 8 | 8 | 0 | 8 | 8 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - Booster Fan | 12 | 12 | 0 | 12 | 12 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | CPP - ID Fans | 12 | 12 | 0 | 12 | 12 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
9 | WTP | Overhead water tank | 114 | 114 | 0 | 114 | 114 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | GCP TBS Pump House & TBS ECR Building | 97 | 97 | 0 | 97 | 97 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | GCP Cooling Tower | 61 | 61 | 0 | 61 | 61 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | TB, TRT, PCI & Aircompressor Cooling Tower | 31 | 31 | 0 | 28 | 28 | 3 | 90.3226 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Thickner | 135 | 135 | 0 | 135 | 135 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
10 | Stock House & MCC | Stock house building | 964 | 964 | 0 | 964 | 964 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Fines Building | 115 | 115 | 0 | 115 | 115 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Surge Hopper building | 118 | 118 | 0 | 118 | 118 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Drive House | 44 | 44 | 0 | 44 | 44 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Screening Building | 86 | 86 | 0 | 86 | 86 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Main charging conveyor | 119 | 119 | 0 | 119 | 119 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Stock House Conveyors (SFC01 & CFC) | 130 | 68 | 62 | 17 | 17 | 113 | 13.0769 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
12 | E&I | Main control room ECR - 1 | 239 | 239 | 0 | 239 | 239 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Pump house ECR-2 | 108 | 108 | 0 | 108 | 108 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Main htss & stock house ECR - 3 | 246 | 246 | 0 | 246 | 246 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | GCP ECR-4 | 102 | 102 | 0 | 102 | 102 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SGP East ECR - 5 | 82 | 82 | 0 | 82 | 82 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | SGP West ECR - 6 | 104 | 104 | 0 | 104 | 104 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | RMHS ECR | 111 | 111 | 0 | 111 | 111 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Chiller Plant | 32 | 32 | 0 | 0 | 0 | 32 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
13 | TRT | TRT Proper | 32 | 32 | 0 | 32 | 32 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | TRT Building | 94 | 94 | 0 | 94 | 94 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
14 | Blower House | Blower Proper | 96 | 96 | 0 | 96 | 96 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Blower building | 326 | 326 | 0 | 326 | 326 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Disel Engine Turbo Blower | 6 | 6 | 0 | 0 | 0 | 6 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Suction Filter | 36 | 36 | 0 | 0 | 0 | 36 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
15 | IPPL | Zone1 GVP to TRT | 66 | 66 | 0 | 66 | 66 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Zone2 Pump House to BF Proper | 121 | 121 | 0 | 22 | 22 | 99 | 18.1818 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Zone3 TRT to Flare Stack | 51 | 51 | 0 | 62 | 62 | -11 | 121.5686 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Balance Zones | 70 | 33 | 37 | 0 | 0 | 70 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
16 | Flare Stack | Flare Stack | 66 | 66 | 0 | 66 | 66 | 0 | 100 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
17 | Additional Piles | Additional Piles based on site condition | 25 | 25 | 0 | 25 | 25 |  |  |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | TOTAL | 8678 | 8554 | 124 | 8255 | 8290 | 388 | 95.5289 |  | 100 | 0 | 6 | 6 | 0 | 2 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 2 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
RCC PROGRESS IN CuM | [10 empty] | 2022-09-22
SI. No. | Area | Name Of Structure | Scope in CuM | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug-22 | Cumm As on Sep' 22 | Balance qty | % of Execution |  | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | Furnace | BF Proper Main Foundation & Furnace Tower | 9400 | 9400 | 0 | 9367 | 9367 | 33 | 99.6489 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-19: 0 | 0
|  | Elevator Tower | 80 | 80 | 0 | 75 | 75 | 5 | 93.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 | Cast House | Cast house Foundations | 3515 | 3515 | 0 | 3515 | 3519 | -4 | 100.1138 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [12 empty] | 4
|  | Cast House south side stair case | 17 | 17 | 0 | 17 | 17 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Ramp East side | 254 | 254 | 0 | 225 | 225 | 29 | 88.5827 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Ramp West side | 254 | 254 | 0 | 192 | 192 | 62 | 75.5906 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Control Room Ramp | 254 | 254 | 0 | 0 | 0 | 254 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CH Hydraulic Room North Side | 75 | 75 | 0 | 40 | 40 | 35 | 53.3333 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CH Floor | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Trough Cooling Fan | 80 | 80 | 0 | 0 | 0 | 80 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
3 | Stock House | Stock House Proper | 5078.5 | 5078.5 | 0 | 5078.5 | 5078.5 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Stock House MCC | 418 | 418 | 0 | 417.5 | 443.5 | -25.5 | 106.1005 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 26
|  | Fines Building | 363 | 363 | 0 | 362.5 | 362.5 | 0.5 | 99.8623 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Surge Hopper building | 360 | 360 | 0 | 431 | 437 | -77 | 121.3889 |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 6
|  | Screening Building | 240 | 240 | 0 | 0 | 0 | 240 | 0 |  | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Drive House | 255 | 255 | 0 | 33 | 35 | 220 | 13.7255 |  | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2
|  | Gathering Conveyors | 300 | 0 | 300 | 0 | 0 | 300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Fines Conveyors & Junction Houses | 750 | 0 | 750 | 0 | 0 | 750 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Hydrauic Room | 40 | 0 | 40 | 3 | 3 | 37 | 7.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
4 | Cyclone, GCP & Gas Network | Cyclone, | 391 | 391 | 0 | 391 | 391 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Scrubber & Demister | 490 | 490 | 0 | 374 | 374 | 116 | 76.3265 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Google Valve Platform | 230 | 230 | 0 | 230 | 230 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Dust Conveying System | 50 | 0 | 50 | 0 | 0 | 50 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
5 | Hot Blast Stoves | Stove Proper | 3269.5 | 3269.5 | 0 | 3269.5 | 3269.5 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Stove Housing | 1448 | 1448 | 0 | 1357 | 1357 | 91 | 93.7155 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Waste Gas Chimney | 384 | 384 | 0 | 384 | 384 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Hydraulic & Analyser Room | 50 | 50 | 0 | 40 | 42 | 8 | 84 |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2
|  | WHRS | 1450 | 1450 | 0 | 1215 | 1479 | -29 | 102 |  | 155 | 6 | 0 | 46 | 0 | 0 | 0 | 0 | 40 | 13 | 5 | 0 | 0 | 58 | 24 | 6 | 66 | 0 | 0 | 0 | [12 empty] | 264
|  | CA Fan | 240 | 240 | 0 | 4 | 4 | 236 | 1.6667 |  | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
6 | WTP & Utilities | Overhead water tank | 1779 | 1779 | 0 | 947 | 961 | 818 | 54.0191 |  |  | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 14
|  | Recirculating water Pump House | 3273 | 3273 | 0 | 3230.41 | 3236.41 | 36.59 | 98.8821 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [12 empty] | 6
|  | Soft Water Tank | 1595 | 1595 | 0 | 1656.5 | 1656.5 | -61.5 | 103.8558 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Soft Water Plant | 143 | 143 | 0 | 59 | 83 | 60 | 58.042 |  | 75 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | [12 empty] | 24
|  | GCP, TB & TRT pump house with ECR & GCP Recirculation Pumps | 1422 | 1422 | 0 | 575 | 582 | 840 | 40.9283 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 7
|  | Thickner | 1200 | 1200 | 0 | 29 | 65 | 1135 | 5.4167 |  | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 36
|  | Sludge storage Tank | 102 | 102 | 0 | 0 | 0 | 102 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Flash Mixer | 250 | 0 | 250 | 0 | 0 | 250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | FRP Cooling Tower | 1926 | 1926 | 0 | 1655.5 | 1716.5 | 209.5 | 89.1225 |  | 48 | 3 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | [12 empty] | 61
|  | Pump Foundations + Flooring | 1420 | 1420 | 0 | 30 | 93 | 1327 | 6.5493 |  | 88 | 10 | 2 | 10 | 0 | 0 | 0 | 4 | 9 | 0 | 26 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 63
|  | AVGF | 200 | 200 | 0 | 108 | 108 | 92 | 54 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
7 | SGP | SGP East - Drum & Hot Water Tank | 1755 | 1755 | 0 | 1801.5 | 1801.5 | -46.5 | 102.6496 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SGP West - Drum & Hot Water Tank | 1755 | 1755 | 0 | 2074 | 2113 | -358 | 120.3989 |  | 14 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | [12 empty] | 39
|  | SGP East Cooling Tower | 1958 | 1958 | 0 | 888 | 888 | 1070 | 45.3524 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SGP West Cooling Tower | 1958 | 1958 | 0 | 818 | 818 | 1140 | 41.7773 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SGP East Condensation Tower | 230 | 230 | 0 | 259 | 259 | -29 | 112.6087 |  | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SGP West Condensation Tower | 244 | 244 | 0 | 253 | 253 | -9 | 103.6885 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Dry Slag Pit(east) | 3100 | 3100 | 0 | 2178 | 2373 | 727 | 76.5484 |  | 352 | 0 | 49 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 100 | 0 | 0 | 18 | [12 empty] | 195
|  | Dry Slag Pit(west) | 3100 | 3100 | 0 | 2070 | 2204 | 896 | 71.0968 |  |  | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 42 | 6 | [12 empty] | 134
|  | Conveyor to 1st Tower - East | 900 | 900 | 0 | 852 | 852 | 48 | 94.6667 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Conveyor to 1st Tower - West | 830 | 830 | 0 | 760 | 760 | 70 | 91.5663 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Dry Slap Pit Pump House - East | 295 | 295 | 0 | 146 | 176 | 119 | 59.661 |  | 15 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 30
|  | Dry Slap Pit Pump House - West | 295 | 295 | 0 | 53 | 53 | 242 | 17.9661 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | INBA East Pipe Rack | 380 | 380 | 0 | 90 | 90 | 290 | 23.6842 |  | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | INBA West Pipe Rack | 390 | 390 | 0 | 122 | 168 | 222 | 43.0769 |  |  | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 46
8 | E&I | ECR-1 | 2297 | 2297 | 0 | 1234.5 | 1234.5 | 1062.5 | 53.744 |  | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | ECR-2 | 1294 | 1294 | 0 | 356 | 366 | 928 | 28.2844 |  | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [12 empty] | 10
|  | ECR-3 | 700 | 700 | 0 | 687 | 687 | 13 | 98.1429 |  | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | ECR-4 | 1141 | 1141 | 0 | 759.5 | 768.5 | 372.5 | 67.3532 |  | 170 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 9
|  | ECR-5 | 1025 | 1025 | 0 | 335.5 | 348.5 | 676.5 | 34 |  | 220 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 13
|  | ECR-6 | 330 | 330 | 0 | 335.5 | 335.5 | -5.5 | 101.6667 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | RMHS ECR | 175 | 175 | 0 | 114.5 | 114.5 | 60.5 | 65.4286 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Other Cable bridges connectivity to ECRs & Cable Bridge cast house to SGP | 500 | 0 | 500 | 0 | 0 | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Transformers | 1572 | 1572 | 0 | 0 | 0 | 1572 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Chiller Plant | 350 | 80 | 270 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
9 | TLRS | TLRS Building & TLRS Office & Store | 924 | 924 | 0 | 962 | 962 | -38 | 104.1126 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | TLRS Track Foundation & Floor | 1260 | 1260 | 0 | 605.5 | 605.5 | 654.5 | 48.0556 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
10 | PCI & CPP | CPP Building | 1761 | 1761 | 0 | 1745 | 1745 | 16 | 99.0914 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CPP mill Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | PCI & CPP building Floor Drawing | 480 | 480 | 0 | 0 | 0 | 480 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CPP Booster Fan | 125 | 125 | 0 | 115.5 | 115.5 | 9.5 | 92.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CPP Booster Station | 38 | 38 | 0 | 41 | 41 | -3 | 107.8947 |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | HGG 1 & 2 | 110 | 110 | 0 | 82 | 82 | 28 | 74.5455 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Nitrogen vessels & storage tank | 509 | 509 | 0 | 769 | 769 | -260 | 151.0806 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | ID Fans | 370 | 370 | 0 | 385.5 | 385.5 | -15.5 | 104.1892 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | PCI Injection Vessels Supports | 235 | 235 | 0 | 0 | 0 | 235 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | PCI Lift Pit | 5 | 5 | 0 | 2 | 2 | 3 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 4
|  | MCC Room Slab | 340 | 340 | 0 | 0 | 0 | 340 | 0 |  | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Incoming coal conveying Line | 400 | 0 | 400 | 0 | 0 | 400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | CPP to Distributor Coal conveying Line | 50 | 0 | 50 | 0 | 0 | 50 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
11 | TRT | TRT Proper | 922 | 922 | 0 | 898 | 898 | 24 | 97.397 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | TRT Building | 315 | 315 | 0 | 282 | 282 | 33 | 89.5238 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | TRT Inlet Ducts & Google Valves | 350 | 0 | 350 | 0 | 0 | 350 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | TRT 0mtr Floor | 200 | 200 | 0 | 0 | 0 | 200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
12 | Blower House | Blower Proper | 6000 | 5152 | 848 | 1352 | 1371 | 4629 | 22.85 |  | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 19
|  | Blower Building | 2050 | 950 | 1100 | 1208 | 1253 | 797 | 61.122 |  |  | 0 | 18 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 45
13 | IPPL/ CABLING Bridge (Zone Wise) | From GCP to TRT | 360 | 360 | 0 | 162 | 361 | -1 | 100.2778 |  | 123 | 0 | 24 | 0 | 0 | 0 | 0 | 42 | 24 | 0 | 32 | 0 | 51 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 199
|  | Pump House to BF Proper | 350 | 350 | 0 | 0 | 0 | 350 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Zone3 TRT to Flare Stack | 275 | 275 | 0 | 0 | 0 | 275 | 0 |  | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | IPPL Near TRT Station | 145 | 145 | 0 | 0 | 0 | 145 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Balance Zones | 355 | 0 | 355 | 88 | 88 | 267 | 24.7887 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
14 | Dedusting System | Cast House dedusting duct support | 80 | 80 | 0 | 0 | 0 | 80 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Cast House DDS East | 185 | 185 | 0 | 237 | 345 | -160 | 186.4865 |  | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 108
|  | Cast House DDS West | 185 | 185 | 0 | 0 | 8 | 177 | 4.3243 |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 8
|  | Bag House Building Floor E & W | 190 | 190 | 0 | 13 | 135 | 55 | 71.0526 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 83 | 0 | 0 | 0 | 0 | [12 empty] | 122
|  | STACK LAYOUT + Duct Support | 300 | 300 | 0 | 0 | 0 | 300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | ID FAN FOUNDATION | 880 | 880 | 0 | 0 | 0 | 880 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SH DE SYSTEM INC. STACK DES - 1 | 200 | 200 | 0 | 0 | 0 | 200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | SH DE SYSTEM INC. STACK DES - 2 | 45 | 45 | 0 | 0 | 0 | 45 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | STACK LAYOUT | 750 | 0 | 750 | 0 | 0 | 750 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | ID FAN FOUNDATION | 600 | 0 | 600 | 0 | 0 | 600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Duct Support | 100 | 0 | 100 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
15 | Flare Stack | Flare Stack | 545 | 545 | 0 | 504 | 512 | 33 | 93.945 |  | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 8
16 | Hydraulics | Oil filling station GCP | 49 | 49 | 0 | 42 | 42 | 7 | 85.7143 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
17 | Air Compressor | Building | 135 | 135 | 0 | 0 | 0 | 135 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
18 | Others | Main Project Office | 200 | 200 | 0 | 38 | 148 | 52 | 74 |  | 71 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 110
| L&T |  | 93193 | 86480 | 6713 | 61029.91 | 62639.91 | 30553.09 | 67.2153 | 0 | 3630 | 90 | 136 | 90 | 37 | 114 | 37 | 205 | 100 | 34 | 78 | 3 | 61 | 86 | 113 | 132 | 166 | 0 | 42 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614
19 | BMCPL | ECR3 Grid AE/1-14 | 1855 | 1855 | 0 | 52 | 120 | 1735 | 6.469 |  | 490 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 3 | 0 | 0 | 18 | 2 | 7 | 0 | 0 | 0 | 20 | [12 empty] | 68
|  | Transformer Grid A-E/3-14 | 165 | 165 | 0 | 24 | 24 | 141 | 14.5455 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | RMHS ECR | 410 | 410 | 0 | 5 | 5 | 405 | 1.2195 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | RMHS Transformer | 75 | 75 | 0 | 0 | 0 | 75 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Canteen | 275 | 275 | 0 | 5 | 25 | 250 | 9.0909 |  | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 20
|  | Substation | 25 | 25 | 0 | 0 | 0 | 25 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| BMCPL |  | 2805 | 2805 | 0 | 86 | 174 | 2631 | 6.2032 | 0 | 555 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 9 | 3 | 0 | 5 | 18 | 12 | 7 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
20 | Fortune | GCP Cooling Tower | 800 | 800 | 0 | 52 | 144 | 656 | 18 |  | 80 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 30 | 0 | 0 | 12 | 12 | 6 | 0 | 0 | 5 | 20 | [12 empty] | 92
|  | TRT Cooling Tower | 500 | 500 | 0 | 15 | 21 | 479 | 4.2 |  | 50 | 0 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 6
| FORTUNE |  | 1300 | 1300 | 0 | 67 | 165 | 1135 | 12.6923 |  | 130 | 0 | 4 | 0 | 0 | 2 | 7 | 0 | 0 | 0 | 30 | 0 | 0 | 12 | 12 | 6 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
21 | Shwetha Const | ECR - 6 | 1875 | 1875 | 0 | 54 | 62.4 | 1812.6 | 3.328 |  | 200 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 3.4; 2022-09-05: 5; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 8.4
|  | TOTAL | 99173 | 92460 | 6713 | 61236.91 | 63041.31 | 36131.69 | 63.567 |  | 4515 | 90 | 140 | 90 | 40.4 | 121 | 58 | 205 | 100 | 43 | 111 | 3 | 66 | 116 | 137 | 145 | 166 | 0 | 47 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1808.4
| BF#6 & HSM3 | Interface & retaining wall | 8100 | 8100 | 0 | 0 | 0 | 8100 | 0 |  |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0 | 0
4515
5590
RCC
[7 empty] | ecr4 | 26
[7 empty] | 2 | 7
[7 empty] | DSP sump west | 53
[7 empty] | whrs | 16
[7 empty] | DSP sump east | 12
[7 empty] | blower house | 7
[7 empty] | PCC | 0
Fab
[7 empty] | Uptabke | 6
[7 empty] | WGM | 5
[7 empty] | SGP tech | 3
BLD
[7 empty] | Furnace tower | 6.79
[7 empty] | ch | 25
[7 empty] | sh | 10
[7 empty] | mcc | 11
Erec
[7 empty] | Stove nozzle | 3
[7 empty] | CH | 12
[7 empty] | Staves | 13.8

## Strl Fab Day Wise Progress
BUILDING STRUCTURE FABRICATION PROGRESS IN MT | [11 empty] | 2022-09-22
SI. No. | Agency | Name Of Structure | Est. Scope | Scope in MT | BOQ Received | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug'22 | Cumm As on Sep'22 | Balance qty | % of Execution | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | L&T | Furnace Tower
|  | Lower Tower | 3000 | 884 | 884 | 884.05 | -0.05 | 883.7 | 899.6 | -15.6 | 101.7647 | 256 | 0 | 0 | 0 | 0 | 0 | 7.25 | 6.25 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 15.9
|  | Middle Tower |  | 1725.54 | 1725.54 | 1725.54 | 0 | 1726 | 1729 | -3.46 | 100.2005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 3
|  | Upper Tower |  | 842 | 842 | 842 | 0 | 509.9 | 515.8 | 326.2 | 61.2589 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9 | [12 empty] | 5.9
|  | Fixed & Movable Platform |  | 89 | 89 | 89 | 0 | 37 | 37 | 52 | 41.573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 |  | Tuyere Platform |  | 449.6 | 449.6 | 449.6 | 0 | 130 | 185 | 264.6 | 41.1477 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 55
3 |  | Elevator Tower | 200 | 200 | 200 | 200 | 0 | 9 | 9 | 191 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
4 |  | Cast House | 5000 | 8014 | 8014 | 8014 | 0 | 2118.98 | 2376.32 | 5637.68 | 29.6521 | 810 | 0 | 0 | 0 | 0 | 2 | 0 | 13.34 | 6 | 0 | 0 | 0 | 17 | 41 | 0 | 133 | 0 | 0 | 0 | 45 | [12 empty] | 257.34
|  | Road ramp to Cast House | 300 | 338 | 338 | 338 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
5 |  | Stove Housing | 1750 | 3734 | 3734 | 3634 | 100 | 1438 | 1887.99 | 1846.01 | 50.5621 | 500 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 149.39 | 61 | 0 | 0 | 31.6 | 0 | 51 | 0 | 0 | 0 | 0 | [12 empty] | 449.99
|  | WGM Chimney |  | 20.41 | 20.41 | 20.41 | 0 | 0 | 0 | 20.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
6 |  | WHRS structures |  | 958 | 958 | 958 | 0 | 131.38 | 131.38 | 826.62 | 13.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
7 |  | Stock house proper | 9600 | 5232 | 5082 | 5082 | 150 | 4742 | 4801.5 | 430.5 | 91.7718 | 150 | 0 | 0 | 0 | 0 | 0 | 0.6 | 41 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 1.6 | 0 | 0 | 0 | 4.3 | [12 empty] | 59.5
|  | Fines building |  | 1315 | 1315 | 1315 | 0 | 127 | 193 | 1122 | 14.6768 | 160 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 16 | 5 | 0 | 15 | 0 | 0 | 0 | 10 | [12 empty] | 66
|  | MCC Conveyor |  | 1120 | 1120 | 1120 | 0 | 625 | 687 | 433 | 61.3393 | 150 | 35 | 0 | 0 | 0 | 12 | 0 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | [12 empty] | 62
|  | Drive house |  | 145 | 145 | 145 | 0 | 5 | 5 | 140 | 3.4483 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Surge hopper station |  | 632 | 632 | 259 | 373 | 260 | 260 | 372 | 41.1392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Screening building |  | 1514 | 1514 | 1514 | 0 | 90 | 134 | 1380 | 8.8507 | 80 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | [12 empty] | 44
|  | Conveyors trestles and Galleries |  | 1500 | 726 | 356 | 1144 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
8 |  | Cyclone Structure | 600 | 643 | 643 | 643.35 | -0.35 | 478.8 | 480.8 | 162.2 | 74.7745 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [12 empty] | 2
9 |  | Scrubber Structures | 400 | 152.14 | 152.14 | 152.14 | 0 | 0 | 0 | 152.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
11 |  | Flare Stack Structures | 100 | 396 | 396 | 396.1 | -0.1 | 36 | 66 | 330 | 16.6667 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 30
12 |  | Crude Gas Main Structure & Clean Gas Main | 250 | 258.361 | 258.361 | 258.361 | 0 | 0 | 0 | 258.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
14 |  | SGP Structures ( East & West) | 1000 | 721 | 721 | 721 | 0 | 0 | 0 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
16 |  | CH DDS | 500 | 309.4 | 309.4 | 309.4 | 0 | 0 | 0 | 309.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
17 |  | SH DDS | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
18 |  | WTP - OHT | 0 | 34 | 34 | 34 | 0 | 28 | 28 | 6 | 82.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
19 |  | IPPL | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total (A) | 22880 | 31531.451 | 30482.451 | 29639.951 | 1891.5 | 13375.76 | 14426.39 | 17105.061 | 45.7524 | 2316 | 35 | 0 | 0 | 180 | 14 | 17.85 | 60.59 | 21.4 | 212.39 | 78 | 0 | 35 | 102.6 | 0 | 228.6 | 0 | 0 | 0 | 65.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050.63
1 | DS Engg | CPP/PCI Building | 3000 | 4290 | 3122 | 3122 | 1168 | 2548.788 | 2637.788 | 1652.212 | 61.4869 | 0 | 2022-09-01: 0; 2022-09-02: 2; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 2; 2022-09-07: 5; 2022-09-08: 3; 2022-09-09: 8; 2022-09-10: 5; 2022-09-11: 0; 2022-09-12: 3; 2022-09-13: 5; 2022-09-14: 8; 2022-09-15: 0; 2022-09-16: 8; 2022-09-17: 0; 2022-09-18: 40 | 89
|  | Total (B) | 3000 | 4290 | 3122 | 3122 | 1168 | 2548.788 | 2637.788 | 1652.212 | 61.4869 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 5 | 3 | 8 | 5 | 0 | 3 | 5 | 8 | 0 | 8 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89
1 | JSSL | IPPL | 800 | 800 | 407 | 407 | 393 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 |  | BF Circulating water and Firefighting pump house | 750 | 770 | 770 | 770 | 0 | 774.77 | 774.77 | -4.77 | 100.6195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
4 |  | Pipe bridge from BF pump house to furnace tower | 250 | 252 | 252 | 252 | 0 | 0 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
5 |  | Blower Building | 2600 | 1400 | 1400 | 1400 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
6 |  | Compressor Building | 350 | 115.26 | 115.26 | 115.26 | 0 | 0 | 0 | 115.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
7 |  | TRT Building | 500 | 583 | 583 | 583 | 0 | 321.01 | 493.76 | 89.24 | 84.693 | 150 | 0 | 48.23 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 15.47 | 0 | 48.89 | 16.79 | 0 | 0 | 26.87 | 0 | 0 | 0 | [12 empty] | 172.75
9 |  | Cable Bridges | 1000 | 1703 | 103 | 103 | 1600 | 0 | 0 | 1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
10 |  | TLRS Building | 700 | 1122 | 1122 | 1122 | 0 | 1160.74 | 1160.74 | -38.74 | 103.4528 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Total (C) | 6950 | 6745.26 | 4752.26 | 4752.26 | 1993 | 2256.52 | 2429.27 | 4315.99 | 36.0145 | 650 | 0 | 48.23 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 15.47 | 0 | 48.89 | 16.79 | 0 | 0 | 26.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.75
1 | SAI BALAJI | Cast House Dedusting | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 | SASEC | Stock House Dedusting | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Total(D) | 0 | 500 | 200 | 200 | 300 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL (A+B+C+D) | 32830 | 43066.711 | 38556.711 | 37714.211 | 5352.5 | 18181.068 | 19493.448 | 23573.263 | 45.2634 | 2966 | 35 | 50.23 | 0 | 196.5 | 14 | 19.85 | 65.59 | 24.4 | 220.39 | 98.47 | 0 | 86.89 | 124.39 | 8 | 228.6 | 34.87 | 0 | 40 | 65.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.38
TECHNOLOGICAL STRUCTURE FABRICATION PROGRESS IN MT | [11 empty] | 2022-09-22
SI. No. |  | Name Of Structure | Est. Scope | Scope in MT | BOQ Received | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug'22 | Cumm As on Sep'22 | Balance qty | % of Execution | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | L&T | BF Shell Plates (ASTM 516 GR 70) | 1500 | 1347 | 1347 | 1347 | 0 | 1347 | 1347 | 0 | 100 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
2 |  | Bustle Main(ASTM 516 GR 70) | 200 | 199 | 199 | 199 | 0 | 114 | 114 | 85 | 57.2864 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
3 |  | Top Gas Piping(UTDC) | 400 | 411 | 410.6 | 410.6 | 0.4 | 304.65 | 308.65 | 101.95 | 75.1705 | 25 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 4; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 4
4 |  | Cast house Runners & Runner Cover |  | 1558.7 | 1558.7 | 1558.7 | 0 | 0 | 0 | 1558.7 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Trough Cooling fan Duct |  | 60 | 60 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
5 |  | Stove Shell (16Mo3/WELACC) | 2600 | 2003 | 2003 | 2003 | 0 | 1761.54 | 1761.54 | 241.46 | 87.9451 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
6 |  | Hot Blast Main (ASTM 516 GR 70) | 300 | 317 | 317 | 317 | 0 | 191 | 191 | 126 | 0 | 18 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
7 |  | Combustion Gas Main in HB Stoves | 610 | 202 | 202.33 | 202.33 | -0.33 | 56.5 | 56.5 | 145.83 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
8 |  | Combustion Air Main in HB Stove |  | 183 | 183 | 183 | 0 | 0 | 0 | 183 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
9 |  | BF GAS MAIN (STOVES) Mixing chamber |  | 22.27 | 22 | 22.27 | 0 | 0 | 0 | 22.27 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
10 |  | Waste Gas Chimney | 200 | 275 | 275 | 275 | 0 | 216.34 | 226.34 | 48.66 | 0 | 33 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 10; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 10
11 |  | Waste Gas Main | 250 | 433 | 432.57 | 432.57 | 0.43 | 70 | 146.1 | 286.47 | 0 | 90 | 1 | 3 | 0 | 4 | 2 | 0 | 8.1 | 5 | 7 | 5 | 0 | 12 | 8 | 0 | 0 | 10 | 0 | 0 | 11 | [12 empty] | 76.1
12 |  | Cold Blast Main (ASTM 516 GR 70) | 90 | 102.5 | 102.5 | 102.5 | 0 | 0 | 0 | 102.5 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
13 |  | Backdraft Chimney | 60 | 18 | 18.3 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
15 |  | Material handling System | 6200 | 5170 | 5170 | 5170 | 0 | 4877 | 4895 | 275 | 94.6809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [12 empty] | 18
16 |  | Fines Building |  | 1053 | 1053 | 1053 | 0 | 996 | 1022 | 31 | 97.056 | 83 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 6; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 20; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 26
17 |  | MS Technological structures (weigh hoppers, discharge chutes, including sail hard liner installation etc.) |  | 3000 | 800 | 800 | 2200 | 0 | 0 | 800 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
18 |  | Cyclone Shell (ASTM 516 GR 70) | 400 | 280 | 280 | 280 | 0 | 166.98 | 166.98 | 113.02 | 59.6357 | 14 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
19 |  | GCP Scrubber, Demister & Quick dump tank | 500 | 265 | 265 | 265 | 0 | 269 | 269 | -4 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
20 |  | Crude Gas Main | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
21 |  | Semi Clean Gas Line | 80 | 38 | 38 | 38 | 0 | 0 | 0 | 38 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
22 |  | Clean Gas Main Duct | 300 | 221.86 | 221.86 | 222 | -0.14 | 0 | 0 | 222 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
23 |  | Flare Stack | 150 | 195 | 195 | 195 | 0 | 0 | 0 | 195 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
24 |  | SGP (E&W)Condensating Tower, Buffer tank,etc | 400 | 291 | 290.74 | 290.74 | 0.26 | 38 | 48.4 | 242.34 | 16.6472 | 63 | 0 | 0 | 0 | 0 | 0 | 3 | 1.4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [12 empty] | 10.4
26 |  | CH DDS | 800 | 1702.88 | 1702.88 | 1702.88 | 0 | 0 | 0 | 1702.88 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
27 |  | SH DDS | 0 | 675 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Total (E) | 15140 | 20123.21 | 17247.48 | 17247.59 | 2875.62 | 10408.01 | 10552.51 | 9570.7 | 52.4395 | 326 | 1 | 3 | 0 | 4 | 2 | 3 | 9.5 | 15 | 7 | 23 | 0 | 12 | 8 | 10 | 20 | 10 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5
29 | DS Engg | PCI & CPP Technological Structures | 1000 | 1000 | 1000 | 811 | 189 | 339 | 367 | 444 | 45.2528 | 260 | 3 | 2 | 3 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | [12 empty] | 28
|  | Total (F) | 1000 | 1000 | 1000 | 811 | 189 | 339 | 367 | 633 | 36.7 | 260 | 3 | 2 | 3 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
22 | VREW | BF Gas IPPL | 550 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 |  | Cold blast IPPL(ASTM 516 GR 70) | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total (G) | 750 | 800 | 0 | 0 | 800 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | SAI BALAJI | Cast House dedusting Duct Work | 0 | 472.918 | 472.918 | 472.918 | 0 | 116 | 151 | 321.918 | 0 | 50 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | [11 empty] | 0 | 35
28 | SASEC | Stock House Dedusting Duct work | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0
|  | Total(H) | 0 | 1122.918 | 472.918 | 472.918 | 650 | 116 | 151 | 971.918 | 13.4471 | 50 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
|  | TOTAL (E+F+G+H) | 16890 | 23046.128 | 18720.398 | 18531.508 | 4514.62 | 10863.01 | 11070.51 | 11975.618 | 48.0363 | 636 | 4 | 5 | 3 | 4 | 11 | 5 | 9.5 | 15 | 7 | 23 | 0 | 12 | 8 | 10 | 20 | 14 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207.5
|  | Grand Total | 49720 | 66112.839 | 57277.109 | 56245.719 | 9867.12 | 29044.078 | 30563.958 | 35548.881 | 46.23 | 3602 | 39 | 55.23 | 3 | 200.5 | 25 | 24.85 | 75.09 | 39.4 | 227.39 | 121.47 | 0 | 98.89 | 132.39 | 18 | 248.6 | 48.87 | 0 | 40 | 122.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.88

## Strl Erec Day Wise
BUILDING STRUCTURE ERECTION PROGRESS IN MT | [11 empty] | 2022-09-22
SI. No. | Agency | Name Of Structure | Est. Scope | Scope in MT | BOQ Received | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug-22 | Cumm As on Sep-22 | Balance qty | % of Execution | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | L&T | Furnace Tower
|  | Lower Tower | 3000 | 884 | 884 | 884.05 | -0.05 | 768 | 774.5 | 109.55 | 87.6082 | 160 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 6.5
|  | Middle Tower |  | 1725.54 | 1725.54 | 1725.54 | 0 | 856.9 | 890.9 | 834.64 | 51.6302 |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 5; 2022-09-11: 0; 2022-09-12: 5; 2022-09-13: 10; 2022-09-14: 8; 2022-09-15: 6; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 34
|  | Upper Tower |  | 842 | 842 | 842 | 0 | 0 | 0 | 842 | 0 |  | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Fixed & Movable Platform |  | 89 | 89 | 89 | 0 | 0 | 0 | 89 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
2 |  | Tuyere Platform |  | 449.6 | 449.6 | 449.6 | 0 | 0 | 0 | 449.6 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
3 |  | Elevator Tower | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0 |  |  | 407.9
4 |  | Cast House | 5000 | 8014 | 8014 | 8014 | 0 | 607.5 | 845.5 | 7168.5 | 0 | 500 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 45 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 4 | 0 | [12 empty] | 238
|  | Road ramp to Cast House | 300 | 338 | 338 | 338 | 0 | 0 | 0 | 338 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
5 |  | Stove Housing | 1750 | 3734 | 3734 | 3634 | 100 | 302.4 | 347.7 | 3286.3 | 0 | 240 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 14; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 8.6; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 6.4; 2022-09-16: 5; 2022-09-17: 0; 2022-09-18: 4; 2022-09-19: 7.3 | 45.3
|  | WGM Chimney |  | 20.41 | 20.41 | 20.41 | 0 | 0 | 1.3 | 19.11 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 1.3 | 1.3
6 |  | WHRS structures |  | 958 | 958 | 958 | 0 | 0 | 0 | 958 | 0 | 21 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
7 |  | Stock house proper | 9600 | 5232 | 5082 | 5082 | 150 | 2661.2 | 2738.5 | 2343.5 | 53.8863 | 120 | 0 | 4 | 0 | 2 | 0 | 3.5 | 0 | 2.5 | 1 | 14 | 0 | 6 | 6 | 8 | 9.8 | 4 | 0 | 8 | 8.5 | [12 empty] | 77.3
|  | Fines building |  | 1315 | 1315 | 1315 | 0 | 0 | 0 | 1315 | 0 | 108 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | MCC Conveyor |  | 1120 | 1120 | 1120 | 0 | 0 | 0 | 1120 | 0 | 40 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Drive house |  | 145 | 145 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Surge hopper station |  | 632 | 632 | 259 | 373 | 82.5 | 93 | 166 | 35.9073 | 42 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 1; 2022-09-06: 0; 2022-09-07: 3; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 6.5 | 10.5
|  | Screening building |  | 1514 | 1514 | 1514 | 0 | 0 | 0 | 1514 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
|  | Conveyors trestles and Galleries |  | 1500 | 726 | 356 | 1144 | 0 | 0 | 356 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
8 |  | Cyclone Structure | 600 | 643 | 643 | 643.35 | -0.35 | 253.1 | 266.8 | 376.55 | 41.4704 | 88 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 2.5 | [12 empty] | 13.7
9 |  | Scrubber Structures | 400 | 152.14 | 152.14 | 152.14 | 0 | 0 | 0 | 152.14 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
11 |  | Flare Stack Structures | 100 | 396 | 396 | 396.1 | -0.1 | 0 | 0 | 396.1 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
12 |  | Crude Gas Main Structure& Clean Gas Main | 250 | 258.361 | 258.361 | 258.361 | 0 | 0 | 0 | 258.361 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
14 |  | SGP Structures ( East & West) | 1000 | 721 | 721 | 721 | 0 | 0 | 0 | 721 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
16 |  | CH DDS | 500 | 309.4 | 309.4 | 309.4 | 0 | 0 | 0 | 309.4 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
17 |  | SH DDS | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
18 |  | WTP - OHT | 0 | 34 | 34 | 34 | 0 | 0 | 0 | 34 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0 | 0
19 |  | IPPL | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0; 2022-09-19: 0
|  | Total (A) | 22880 | 31531.451 | 30482.451 | 29639.951 | 1891.5 | 5531.6 | 5958.2 | 25573.251 | 18.8961 | 1319 | 0 | 4 | 0 | 50 | 16 | 7 | 4 | 60.1 | 8 | 66 | 0 | 11 | 16 | 16 | 24.4 | 102 | 0 | 16 | 26.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.6
1 | DS Engg | CPP/PCI Building | 3000 | 4290 | 3122 | 3122 | 1168 | 882 | 939 | 3351 | 30.0769 | 86.67 | 4 | 4 | 0 | 2 | 3 | 4 | 3 | 3 | 3 | 5 | 0 | 3 | 3 | 4 | 3 | 3 | 0 | 5 | 5 | [12 empty] | 57
|  | Total (B) | 3000 | 4290 | 3122 | 3122 | 1168 | 882 | 939 | 3351 | 21.8881 | 86.67 | 4 | 4 | 0 | 2 | 3 | 4 | 3 | 3 | 3 | 5 | 0 | 3 | 3 | 4 | 3 | 3 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
1 | JSSL | IPPL | 800 | 800 | 407 | 407 | 393 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 |  | BF Circulating water and Firefighting pump house | 750 | 770 | 770 | 770 | 0 | 735.3 | 737.42 | 32.58 | 95.7688 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.12 | [12 empty] | 2.12 | 734.85 | -2.57
4 |  | Pipe bridge from BF pump house to furnace tower | 250 | 252 | 252 | 252 | 0 | 0 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
5 |  | Blower Building | 2600 | 1400 | 1400 | 1400 | 0 | 0 | 12.12 | 1387.88 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.12 | [12 empty] | 12.12
6 |  | Compressor Building | 350 | 115.26 | 115.26 | 115.26 | 0 | 0 | 0 | 115.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
7 |  | TRT Building | 500 | 583 | 583 | 583 | 0 | 145.04 | 362.96 | 220.04 | 0 | 160 | 12.23 | 14.12 | 0 | 24.27 | 20.12 | 10.17 | 21.12 | 14.15 | 13.29 | 7.67 | 0 | 14.4 | 12.54 | 13.85 | 12.59 | 14.07 | 0 | 0 | 13.33 | [12 empty] | 217.92 | 145.07
9 |  | Cable Bridges | 1000 | 1703 | 103 | 103 | 1600 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
10 |  | TLRS Building | 700 | 1122 | 1122 | 1122 | 0 | 742.9 | 793.78 | 328.22 | 0 | 100 | 6.45 | 3.12 | 0 | 0 | 6.17 | 7.92 | 3.14 | 7.7 | 8 | 5.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.14 | [12 empty] | 50.88 | 743.42
|  | Total (C) | 6950 | 6745.26 | 4752.26 | 4752.26 | 1993 | 1623.24 | 1906.28 | 4838.98 | 28.261 | 550 | 18.68 | 17.24 | 0 | 24.27 | 26.29 | 18.09 | 24.26 | 21.85 | 21.29 | 12.91 | 0 | 14.4 | 12.54 | 13.85 | 12.59 | 14.07 | 0 | 0 | 30.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.04
1 | SAI BALAJI | Cast House Dedusting | 0 | 1500 | 200 | 200 | 1300 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
2 | SASEC | Stock House Dedusting | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | Total(D) | 0 | 3000 | 200 | 200 | 2800 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL (A+B+C+D) | 32830 | 45566.711 | 38556.711 | 37714.211 | 7852.5 | 8036.84 | 8803.48 | 36763.231 | 19.32 | 1955.67 | 22.68 | 25.24 | 0 | 76.27 | 45.29 | 29.09 | 31.26 | 84.95 | 32.29 | 83.91 | 0 | 28.4 | 31.54 | 33.85 | 39.99 | 119.07 | 0 | 21 | 61.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766.64
TECHNOLOGICAL STRUCTURE ERECTION PROGRESS IN MT | [11 empty] | 2022-08-22
SI. No. |  | Name Of Structure | Est. Scope | Est Scope in MT | BOQ Received | Drawings receipt as on date | Balance drawings yet to be recive | Up to Aug-22 | Cumm As on Sep-22 | Balance qty | % of Execution | TOTAL PLAN | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | TOTAL ACHIEVED
1 | L&T | BF Shell Plates (ASTM 516 GR 70) | 1500 | 1347 | 1347 | 1347 | 0 | 1347 | 1347 | 0 | 100 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
2 |  | Bustle Main(ASTM 516 GR 70) | 200 | 199 | 199 | 199 | 0 | 126 | 126 | 73 | 63.3166 | 15 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
3 |  | Top Gas Piping(UTDC) | 400 | 411 | 410.6 | 410.6 | 0.4 | 0 | 0 | 411 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
4 |  | Cast house Runners & Runner Cover |  | 1558.7 | 1558.7 | 1558.7 | 0 | 0 | 0 | 1558.7 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Trough Cooling fan Duct |  | 60 | 60 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
5 |  | Stove Shell (16Mo3/WELACC) | 2600 | 1995 | 1995 | 1995 | 0 | 1451.7 | 1488.7 | 506.3 | 74.6216 | 112 | 2022-09-01: 27; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 2; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 8; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 37
6 |  | Hot Blast Main (ASTM 516 GR 70) | 300 | 317 | 317 | 317 | 0 | 0 | 0 | 317 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
7 |  | Combustion Gas Main in HB Stoves | 610 | 202 | 202.33 | 202.33 | -0.33 | 0 | 0 | 202 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
8 |  | Combustion Air Main in HB Stove |  | 183 | 183 | 183 | 0 | 0 | 0 | 183 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
9 |  | BF GAS MAIN (STOVES) Mixing chamber |  | 22.27 | 22 | 22.27 | 0 | 0 | 0 | 22.27 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
10 |  | Waste Gas Chimney | 200 | 275 | 275 | 275 | 0 | 145.7 | 145.7 | 129.3 | 52.9818 | 32 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
11 |  | Waste Gas Main | 250 | 433 | 432.57 | 432.57 | 0.43 | 0 | 0 | 433 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
12 |  | Cold Blast Main (ASTM 516 GR 70) | 90 | 102.5 | 102.5 | 102.5 | 0 | 0 | 0 | 102.5 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
13 |  | Backdraft Chimney | 60 | 18 | 18.3 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
15 |  | Material handling System | 6200 | 5170 | 5170 | 5170 | 0 | 3829.5 | 3919.5 | 1250.5 | 75.8124 | 370 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 90; 2022-09-17: 0; 2022-09-18: 0 | 90
16 |  | Fines Building |  | 1053 | 1053 | 1053 | 0 | 0 | 0 | 1053 | 0 | 50 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
17 |  | MS Technological structures (weigh hoppers, discharge chutes, including sail hard liner installation etc.) |  | 3000 | 283 | 283 | 2717 | 0 | 0 | 3000 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
18 |  | Cyclone Shell (ASTM 516 GR 70) | 400 | 280 | 280 | 280 | 0 | 62 | 62 | 218 | 22.1429 | 55 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
19 |  | GCP Scrubber, Demister & Quick dump tank | 500 | 265 | 265 | 265 | 0 | 157.4 | 157.4 | 107.6 | 59.3962 | 18 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
20 |  | Crude Gas Main | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
21 |  | Semi Clean Gas Line | 80 | 38 | 38 | 38 | 0 | 0 | 0 | 38 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
22 |  | Clean Gas Main Duct | 300 | 221.86 | 221.86 | 222 | -0.14 | 0 | 0 | 221.86 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
23 |  | Flare Stack | 150 | 195 | 195 | 195 | 0 | 0 | 0 | 195 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
24 |  | SGP (E&W)Condensating Tower, Buffer tank,etc | 400 | 291 | 290.74 | 290.74 | 0.26 | 0 | 0 | 291 | 0 | 22 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
26 |  | CH DDS | 800 | 1702.88 | 1702.88 | 1702.88 | 0 | 0 | 0 | 1702.88 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
27 |  | SH DDS | 0 | 675 | 0 | 0 | 675 | 0 | 0 | 675 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Total (E) | 15140 | 20115.21 | 16722.48 | 16722.59 | 3392.62 | 7119.3 | 7246.3 | 12868.91 | 36.024 | 674 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127
29 | DS Engg | PCI & CPP Technological Structures | 1000 | 1000 | 1000 | 811 | 189 | 0 | 0 | 1000 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0 | 0
|  | Total (F) | 1000 | 1000 | 1000 | 811 | 189 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | VREW | BF Gas IPPL | 550 | 600 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
26 |  | Cold blast IPPL(ASTM 516 GR 70) | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Total (G) | 750 | 800 | 0 | 0 | 800 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | SAI BALAJI | Cast House dedusting Duct Work | 0 | 472.918 | 472.918 | 472.918 | 0 | 0 | 0 | 472.918 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
28 | SASEC | Stock House Dedusting Duct work | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 2022-09-01: 0; 2022-09-02: 0; 2022-09-03: 0; 2022-09-04: 0; 2022-09-05: 0; 2022-09-06: 0; 2022-09-07: 0; 2022-09-08: 0; 2022-09-09: 0; 2022-09-10: 0; 2022-09-11: 0; 2022-09-12: 0; 2022-09-13: 0; 2022-09-14: 0; 2022-09-15: 0; 2022-09-16: 0; 2022-09-17: 0; 2022-09-18: 0 | 0
|  | Total(H) | 0 | 1122.918 | 472.918 | 472.918 | 650 | 0 | 0 | 1122.918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL (E+F+G+H) | 16890 | 23038.128 | 18195.398 | 18006.508 | 5031.62 | 7119.3 | 7246.3 | 15791.828 | 31.4535 | 674 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127
|  | Grand Total | 49720 | 68604.839 | 56752.109 | 55720.719 | 12884.12 | 15156.14 | 16049.78 | 52555.059 | 23.3945 | 2629.67 | 49.68 | 25.24 | 0 | 76.27 | 45.29 | 29.09 | 33.26 | 84.95 | 32.29 | 91.91 | 0 | 28.4 | 31.54 | 33.85 | 39.99 | 209.07 | 0 | 21 | 61.81 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893.64
35.46

## EQUIPMENT
Project Name - EQUIPMENT BREAKUP
Name of Structure | Est. Scope | Drgs received | Drawing Balance Qty | Eqpt Receipt up to Aug'22 | Equipment Receipt Sep'22 |  | Cumm Eqpt Receipt | Execution Up to Aug-22 | Equipment Erection Sep'22 |  | Execution Cumm As on Sep-22 | Execution Balance qty | % of Execution
[5 empty] | Plan | Actual |  |  | Plan | Actual
Blast Furnace & BLT | 3016 | 3016 | 0 | 1465.662 | 563.75 | 504.63 | 1970.292 | 170 | 140 | 127.9 | 297.9 | 2846 | 9.8773
Cast House & Ramps | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 570 | 0
Hot Blast Stoves | 2328 | 1970 | 358 | 387.1 | 743 | 467 | 854.1 | 0 |  |  | 0 | 2328 | 0 | -0.3
Stock House | 3000 | 1825 | 1175 | 140 | 200 | 40 | 180 | 0 |  |  | 0 | 3000 | 0
Slag Granulation Plant | 550 | 550 | 0 | 164.953 | 127 | 70.05 | 235.003 | 8.5 | 67 | 20.2 | 28.7 | 541.5 | 5.2182
Cranes & Hoists | 506 | 506 | 0 | 156.72 | 0 | 0 | 156.72 | 0 |  |  | 0 | 506 | 0
Cyclone, GCP & Gas Network | 506 | 68 | 438 | 42.82 | 152.54 | 36.825 | 79.645 | 0 |  |  | 0 | 506 | 0
Blower House & Compressor House | 928 | 928 | 0 | 4 | 0 | 0 | 4 | 0 |  |  | 0 | 928 | 0
TRT | 475 | 475 | 0 | 0 | 300 | 283 | 283 | 0 |  |  | 0 | 475 | 0
PCI & CPP | 1800 | 849.4 | 950.6 | 398.8 | 181 | 106 | 504.8 | 72 | 99.5 | 52 | 124 | 1728 | 6.8889
WTP & Utility | 715 | 500 | 215 | 223.3 | 40 | 40 | 263.3 | 2 | 10 | 10 | 12 | 713 | 1.6783
De-dusting Systems (CH) | 350 | 172.2 | 177.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 350 | 0
TLRS Building (Torpedo ladle & Burners) | 2280 | 2100 | 180 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2280 | 0
Hydraulics Equipment | 78.5 | 66.04 | 12.46 | 0 | 55.8 | 1 | 1 | 0 |  |  | 0 | 78.5 | 0
De-Dusting System (SH) | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total | 17402.5 | 13595.64 | 3806.86 | 2983.355 | 2363.09 | 1548.505 | 4531.86 | 252.5 | 316.5 | 210.1 | 462.6 | 16850 | 2.6582

## PIPING
PIPING ERECTION PROGRESS IN MT
SI. No. | Agency | Area | Name Of Structure | Scope in MT | Drawings receipt as on date | Balance drawings yet to be recive | Receipt Up to May-22 | Cumm Receipt As on June-22 | Cumm Receipt As on Aug'22 | Piping Receipt Sep'22 |  | Cumm Receipt As on Sep'22 | Execution Up to Aug-22 | Piping Execution Sep'22 |  | Execution Cumm As on Sep-22 | Balance qty | % of Execution | 12708
[10 empty] | Plan | Actual |  |  | Plan | Actual
1 |  | WTP | Furnace Proper/BLT/ cast house | 120000 | 105000 | 15000 | 126000 | 100000 | 330000 | 18000 | 15000 | 345000 | 5000 | 5200 | 62.2 | 5000 | 115000 | 4.1667 | Under Hearth Cooling Pipe, Radius Pipes, Rigid Pipes, Isometric Transmittal T 255, Isometric 271, Isometric 272, Isometric 274. Isometric 275, Isometric 277, Isometric 279, Isometric 280, Isometric 287, Isometric T286
2 |  |  | Gas Cleaning Plant & TRT | 12000 | 7000 | 5000 | [6 empty] | 0 |  |  | 0 | 12000 | 0
3 |  |  | Make-up water & Fire water | 89000 | 60000 | 29000 | [6 empty] | 0 |  |  | 0 | 89000 | 0
4 |  |  | Stock House | 4000 | 0 | 4000 | [6 empty] | 0 |  |  | 0 | 4000 | 0
5 |  |  | Stoves | 10000 | 6600 | 3400 | [6 empty] | 0 |  |  | 0 | 10000 | 0
6 |  |  | WTP Pump House | 106000 | 80000 | 26000 | [6 empty] | 14025 | 10000 | 7720 | 21745 | 84255 | 20.5142 | Drawings received from MECON - 18th June 2022
7 |  |  | Emergency overhead tank | 7000 | 0 | 7000 | [6 empty] | 0 |  |  | 0 | 7000 | 0
8 |  | Utilities | Furnace Proper/BLT/ cast house | 30000 | 3400 | 26600 | 18449 | 31166 | 60000 |  | 0 | 60000 | 0 |  |  | 0 | 30000 | 0
9 |  |  | Gas Cleaning Plant & TRT | 10000 | 700 | 9300 | [6 empty] | 0 |  |  | 0 | 10000 | 0
10 |  |  | Stock House | 5000 | 0 | 5000 | [6 empty] | 0 |  |  | 0 | 5000 | 0
11 |  |  | Stoves | 5000 | 2900 | 2100 | [6 empty] | 0 |  |  | 0 | 5000 | 0
12 |  |  | Inter plant utility pipeline | 50000 | 10000 | 40000 | [6 empty] | 0 |  |  | 0 | 50000 | 0
|  |  | Trough Cooling system | 11000 | 11000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0
13 |  | SGP | Isometric drawings | 35000 | 35000 | 0 | 10000 | 856 | 10856 |  | 0 | 10856 | 912 | 2356 |  | 912 | 34088 | 2.6057
14 |  | PCI & CPP | Isometric drawings | 5000 | 0 | 5000 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 5000 | 0
15 |  | Blower, TRT & Air Compressor | Isometric drawings | 10000 | 0 | 10000 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 10000 | 0
16 |  | Hydraulics & Lubrication | BLT | 3612 | 3612 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 3612 | 0
17 |  |  | Cast House | 8100 | 8030 | 70 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 8100 | 0
18 |  |  | Gas Cleaning Plant | 368 | 368 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 368 | 0
19 |  |  | Stock House | 3000 | 0 | 3000 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 3000 | 0
20 |  |  | Stoves | 11585 | 11585 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 11585 | 0
21 |  |  | PCI | 500 | 500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 500 | 0
22 |  |  | Blower | 800 | 0 | 800 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 800 | 0
23 |  |  | TRT | 800 | 0 | 800 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 800 | 0
24 |  |  | Central Filling station | 300 | 0 | 300 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 300 | 0
|  |  | Grand Totoal | 538065 | 345695 | 192370 | 154449 | 132022 | 286471 | 18000 | 15000 | 301471 | 19937 | 17556 | 7782.2 | 27657 | 510408 | 5.1401

## Sheet7 (hidden)
SI. No. | Area | Civil | [5 empty] | Structural |  |  |  |  | Equipment in MT |  |  | Piping in Inch-Mtr
|  | Piling in Nos |  |  | RCC in Cum |  |  | Fab in MT |  |  | Erec in MT
|  | Est Scope | Drgs received | Executed | Est Scope | Drgs received | Executed | Est. Scope | Drgs received | Executed | Est. Scope | Executed | Est. Scope | Drgs received | Executed | Est Scope | Drgs received | Executed
1 | BF Proper | 731 | 731 | 727 | 9700 | 9480 | 9442 | 5972 | 5959 | 3843 | 5972 | 1952 | 3016 | 3016 | 0 | 153600 | 55810 | 5000
2 | CH Proper | 1294 | 1294 | 1294 | 8540 | 4195 | 3868 | 8764 | 8322 | 0 | 8764 | 0 | 570 | 570 | 0 | 8100 | 8030 | 0
3 | Hot Blast Stoves | 1128 | 1128 | 1128 | 9260 | 6842 | 5246 | 7394 | 7484 | 1785 | 7394 | 992 | 2328 | 743 | 0 | 19000 | 0 | 0
4 | Stock House | 1557 | 1427 | 1360 | 13459 | 6558 | 5859 | 20680 | 15046 | 9026 | 20680 | 4739 | 3000 | 100 | 0 | 12000 | 0 | 0
5 | Slag Granulation Plant & Cranes | 578 | 578 | 578 | 18580 | 16096 | 8240 | 1209 | 1012 | 0 | 1209 | 0 | 1043 | 853.7 | 0 | 35000 | 35000 | 0
6 | Cyclone & GCP | 136 | 136 | 136 | 3000 | 1111 | 995 | 1928 | 1481 | 475 | 1928 | 32 | 506 | 68 | 0 | 22500 | 368 | 0
7 | Blower House & Compressor House | 428 | 428 | 422 | 7500 | 6237 | 1328 | 2950 | 1325 | 0 | 2950 | 0 | 928 | 928 | 0 | 8000 | 0 | 0
8 | TRT | 126 | 126 | 126 | 3000 | 936 | 875 | 500 | 375 | 0 | 500 | 0 | 475 | 475 | 0 | 4000 | 0 | 0
9 | Gas Network lines | 374 | 304 | 124 | 3551 | 2536 | 0 | 3599 | 1266 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | PCI & CPP | 416 | 416 | 407 | 7000 | 3596 | 2004 | 5240 | 3168 | 2106 | 5240 | 0 | 1800 | 849.4 | 0 | 5500 | 0 | 0
12 | WTP & Utility | 358 | 300 | 269 | 9110 | 8016 | 6560 | 975 | 767 | 149 | 975 | 68 | 600 | 300 | 0 | 252000 | 0 | 0
13 | De-dusting Systems (CH&SH) | 460 | 180 | 156 | 5000 | 443 | 0 | 7203 | 1742 | 0 | 7203 | 0 | 660 | 0 | 0 | 0 | 0 | 0
14 | E&I | 992 | 992 | 992 | 5549 | 5039 | 2310 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | TLRS Building | 0 | No Piles |  | 1951 | 2269 | 1390 | 1145 | 1145 | 0 | 1145 | 0 | 2280 | 1980 | 0 |  | 0 | 0
16 | Miscellaneous |  |  | 25 |  | 8149 | 0 | 880 |  |  | 880 |  | 79 | 66.04 |  | 300 | 0
| Total | 8578 | 8040 | 7744 | 105200 | 81503 | 48117 | 69189 | 49092 | 17384 | 69189 | 7783 | 17285 | 9949.14 | 0 | 520000 | 99208 | 5000

## Sheet8 (hidden)
Piling | Nos | 8500 | 8040 | 400 | 198 | 7746 | 91.1294 | 754
Civil | CuM | 105000 | 76110 | 4198 | 2354 | 48309 | 46.0086 | 56691
Structural Fab | MT | 69092 | 47487 | 2463 | 532 | 13709 | 19.8417 | 55383
L&T Scope | MT | 49986 | 40407 | 1554 | 906 | 15283 | 30.5746 | 34703
DS Engg Scope | MT | 5240 | 3168 | 454 | 341 | 2123 | 40.5153 | 3117
JSSL Scope | MT | 9566 | 3767 | 455 | 159 | 159 | 1.6621 | 9407
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 4300
Structural Erec | MT | 69092 | 47487 | 2176 | 195 | 6344 | 9.182 | 62748
L&T Scope | MT | 49986 | 40407 | 1741 | 470 | 7824 | 15.6524 | 42162
DS Engg Scope | MT | 5240 | 3168 | 285 | 45 | 45 | 0.85878 | 5195
JSSL Scope | MT | 9566 | 3767 | 150 | 87 | 88 | 0.91992 | 9478
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 4300

## Refractory
Project Name - REFRACTORY SCOPE
Area | Scope in MT | Drawing Receipt in MT | Balance drawings yet to be recive | Receipt (MT) Sep'22 |  | Cumm Refractory Receipt MT | Execution Completed Up to July-22 | Erection Plan Aug'22 |  | Cumm As on Aug' 22 | Balance qty | % of Execution
|  |  |  | Plan | Actual |  |  | Plan | Actual
Furnace Proper area | 4724 | 4724 | 0 | 300 |  | 340 | 130 | 0 | 0 | 130 | 4594 | 2.7519
Hot Blast system | 19050.3 | 19050 | 0.3 | 1700 | 1500 | 7660 | 0 | 0 | 0 | 0 | 19050.3 | 0
Cast House | 7640 | 3140 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 7640 | 0
Stock House | 1300 | 1300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1300 | 0
Grand Total | 32714.3 | 28214 | 4500.3 | 2000 | 1500 | 8000 | 130 | 0 | 0 | 130 | 32584.3 | 0.39738
24.4541

## Graphs
S.No |  | Area | Scope | Dwg Issued | % Dwg Issued | Work Done | % wrt Scope | % wrt Dwg issued | Plan | Actual | FTD
1 | Piling | Furnace | 7102 | 7040 | 99.13% | 6827 | 96.13% | 96.97% | 100 | 35 | 0
2 |  | Stock House | 1576 | 1514 | 96.07% | 1463 | 92.83% | 96.63%
1 | Civil | Furnace | 85188.5 | 79565.5 | 93.4% | 56132.41 | 65.89% | 70.55% | 3347 | 1470 | 228
2 |  | Stock House | 7804.5 | 6714.5 | 86.03% | 6359.5 | 81.49% | 94.71% | 212 | 34 | 0
|  | Civil | 92993 | 86280 | 92.78% | 62491.91 | 67.2% | 72.43% | 3559 | 1504 | 228
1 | Structural Erection | L&T | 51654.661 | 46887.541 | 90.77% | 13207.5 | 25.57% | 28.17% | 1993 | 553.6 | 26
2 |  | JSSL | 7545.26 | 4635.5 | 61.44% | 1873.11 | 24.82% | 40.41% | 550 | 283.04 | 30.71
3 |  | DSE | 5290 | 3933 | 74.35% | 939 | 17.75% | 23.87% | 86.67 | 57 | 5
4 |  | Others | 1972.918 | 672.918 | 34.11% | 0 | 0% | 0% | 0 | 0 | 0
|  | Total | 66462.839 | 56128.959 | 84.45% | 16019.61 | 24.1% | 28.54% | 2629.67 | 893.64 | 61.71
Project NameOVERALL PROGRESS
Project Name MONTHLY PLAN VS ACTUAL

## Sheet9 (hidden)
Piling | Nos | 8500 | 8062 | 80 | 0 | 7805 | 91.8235 | 695
Civil | CuM | 105000 | 84179 | 4029 | 379 | 50116 | 47.7295 | 54884
Structural Fab | MT | 70142 | 50265 | 2879 | 137 | 18186 | 25.9274 | 51956 | 924
L&T Scope | MT | 51166 | 42834 | 1780 | 38 | 15673 | 30.6317 | 35493 | 835
DS Engg Scope | MT | 5260 | 3392 | 351 | 17 | 2177 | 41.3878 | 3083 | 460
JSSL Scope | MT | 9416 | 3895 | 748 | 82 | 336 | 3.5684 | 9080 | 755
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 4300 | 445
Structural Erec | MT | 70142 | 50265 | 3083 | 85 | 8754 | 12.4804 | 61388 | 490
L&T Scope | MT | 51166 | 42834 | 2131 | 3 | 8387 | 16.3917 | 42779
DS Engg Scope | MT | 5260 | 3392 | 352 | 55 | 191 | 3.6312 | 5069
JSSL Scope | MT | 9416 | 3895 | 600 | 27 | 176 | 1.8692 | 9240
Other Agency | MT | 4300 | 144 | 0 | 0 | 0 | 0 | 4300
Equipment
Receipt | MT | 17129 | 9949 | 1074 | 50 | 531 | 3.1 | 16598
Erection | MT | 17129 | 9949 | 50 | 4 | 24 | 0.14011 | 17119
Refractory
Receipt | MT | 32714 | 28214 | 200 | 0 | 1600 | 4.89 | 31114
Erection | MT | 32714 | 28214 | 0 | 0 | 130 | 0.4 | 32584
Piping Erection | Inch-m | 520000 | 99028 | 0 | 0 | 5000 | 0.96 | 515000
Electrical
Cable Tray | KM | 29.5 | NA | 0 | 0 | 0 | 0 | 29.5
Cables | KM | 1255 | NA | 0 | 0 | 0 | 0 | 1255
Panels | Nos | 1275 | NA | 0 | 0 | 0 | 0 | 1275
Transformers | Nos | 33 | NA | 0 | 0 | 0 | 0 | 33

## Sheet10 (hidden)
Est Scope | Drgs received | Executed | Est Scope | Drgs received | Executed | Est. Scope | Drgs received | Executed | Est. Scope | Executed | Est. Scope | Drgs received | Executed | Est Scope | Drgs received | Executed
731 | 731 | 727 | 9700 | 9480 | 9442 | 5972 | 5995 | 4183 | 5972 | 2146 | 3016 | 3016 | 0 | 153600 | 55810 | 5000
1294 | 1294 | 1294 | 8540 | 4195 | 3882 | 8764 | 9104 | 0 | 8764 | 0 | 570 | 570 | 0 | 8100 | 8030 | 0
1128 | 1128 | 1128 | 9260 | 6842 | 5260 | 7394 | 7484 | 2070 | 7394 | 1124 | 2328 | 743 | 0 | 19000 | 0 | 0
1557 | 1446 | 1360 | 13459 | 6579 | 5859 | 20680 | 15178 | 9526 | 20680 | 4989 | 3000 | 100 | 0 | 12000 | 0 | 0
578 | 578 | 578 | 18580 | 16350 | 8967 | 1209 | 1012 | 0 | 1209 | 0 | 1043 | 854 | 0 | 35000 | 35000 | 0
136 | 136 | 136 | 3000 | 1111 | 995 | 1928 | 1481 | 537 | 1928 | 128 | 506 | 68 | 0 | 22500 | 368 | 0
428 | 428 | 422 | 7500 | 6237 | 1414 | 2950 | 1325 | 0 | 2950 | 0 | 928 | 928 | 0 | 8000 | 0 | 0
126 | 126 | 126 | 3000 | 937 | 904 | 500 | 375 | 0 | 500 | 0 | 475 | 475 | 0 | 4000 | 0 | 0
374 | 304 | 154 | 3551 | 1495 | 470 | 3599 | 1266 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 416 | 407 | 7000 | 3633 | 2381 | 5240 | 3392 | 2256 | 5240 | 191 | 1800 | 849 | 0 | 5500 | 0 | 0
358 | 303 | 300 | 9110 | 9539 | 6711 | 975 | 767 | 364 | 975 | 176 | 600 | 400 | 0 | 252000 | 0 | 0
460 | 180 | 156 | 5000 | 443 | 0 | 7203 | 1742 | 0 | 7203 | 0 | 660 | 0 | 0 | 0 | 0 | 0
992 | 992 | 992 | 5549 | 6920 | 2417 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | No Piles |  | 1951 | 2269 | 1417 | 1145 | 1145 | 0 | 1145 | 0 | 2280 | 1980 | 0 |  | 0 | 0
|  | 25 |  | 8149 | 0 | 880 |  |  | 880 |  | 79 | 66 |  | 300 | 0
8578 | 8062 | 7805 | 105200 | 84179 | 50119 | 69189 | 50266 | 18936 | 69189 | 8754 | 17285 | 10049 | 0 | 476600 | 99208 | 5000

## Strl Erec Day Wise Progress (hidden)
BUILDING STRUCTURE ERECTION PROGRESS IN MT | [8 empty] | 2022-01-22
SI. No. | Name Of Structure | Est Scope in MT | BOQ Received | Drawings receipt as on date | Up to Dec-21 | Cumm As on Jan-22 | Balance qty | % of Execution | TOTAL PLAN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL ACHIEVED
1 | Furnace Tower | 3000 | 3138
| Lower Tower |  | 789 | 876.45 | 61 | 61 | 815.45 | 0 | 124 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| Middle Tower |  | 1507 | 1470.097 | 0 | 0 | 1470.097 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| Upper Tower |  | 842 | 52.5 | 0 | 0 | 52.5 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| Fixed & Movable Platform |  |  | 89 | 0 | 0 | 89 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
2 | Tuyere Platform |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
3 | Elevator Tower | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
4 | Cast House | 5000 | 2988 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| Road ramp to Cast House | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
5 | Stove Housing | 1600 | 2369.17 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
6 | WHRS structures | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
7 | Stock House Proper | 9575 | 3759.65 | 3759.65 | 950 | 959.5 | 2800.15 | 0 | 489 | 1: 0; 2: 0; 3: 0; 4: 7; 5: 2.5 | 9.5
| Fines Building |  | 704.8 | 838.401 | 0 | 0 | 838.401 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| Surge Hopper Building |  | 632 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| MCC |  | 1100 | 1100 | 0 | 0 | 1100 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
8 | Cyclone Structure | 600 | 474.81 | 643.35 | 0 | 0 | 643.35 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
9 | Scrubber Structures | 300 | 207.331 | 152.14 | 0 | 0 | 152.14 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
10 | Crude Gas Main Structure | 80 | 80 | 80.068 | 0 | 0 | 80.068 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
11 | Flare Stack Structures | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
12 | Clean Gas Main | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
13 | IPPL | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
14 | SGP East | 1000 | 180 | 180 | 0 | 0 | 180 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
15 | SGP West |  |  |  | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
16 | CPP/PCI Building | 3000 | 1988 | 1560.04 | 0 | 0 | 1560.04 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
17 | BF Circulating water and Firefighting pump house & OHT | 825 | 767 | 274.358 | 0 | 0 | 274.358 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
18 | SGP Pump house | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
19 | Pipe bridge from BF pump house to furnace tower | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
20 | Cast House Dedusting | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
21 | Stock House Dedusting | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
22 | Blower Building | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
23 | Compressor Building | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
24 | TRT Building | 500 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
25 | Electrical Rooms | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
26 | Cable Bridges | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
27 | TLRS Building | 700 | 1145 | 632 | 0 | 0 | 632 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
28 | Miscellaneous | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| TOTAL | 37375 | 19908.761 | 11708.054 | 1011 | 1020.5 | 10687.554 | 8.7162 | 613 | 0 | 0 | 0 | 7 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
TECHNOLOGICAL STRUCTURE ERECTION PROGRESS IN MT | [8 empty] | 2022-01-22
SI. No. | Name Of Structure | Est Scope in MT | BOQ Received | Drawings receipt as on date | Up to Dec-21 | Cumm As on Jan-22 | Balance qty | % of Execution | TOTAL PLAN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL ACHIEVED
1 | BF Shell Plates (ASTM 516 GR 70) | 1500 | 1340 | 1340 | 539 | 539 | 801 | 40.2239 | 188 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
2 | Bustle Main(ASTM 516 GR 70) | 245 | 165 | 154.21 | 0 | 0 | 154.21 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
3 | Top Gas Piping(UTDC) | 400 | 410.6 | 410.6 | 0 | 0 | 410.6 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0 | 33
4 | Cast house Runners & Runner Cover | 1550 | 1214.6 | 1214.6 | 0 | 0 | 1214.6 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0 | 4
5 | Stove Shell (16Mo3/WELACC) | 2650 | 1888.5 | 1809.97 | 149.6 | 162.5 | 1647.47 | 8.978 | 90 | 1: 0; 2: 0; 3: 0; 4: 6.4; 5: 6.5 | 12.9 | 36.1
6 | Hot Blast Main (ASTM 516 GR 70) | 450 | 200 | 237 | 0 | 0 | 237 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0 | 12
7 | Mixed Gas Main in HB Stoves | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0 | 35
8 | Combustion Air Main in HB Stove |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0 | 29.5
9 | BF GAS MAIN (STOVES) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
10 | Waste Gas Chimney | 200 | 275 | 275 | 0 | 0 | 275 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
11 | Waste Gas Main | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
12 | Backdraft Chimney | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
13 | Waste Heat Recovery System Duct Work | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
14 | Material handling System | 9150 | 5007 | 4438.046 | 273 | 273 | 4165.046 | 6.1514 | 270 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
15 | Fines Building |  | 1057.2 | 574.606 | 0 | 0 | 574.606 | 1 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
15 | Cyclone Shell (ASTM 516 GR 70) | 300 | 384.7 | 202 | 0 | 0 | 202 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
16 | Scrubber GCP | 470 | 271.3 | 41 | 0 | 0 | 41 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
17 | Demister |  | 241 | 101 | 0 | 0 | 101 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
18 | Crude Gas Main | 100 | 54.48 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
19 | Semi Clean Gas Line | 30 | 38 | 38 | 0 | 0 | 38 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
20 | Clean Gas Main Duct | 300 | 61.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
21 | Flare Stack | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
22 | BF Gas IPPL | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
23 | SGP (E&W)Condensating Tower, Buffer tank,etc | 400 | 316 | 170.79 | 0 | 0 | 170.79 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
24 | SGP Ducting | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
25 | Cold Blast Main (ASTM 516 GR 70) | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
26 | Cold blast IPPL(ASTM 516 GR 70) | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
27 | Cast House dedusting Duct Work | 1460 | 323 | 323 | 0 | 0 | 323 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
28 | Stock House Dedusting Duct work | 1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
29 | PCI & CPP Technological Structures | 1040 | 0 | 196 | 0 | 0 | 196 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
30 | Miscellaneous | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
| TOTAL | 24405 | 13248.24 | 11525.822 | 961.6 | 974.5 | 10551.322 | 8.4549 | 548 | 0 | 0 | 0 | 6.4 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9

## Sheet3 (hidden)
9364
1046
2197
5028
1012
759
0
0
0
0
3182
0
0
0
123
22711
22831
120

## Sheet2 (hidden)
Middle Tower - 30.10.2021
JVML TECHNOGICAL STRUCTURE OCT'21 PROGRESS | [9 empty] | Scrubbe Shell Drgs Wt |  | 066504FC1093 | 1613.89
Area | LnT |  |  | JVML |  |  | Difference |  |  | Ring1 | 11534.49 | 066504FC1094 | 6179.01
| Plan | Actual | Cumm | Plan | Actual | Cumm | Actual | Cumm |  | Ring2 | 6059 | 066504FC1095 | 47368.73
Furnace | 199 | 180 | 1249 | 260 | 256 | 691 | -76 | 558 |  | Ring3 | 5096.53 | 066504FC1096 | 927.9
Bustle Pipe | 0 | 60 | 60 | 0 | 53 | 53 | 7 | 7 |  | Ring4 | 4662.55 | 066504FC1097 | 1839.67
HBS | 346 | 247 | 416 | 200 | 269 | 269 | -22 | 147 |  | Ring5 | 5128.01 | 066504FC1098 | 381.16
Cyclone | 61 | 21 | 53.8 | 30 | 12.5 | 45.5 | 8.5 | 8.3 |  | Ring6 | 5510.55 | 066504FC1099 | 746.98
Stock House | 697 | 394 | 586 | 670 | 394 | 586 | 0 | 0 |  | Ring7 | 3124.22 | 066504FC1100 | 1127.05
Total (A) | 1303 | 902 | 2364.8 | 1160 | 984.5 | 1644.5 | -82.5 | 720.3 | Total |  | 41115.35 | 066504FC1101 | 240.89
[11 empty] | 41.1153 | 066504FC1102 | 492.61
JVML BUILDING STRUCTURE OCT'21 PROGRESS | [9 empty] | Demister |  | 066504FC1103 | 3678.07
Area | LnT |  |  | JVML |  |  | Difference |  |  | Ring 1 | 4820.26 | 066504FC1104 | 455.9
| Plan | Actual | Cumm | Plan | Actual | Cumm | Actual | Cumm |  | Ring 2 | 2623.48 | 066504FC1105 | 1011.11
Furnace | 145 | 0 | 0 | 150 | 0 | 0 | 0 | 0 |  | Ring3 | 2281.37 | 066504FC1106 | 2535.74
Stock House | 663 | 575 | 1673 | 770 | 575 | 1673 | 0 | 0 |  | Ring4 | 2554.33 | 066504FC1107 | 1569.26
OHT | 26 | 27 | 27 | 0 | 27 | 27 | 0 | 0 |  | Ring5 | 2941.85 | 066504FC1108 | 671.1
Total (B) | 834 | 602 | 1700 | 920 | 602 | 1700 | 0 | 0 |  | Ring6 | 3467.98 | 066504FC1109 | 1408.68
Grand Total (A+B) | 2137 | 1504 | 4064.8 | 2080 | 1586.5 | 3344.5 | -82.5 | 720.3 |  | Ring7 | 3467.98 | 066504FC1110 | 4632.78
[10 empty] | Ring8 | 3467.98 | 066504FC1111 | 3411.94
[10 empty] | Ring9 | 3467.98 | 066504FC1112 | 180.27
[10 empty] | Ring10 | 3467.98 | 066504FC1113 | 1531.7
[10 empty] | Ring11 | 3467.98 | 066504FC1114 | 776.11
[10 empty] | Ring12 | 3467.98 | 066504FC1115 | 2332.63
[10 empty] | Ring13 | 3467.98 | 066504FC1116 | 2332.75
[10 empty] | Ring14 | 3467.98 | 066504FC1117 | 5351.14
[10 empty] | Ring15 | 3467.98 | 066504FC1118 | 13970.97
[11 empty] | 49901.09 | 066504FC1119 | 200.17
[11 empty] | 49.9011 | 066504FC1120 | 735.83
[12 empty] | 066504FC1121 | 1885.57
[12 empty] | 066504FC1122 | 1934.91
[12 empty] | 066504FC1123 | 1712.62
[12 empty] | 066504FC1124 | 3876.97
[12 empty] | 066504FC1125 | 1792.8
[12 empty] | 066504FC1126 | 1792.8
[12 empty] | 066504FC1127 | 1837.76
[12 empty] | 066504FC1128 | 2695.09
[12 empty] | 066504FC1129 | 890.93
[12 empty] | 066504FC1130 | 1025.01
[12 empty] | 066504FC1131 | 1149.34
[12 empty] | 066504FC1132 | 1568.88
[12 empty] | 066504FC1133 | 1756.51
[12 empty] | 066504FC1134 | 5503.55
[12 empty] | 066504FC1135 | 2150.54
[12 empty] | 066504FC1136 | 5109.79
[12 empty] | 066504FC1137 | 5572.11
[12 empty] | 066504FC1138 | 14714.88
[12 empty] | 066504FC1139 | 3721.21
[12 empty] | 066504FC1140 | 4080.1
[12 empty] | 066504FC1141 | 1700.84
[12 empty] | 066504FC1142 | 521.91
[12 empty] | 066504FC1143 | 8823.13
[12 empty] | 066504FC1144 | 7896.12
[12 empty] | 066504FC1145 | 6557.95
197975.36
197.9754